## Sheet1
Keith Conarroe Annuitant Work Plan
Project
| May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | totals
Wells 12,15,22 | 30 | 30 | 20 | 10 | 10 | 10 | 10 | 10 | 130
Complete analysis and design of facilities to maximize production capability of wells 12,15,22. Get project out to bid for construction.
3.5 MG Water storage tank | 10 | 30 | 20 | 20 | 20 | 10 | 10 | 10 | 130
Complete bid process for Design Build of Water Tank Project
Media regeneration & Well 24 pH adjustment |  | 20 | 20 | 30 | 30 | 30 | 20 | 10 | 160
Finalize technical and financial feasibility and regulatory approval of regeneration methodology
M1 direct connect |  |  | 20 | 10 | 10 | 20 | 10 | 10 | 80
Coordinate construction
Water permit training |  |  |  | 10 | 10 | 10 | 10 | 10 | 50
Totals: | 40 | 80 | 80 | 80 | 80 | 80 | 60 | 50 | 550