## Sheet1
Keith Conarroe Annuitant Work Plan
Project | Hours
| Jun | Jul | Aug | Sept | Oct | Nov | Dec | totals
Wells 12, 15 & 22 | 50 | 50 | 50 | 30 | 10 |  |  | 190
Identify options and design facilities to maximize production capability of wells 12, 15 & 22. Get project out to bid for construction.
Arsenic Filtration Media Regeneration | 10 | 10 | 10 | 20 | 20 | 20 | 40 | 130
Finalize SOP for regeneration methodology, complete pilot-scale testing at Well 20, and obtain regulatory approval of regeneration methodology.
London/Austin Metering Project | 20 | 20 | 20 | 20 | 40 | 40 | 20 | 180
Re-bid project, and manage contractor through end of construction.
Water Regulatory Training | Hours Sept: 10; Hours Oct: 10; Hours Nov: 20; Hours Dec: 20 | 60
Train Fernando to prepare the various reporting documents required by the City’s water permit: quarterly arsenic report, consumer confidence report, annual water report, urban water management plan, water supply assessments and evaluations, etc.
Totals: | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 560