SECTION 00700

GENERAL CONDITIONS

ARTICLE 1 – DEFINITIONS AND TERMINOLOGYtc "ARTICLE 1 – DEFINITIONS AND TERMINOLOGY"
1.01
Defined Terms tc "1.01  Defined Terms " \l 2
A.
Wherever used in the Contract Documents and printed with initial capital letters, the following terms have the meanings indicated which are applicable to both the singular and plural thereof.  In addition to terms specifically defined, terms with initial capital letters in the Contract Documents include references to identified articles and paragraphs, and the titles of other documents or forms.  

1.
Addenda: Written or graphic instruments issued prior to the opening of Proposals which clarify, correct or change the Request for Proposals or the Contract Documents.

2.
Agreement: The written instrument which is evidence of the agreement between Owner and Design/Builder covering the Work.

3.
Application for Payment: The form which is to be used by Design/Builder in requesting progress or final payments and which is to be accompanied by such supporting documentation as is required by the Contract Documents.

4.
Asbestos: Any material that contains more than one percent asbestos and is friable or is releasing asbestos fibers into the air above current action levels established by the United States Occupational Safety and Health Administration.

5.
Bonds: Performance and payment bonds and other instruments of security.

6.
Change Order: A written order which is signed by Design/Builder and Owner  which authorizes an addition, deletion or revision in the Work, or an adjustment in the Contract Price or the Contract Times, issued on or after the Effective Date of the Agreement.

7.
Claim: A demand or assertion by Owner or Design/Builder seeking an adjustment of Contract Price or Contract Times, or both, or other relief with respect to the terms of the Contract.  A demand for money or services by a third party is not a claim.

8.
Conceptual Documents: The drawings, specifications, project manual and/or other graphic or written materials, criteria and information concerning Owner's requirements for the Project, such as design objectives and constraints, space, capacity and performance requirements, flexibility and expandability, including those items enumerated in the Request for Proposals which show or describe the character and scope of, or relate to, the Work to be performed or furnished and which have been prepared by or for Owner.

9.
Construction: The part of the Work that is the result of performing or furnishing of labor, the furnishing and incorporating of materials and equipment into the Work and the furnishing of services (other than Design Professional Services) and documents, all as required by the Contract Documents.

10.
Construction Subagreement: A written agreement between Design/Builder and a construction Subcontractor for provision of Construction.

11.
Contract: The entire and integrated written agreement between Owner and Design/Builder concerning the Work including conceptual documents and project manual.  The Contract supersedes prior negotiations, representations, or agreements, whether written or oral.

12.
Contract Documents: Those items so designated in the Agreement.  Only printed or hard copies of the items listed in the Agreement are Contract Documents.

13.
Contract Price: The moneys payable by Owner to Design/Builder for completion of the Work in accordance with the Contract Documents.

14.
Contract Times: The numbers of days or the dates stated in the Agreement to (i) achieve Substantial Completion, and (ii) complete the Work so that it is ready for final payment in accordance with Article 14.

15.
Design/Builder: The individual or entity with whom Owner has entered into the Agreement.

16. Designer: The individuals or entities with a California license to practice engineering or architecture, as employees or Subcontractors to Design/Builder, designs the works, stamps and signs the plans and specifications.
17.
Design Subagreement: A written agreement between Design/Builder and a design professional for provision of Design Professional Services.

18.
Design Professional Services: That part of the Work comprised of services relating to the preparation of Drawings, Specifications, and other design submittals specified by the Contract Documents and required to be performed by licensed design professionals, as well as other services provided by or for licensed design professionals during Bidding/Negotiating, Construction, or Operational phases.

19.
Drawings: Those portions of the Construction Documents prepared by or for Design/Builder and approved by Owner consisting of drawings, diagrams, illustrations, schedules and other data which show the scope, extent, and character of the Work.

20.
Effective Date of the Agreement: The date indicated in the Agreement on which it becomes effective, but if no such date is indicated it means the date on which the Agreement is signed and delivered by the last of the two parties to sign and deliver.  
21.
Owner’s Engineer: The Owner’s engineering consultant assigned to the Project, as listed in the Supplementary Conditions.
22.
Field Order: A written order issued by Owner which orders minor changes in the Work but which does not involve a change in the Contract Price or the Contract Times.

23.
Hazardous Environmental Condition: The presence at the Site of Asbestos, Hazardous Waste, PCB's, Petroleum Products or Radioactive Materials in such quantities or circumstances that may present a substantial danger to persons or property exposed thereto on connection with the Work.

24.
Hazardous Waste: The term Hazardous Waste shall have the meaning provided in Section 1004 of the Solid Waste Disposal Act (42 USC Section 6903) as amended from time to time.

25.
Laws or Regulations: Any and all applicable laws, rules, regulations, ordinances, codes, and orders of any and all governmental bodies, agencies, authorities and courts having jurisdiction.

26.
Liens: Charges, security interests or encumbrances upon real property or personal property.

27.
Milestone: A principal event specified in the Contract Documents relating to an intermediate completion date or time prior to Substantial Completion of all the Work.

28.
Notice of Award: The written notice by Owner to the successful proposer stating that upon compliance by the successful proposer with the conditions precedent included therein, within the time specified, Owner will sign and deliver the Agreement.

29.
Notice to Proceed: A written notice given by Owner to Design/Builder fixing the date on which the Contract Times will commence to run and on which Design/Builder shall start to perform the Work.

30.
Owner: City of Manteca.

31.
Owner's Consultant: An individual or entity with whom the Owner may contract to furnish services to Owner with respect to the Project and who is identified as such in the Supplementary Conditions.

32.
Partial Utilization: Use by Owner of a substantially completed part of the Work for the purpose for which it is intended (or a related purpose) prior to Substantial Completion of all the Work.

33.
PCBs: Polychlorinated biphenyls.

34.
Petroleum: Petroleum, including crude oil or any fraction thereof which is liquid at standard conditions of temperature and pressure (60 degrees Fahrenheit and 14.7 pounds per square inch absolute), such as oil, petroleum, fuel oil, oil sludge, oil refuse, gasoline, kerosene, and oil mixed with other non-Hazardous Wastes and crude oils.

35.
Project: The total construction of which the Work to be provided under the Contract Documents may be the whole, or a part as indicated elsewhere in the Contract Documents.

36.
Proposal: The documents submitted by Design/Builder in response to the Request for Proposals setting forth the design concepts, proposed prices, and other conditions for the Work to be performed.

37.
Radioactive Material: Source, special nuclear, or byproduct material as defined by the Atomic Energy Act of 1954 (42 USC Section 2011 et seq.) as amended from time to time.

38.
Request for Proposals: The document prepared by Owner specifying and describing Owner's objectives and the procedure to be followed in preparing and submitting a Proposal and awarding a contract.

39.
Resident Project Representative: The authorized representative of Owner assigned to the Project, as listed in the Supplementary Conditions.

40.
Schedule of Values: A schedule prepared by Design/Builder and acceptable to Owner indicating that portion of the Contract Price to be paid for each major component of the Work.

41.
Site: Lands or other areas designated in the Contract Documents as being furnished by Owner upon which Construction is to be performed, including rights-of-way and easements for access thereto, and such other lands furnished by Owner which are designated for use of Design/Builder.

42.
Specifications: The part of the Construction Documents prepared by or for Design/Builder and approved by Owner consisting of written technical descriptions of materials, equipment, construction systems, standards and workmanship as applied to the Work and certain administrative details applicable thereto.

43.
Standards and Codes: Any and all applicable standards and codes of any and all bodies, agencies, and authorities having specific or general industry acceptance.  Standards and codes refer to the latest issue or version.
44.
Subcontractor: An individual or entity other than a Supplier having a direct contract with Design/Builder or with any other Subcontractor for the performance of a part of the Work including design firms, design consultants and design professionals. 

45.
Submittal: A written or graphic document prepared by or for Design/Builder which is required by the Contract Documents to be submitted to Owner by Design/Builder.  Submittals may include Drawings, Specifications, progress schedules, shop drawings, samples, cash flow projections, and Schedules of Values.  Submittals other than Drawings and Specifications are not Contract Documents.

46.
Substantial Completion: The time at which the Work (or a specified part) has progressed to the point where it is sufficiently complete, in accordance with the Contract Documents, so that the Work (or a specified part) can be utilized for the purposes for which it is intended.  The terms "substantially complete" and "substantially completed" as applied to all or part of the Work refer to Substantial Completion thereof.

47.
Supplementary Conditions: The part of the Contract Documents which amends or supplements these General Conditions.

48.
Supplier: A manufacturer, fabricator, supplier, distributor, materialman or vendor having a direct contract with Design/Builder or with any Subcontractor to furnish materials or equipment to be incorporated in the Work by Design/Builder or any Subcontractor.

49.
Unit Price Work: Work to be paid for on the basis of unit prices.

50.
Work: The entire design and construction or the various separately identifiable parts thereof required to be performed or furnished under the Contract Documents.  Work includes and is the result of performing or furnishing Design Professional Services and Construction required by the Contract Documents.

51.
Work Change Directive: A written directive to Design/Builder, issued on or after the Effective Date of the Agreement and signed by Owner ordering an addition, deletion or revision in the Work, or responding to differing site conditions under which the Work is to be performed or to emergencies.  A Work Change Directive will not change the Contract Price or the Contract Times, but is evidence that the parties expect that the change directed or documented by a Work Change Directive will be incorporated in a subsequently issued Change Order following negotiations by the parties as to its effect, if any, on the Contract Price or Contract Times.

1.02
Terminology tc "1.01  Defined Terms " \l 2
A.
The words and terms discussed in Paragraph 1.02.B are not defined terms, but when used in the Contract Documents have the indicated meanings.
B.
Intent of Certain Terms or Adjectives:
1.
The word "day" shall constitute a calendar day of 24 hours measured from midnight to the next midnight.

2.
The word "defective," when modifying the word "Construction" refers to Construction that is unsatisfactory, faulty, or deficient in that it does not conform to the Contract Documents, or does not meet the requirements of any inspection, reference standard, test or approval referred to in the Contract Documents, or has been damaged prior to Owner's final payment (unless responsibility for the protection thereof has been assumed by Owner at Substantial Completion) provided that the defect was not caused by Owner.

3.
The word "furnish," when used in connection with services, materials, or equipment, shall mean to supply and deliver said services, materials or equipment to the Site (or some other specified location) ready for use or installation and in usable or operable condition.

4.
The word "install," when used in connection with services, materials, or equipment, shall mean to put into use or place in final position said services, materials or equipment or equipment complete and ready for intended use. 

5.
The words "perform" or "provide" when used in connection with services, materials, or equipment, shall mean to furnish and install said services, materials, or equipment complete and ready for intended use.

6.
When "furnish," "install," "perform," or "provide" is not used in connection with services, materials, or equipment in a context clearly requiring an obligation of Design/Builder, "provide" is implied. 

7.
Unless stated otherwise in the Contract Documents, words or phrases that have a well-known technical or construction industry or trade meaning are used in the Contract Documents in accordance with that meaning.

8.
When “Design/Builder”, “general Design/Builder”, “electrical Design/Builder”, or “mechanical Design/Builder” is used they mean the Design/Builder or its Subcontractors.

9.
When “engineer” or “architect” is used they mean the licensed engineer or architect employed by the Design Builder that stamp the plans and specifications.

ARTICLE 2 – PRELIMINARY MATTERStc "ARTICLE 2 – PRELIMINARY MATTERS"
2.01
Delivery of Bonds tc "2.01  Delivery of Bonds " \l 2
A.
When Design/Builder delivers the executed counterparts of the Agreement to Owner, Design/Builder shall also deliver to Owner such Bonds as Design/Builder may be required to furnish in accordance with Article 5.
B. Evidence of Insurance:  Before any Work is started, Design/Builder and Owner shall each deliver to the other, with copies to each additional insured identified in the Supplementary Conditions, certificates of insurance (and other evidence of insurance which either of them of any additional insured may reasonably request) that Design/Builder and Owner respectively are required to purchase and maintain in accordance with Article 5.

2.02
Copies of Documents tc "2.01  Delivery of Bonds " \l 2
A.
Owner shall furnish to Design/Builder up to ten printed or hard copies of the Conceptual Drawings and Project Manual.  Additional copies will be furnished upon request at the cost of reproduction.

2.03
Commencement of Contract Times; Notice to Proceed tc "2.02  Commencement of Contract Times; Notice to Proceed " \l 2
A.
The Contract Times will commence to run on the thirtieth day after the Effective Date of the Agreement, or, if a Notice to Proceed is given, on the day indicated in the Notice to Proceed.  A Notice to Proceed may be given at any time within thirty days after the Effective Date of the Agreement. 
2.04
Before Starting the Work tc "2.04  Before Starting the Work " \l 2
A.
Design/Builder's Review of Conceptual Documents: Before undertaking the Work, Design/Builder shall carefully study and compare those Conceptual Documents prepared by Owner and check and verify pertinent figures therein and all applicable field measurements.  Design/Builder shall promptly report in writing to Owner any conflict, error, ambiguity, or discrepancy which Design/Builder may discover and shall obtain a written interpretation or clarification from Owner before proceeding with any Work affected thereby.  

B.
Preliminary Schedules:  Within 10 days after commencement of the Contract Times (unless otherwise specified in the Contract Documents), Design/Builder shall submit the following to Resident Project Representative for its timely review:

1.
A preliminary progress schedule indicating the times (numbers of days or dates) for starting and completing the various stages of the Work, including any Milestones specified in the Contract Documents;

2.
A preliminary schedule of Submittals which will list each required Submittal and the times for submitting, reviewing and processing each Submittal;

3.
A preliminary Schedule of Values for all of the Work which will include quantities and prices of items which when added together equal the Contract Price and subdivides the Work into component parts in sufficient detail to serve as the basis for progress payments during performance of the Work.  Such prices will include an appropriate amount of overhead and profit applicable to each item of Work; and

4.
A preliminary cash flow projection estimating that portion of the Contract Price to be due during each month of performance.

2.05
Starting the Work
A.

Design/Builder shall start design work after receipt of a Notice of Proceed for Design.  Design/Builder shall start construction after receipt of a Notice To Proceed for Construction.  No Work shall be done at the Site prior to receipt of a Notice to Proceed for Construction.
2.06
Initial Conference tc "2.05  Initial Conference " \l 2
A.
Within twenty days after the Contract Times start to run, Design/Builder shall attend a pre-design conference attended by Owner and Design/Builder and others as appropriate to establish a working understanding among the parties as to the Work and to discuss the design concepts, schedules referred to in Paragraph 2.04.B, procedures for handling Submittals, processing Applications for Payment, maintaining required records, items required pursuant to Paragraph 8.01.A.6 and other matters. 

B. At the initial conference Owner and Design/Builder each shall designate, in writing, a specific individual to act as its authorized representative with respect to the services and responsibilities under the Contract.  Such individuals shall have the authority to transmit instructions, receive information, render decisions relative to the Contract, and otherwise act on behalf of each respective party. 
2.07
Initial Acceptance of Schedules tc "2.06  Initial Acceptance of Schedules " \l 2
A.
At least ten days before submission of the first Application for Payment, a conference attended by Design/Builder, Owner, Resident Project Representative and others as appropriate will be held to review for acceptability the schedules submitted in accordance with Paragraph 2.04.B.  Design/Builder shall have an additional ten days to make corrections and adjustments and to complete and resubmit the schedules.  No progress payment shall be made to Design/Builder until the schedules are submitted to and approved by the Resident Project Representative.  

1.
The progress schedule will be acceptable to Owner if it provides an orderly progression of the Work to completion within any specified Milestones and the Contract Times and complies with scheduling requirements in the Contract Documents.  Such acceptance will not impose on Owner or Owner’s representativese responsibility for the progress schedule, for sequencing, scheduling or progress of the Work nor interfere with nor relieve Design/Builder from Design/Builder's full responsibility therefor.

2.
Design/Builder's schedule of Submittals will be acceptable to Owner if it provides a workable arrangement for reviewing and processing the required Submittals and complies with the requirements of the Contract Document.

3.
Design/Builder's Schedule of Values will be acceptable to Owner as to form and substance if it provides a reasonable allocation of the Contract Price to component parts of the work.

ARTICLE 3 – CONTRACT DOCUMENTS: INTENT, AMENDING, REUSEtc "ARTICLE 3 – CONTRACT DOCUMENTS\:  INTENT, AMENDING, REUSE"
3.01
Intent tc "3.01  Intent " \l 2
A.
The Contract Documents are complementary; what is called for by one is as binding as if called for by all.

B.
It is the intent of the Contract Documents for the Design/Builder to design and construct a functionally complete, code compliant Project.  Contract Documents, including but not limited to the Conceptual Drawings and Specifications, are provided to conceptually describe a functionally complete Project (or part thereof).  Design/Builder shall furnish and perform all labor, documentation, services, materials, and equipment that may reasonably be inferred from the Contract Documents or from prevailing custom or trade usage as being required to produce the intended result whether or not specifically called for, at no additional cost to Owner.  

3.02
Reference Standards tc "3.02  Reference Standards " \l 2
A.
Standards, Specifications, Codes, Laws or Regulations.

1.
Reference to standards, specifications, manuals or codes of any technical society, organization or association, or to Laws or Regulations, whether such reference be specific or by implication, shall mean the standard, specification, manual, code, or Laws or Regulations in effect on the Effective Date except as may be otherwise specifically stated in the Contract Documents.

2.
No provision of any such standard, specification, manual, or code, or instruction of a Supplier, shall be effective to change the duties and responsibilities of Owner, Design/Builder, or any of their Subcontractors, consultants, agents, or employees from those set forth in the Contract Documents, nor shall it be effective to assign to Owner or its officers, directors, members, partners, employees, agents, consultants, or Subcontractors any duty or authority to supervise or direct the furnishing or performance of the Work or any duty or authority to undertake responsibility inconsistent with the provisions of the Contract Documents.

3.03
Resolving Discrepancies tc "3.03  Resolving Discrepancies " \l 2
A.
In the event of a discrepancy between the Conceptual Documents on the one hand and the Proposal or Drawings or Specifications on the other hand, the Conceptual Documents will control.  

B.
Except as otherwise specifically stated in the Contract Documents, the provisions of the Contract Documents shall take precedence in resolving any conflict, error, ambiguity, or discrepancy between the provisions of the Contract Documents and:

1.
The provisions of any such standard, specification, manual, code, or instruction (whether or not specifically incorporated by reference in the Contract Documents); or

2.
The provisions of any such Laws or Regulations applicable to the performance of the Work (unless such an interpretation of the provisions of the Contract Documents would result in violation of such Law or Regulation).

C.
All work shall comply with City of Manteca standards (latest version) unless deviations are specifically approved by the Owner.

3.04
Amending and Supplementing Contract Documents tc "3.04  Amending and Supplementing Contract Documents " \l 2
A.
The Contract Documents may be amended to provide for additions, deletions, and revisions in the Work or to modify the terms and conditions thereof in one or more of the following ways:

1.
Owner's approval of required Submittals (pursuant to Paragraph 6.17.B);

2.
A Work Change Directive;

3.
A Change Order;

4.
A Field Order.

3.05
Reuse of Documents tc "3.05  Reuse of Documents " \l 2
A.
All documents including Drawings and Specifications prepared or furnished by Design/Builder pursuant to this Agreement are for Design/Builder's own use, and Design/Builder shall retain an ownership and property interest therein whether or not the Project is completed.  Owner may make and retain copies for information and reference in connection with the use and occupancy of the Project by Owner and others.  However, such documents are not intended or represented to be suitable for reuse by Owner or others on extensions of the Project or on any other project.  Any reuse or any continued use after any termination without written verification or adaptation by Design/Builder for the specific purpose intended will be at Owner's sole risk and without liability or legal exposure to Design/Builder and Owner shall indemnify and hold harmless Design/Builder and Subcontractors from all claims, damages, losses and expenses including attorneys' fees arising out of or resulting therefrom.  

3.06
Electronic Data tc "3.06  Electronic Data " \l 2
A.
Unless otherwise stated in the Supplementary Conditions, the data furnished by Owner to Design/Builder or Design/Builder to Owner that may be relied upon are limited to the printed copies (also known as hard copies).  Files in electronic media format of text, data, graphics, or other types are furnished only for the convenience of the receiving party.  Any conclusion or information obtained or derived from such electronic files will be at the user's sole risk.  If there is a discrepancy between the electronic files and the hard copies, the hard copies govern.

B.
Because data stored in electronic media format can deteriorate or be modified inadvertently or otherwise without authorization of the data's creator, the party receiving electronic files agrees that it will perform acceptance tests or procedures within 60 days, after which the receiving party shall be deemed to have accepted the data thus transferred.  Any errors detected within the 60-day acceptance period will be corrected by the transferring party.  

C.
When transferring documents in electronic media format, the transferring party makes no representations as to long term compatibility, usability, or readability of documents resulting from the use of software application packages, operating systems, or computer hardware differing from those used by the data’s creator.

ARTICLE 4 – AVAILABILITY OF LANDS; DIFFERING SITE CONDITIONS; REFERENCE POINTS; HAZARDOUS ENVIRONMENTAL CONDITIONStc "ARTICLE 4 – AVAILABILITY OF LANDS; DIFFERING SITE CONDITIONS; REFERENCE POINTS; HAZARDOUS ENVIRONMENTAL CONDITIONS"
4.01
Availability of Lands tc "4.01  Availability of Lands " \l 2
A.
Owner shall furnish the Site.  Owner shall notify Design/Builder of any encumbrances or restrictions not of general application but specifically related to use of the Site which Design/Builder will have to comply in performing the Work.  Unless otherwise provided in the Contract Documents, Owner will obtain in a timely manner and pay for easements for permanent structures or permanent changes in existing facilities.  If Design/Builder and Owner are unable to agree on entitlement to or the amount or extent of any adjustments in the Contract Price or the Contract Times as a result of any delay in Owner's furnishing the Site, Design/Builder may make a Claim therefor as provided in Article 10.

1.
Where easement lines are shown on the Conceptual Drawings they shall be considered as shown in their final location unless stipulated otherwise in the Supplementary Conditions.
B.
Upon reasonable written request, Owner shall furnish Design/Builder with a current statement of record legal title and legal description of the lands upon which the Construction is to be performed and Owner's interest therein.

C.
Design/Builder shall provide for all additional lands and access thereto that may be required for temporary construction facilities or storage of materials and equipment.

4.02
Subsurface and Physical Conditions

A.
Reports and Drawings:  The Supplementary Conditions identify:

1.
those reports of explorations and tests of subsurface conditions at or contiguous to the Site that OWNER has used in preparing the Contract Docu​ments; and 

2.
those draw​ings of physical conditions in or relat​ing to existing surface or subsurface struc​tures at or contiguous to the Site (except Underground Facilities) that OWNER has used in preparing the Contract Docu​ments.
B.
Limited Reliance by Design/Builder on Technical Data Autho​rized:  Design/Builder may rely upon the general accuracy of the “technical data” contained in such reports and drawings, but such reports and drawings are not Contract Docu​ments.  Such “techni​cal data” is identi​fied in the Supplementa​ry Conditions.  Except for such reli​ance on such “technical data,” Design/Builder may not rely upon or make any Claim against OWNER or any of its consultants with respect to:

1.
the completeness of such reports and drawings for Design/Builder’s purposes, includ​ing, but not limited to, any aspects of the means, methods, techniques, sequences, and procedures of construction to be employed by Design/Builder, and safety precau​tions and programs incident thereto; or

2.
other data, interpretations, opin​ions, and information contained in such reports or shown or indicated in such draw​ings; or

3.
any Design/Builder inter​preta​tion of or conclusion drawn from any "technical data" or any such other data, interpre​tations, opinions, or infor​mation.
4.03
Differing Site Conditions 

A.
Design/Builder shall promptly, and before the conditions are disturbed, give a written notice to Owner of (i) subsurface or latent physical conditions at the Site which differ materially from those indicated in the Contract Documents, or (ii) unknown physical conditions at the Site, of an unusual nature, which differ materially from those ordinarily encountered and generally recognized as inhering in work of the character called for by the Contract Documents.

B.
Owner will investigate the Site conditions promptly after receiving the notice.  If the conditions do materially so differ and cause an increase or decrease in the Design/Builder's cost of, or the time required for, performing any part of the Work, whether or not changed as a result of the conditions, an equitable adjustment shall be made under this clause and the Contract Price or Times modified in writing by Change Order in accordance with Article 10.

C.
No request by Design/Builder for an equitable adjustment under Paragraph 4.03 shall be allowed unless Design/Builder has given the written notice required; provided that the time prescribed in 10.03.A for giving written notice may be extended by Owner.

D.
The provisions of this Paragraph 4.03 are not intended to apply to a Hazardous Environmental Condition uncovered or revealed at the Site.

4.04
Reference Points tc "4.03  Reference Points " \l 2
A.
Design/Builder shall be responsible for laying out the Work based on reference points identified in the Conceptual Drawings and shall protect and preserve reference points and property monuments established by Owner, and shall make no changes or relocations without the prior written approval of Owner.  Design/Builder shall report to Owner whenever any reference point or property monument is lost or destroyed or requires relocation because of necessary changes in grades or locations, and shall be responsible for the accurate replacement or relocation of such reference points or property monuments by a California licensed land surveyor.

4.05
Hazardous Environmental Condition at Site tc "4.04  Hazardous Environmental Condition at Site " \l 2
A.
Design/Builder will not be responsible for any Hazardous Environmental Condition encountered at the Site which was not identified in the Contract Documents to be within the scope of the Work.  Design/Builder shall be responsible for materials creating a Hazardous Environmental Condition created by any materials brought to the Site by Design/Builder, Subcontractors, Suppliers or anyone else for whom Design/Builder is responsible. 

B.
If Design/Builder encounters a Hazardous Environmental Condition, Design/Builder shall immediately: (i) secure or otherwise isolate such condition; (ii) stop all Construction in connection with such condition and in any area affected thereby (except in an emergency as required by Paragraph 6.17); and (iii) notify Owner (and thereafter confirm such notice in writing).  Owner shall promptly determine the necessity of retaining a qualified expert to evaluate such condition or take corrective action, if any.

C.
Design/Builder shall not be required to resume Construction in connection with such Hazardous Environmental Condition or in any such affected area until after Owner has obtained any required permits related thereto and delivered to Design/Builder written notice (i) specifying that such condition and any affected area is or has been rendered safe for the resumption of Construction, or (ii) specifying any special conditions under which such Construction may be resumed safely.  If Owner and Design/Builder cannot agree as to entitlement to or the amount or extent of an adjustment, if any, in Contract Price or Contract Times as a result of such Construction stoppage or such special conditions under which Construction is agreed to be resumed by Design/Builder, either party may make a Claim therefor as provided in Article 10.

D.
If after receipt of such special written notice Design/Builder does not agree to resume Construction based on a reasonable belief it is unsafe, or does not agree to resume such Construction under such special conditions, then Owner may order such portion of the Work that is related to such Hazardous Environmental Condition to be deleted from the Work.  If Owner and Design/Builder cannot agree as to entitlement to or the amount or extent of an adjustment, if any, in Contract Price or Contract Times as a result of deleting such portion of the Work, then either party may make a Claim therefor as provided in Article 10.  Owner may have such deleted portion of the Work performed by Owner's own forces or others in accordance with Article 7.

E.
To the fullest extent permitted by Laws or Regulations, Owner shall indemnify and hold harmless Design/Builder, Subcontractors, Suppliers and the officers, directors, partners, employees, agents, other consultants and Subcontractors of each and any of them from and against all claims, costs, losses and damages (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) arising out of or resulting from such Hazardous Environmental Condition, provided that such Hazardous Environmental Condition: (i) was not shown or indicated in the Contract Documents to be included in the scope of the Work, and (ii) was not created by Design/Builder or by anyone for whom Design/Builder is responsible.  Nothing in this Paragraph 4.05.E shall obligate Owner to indemnify any individual or entity from and against the consequences of that individual's or entity's own negligence. 

F.
To the fullest extent permitted by Laws or Regulations, Design/Builder shall indemnify and hold harmless Owner, Owner's Consultant and the officers, directors, partners, employees, agents, other consultants and Subcontractors of each and any of them from and against all claims, costs, losses and damages (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) arising out of or resulting from such Hazardous Environmental Condition created by Design/Builder or anyone for whom Design/Builder is responsible.  Nothing in this Paragraph 4.04.F shall obligate Design/Builder to indemnify any individual or entity from and against the consequences of that individual's or entity's own negligence. 

4.06
Underground Facili​ties

A.
Shown or Indicated: The informa​tion and data shown or indicated in the Contract Docu​ments with respect to existing Underground Facili​ties at or contiguous to the Site is based on infor​mation and data furnished to OWNER by the owners of such Under​ground Facili​ties, or by others.  Unless it is otherwise expressly provided in the Sup​plementary Condi​tions:

1.
OWNER and Owner’s Engineer shall not be responsible for the accuracy or com​pleteness of any such information or data; and

2.
the cost of all of the fol​lowing will be included in the Contract Price, and Design/Builder shall have full responsibility for:
a.
reviewing and check​ing all such informa​tion and data,
b.
locating all Underground Facilities shown or indicated in the Contract Documents,

c.
coordination of the Work with the owners of such Un​derground Facili​ties, including OWNER, during construc​tion, and

d.
the safety and protection of all such Under​ground Facili​ties  and repair​ing any damage thereto result​ing from the Work.
3.
Pursuant to Government Code Section 4216‑4216.9, the Design/Builder shall notify the appropriate regional notification center of all excavations as required under Government Code sections 4216 to 4216.9. The Design/Builder shall contact Underground Service Alert for the location of subsurface installations. Design/Builder shall furnish to the Resident Project Representative written documentation of its contact(s) with Underground Service Alert within two (2) days after such contact(s).

4.
At least fourteen (14) days before performing any excavation work, the Design/Builder shall request the utility owners to mark or otherwise indicate the location of their service. Design/Builder shall furnish to the Owner written documentation of its contact(s) with utility owners requesting them to mark or otherwise indicate the location of their respective facilities within three (3) days after such contact(s).

5.
It shall be the Design/Builder’s responsibility to determine the exact location and depth of all utilities, including service connections, which have been marked by the respective owners and which Design/Builder believes may affect or be affected by Design/Builder's operations. Determination of location and depth shall occur a minimum of fourteen (14) day prior to underground work commencing in an area. If no pay item is provided in the Contract for this work, full compensation for such work shall be considered as included in the prices bid for other items of work.

B.
Not Shown or Indicated

1.
If an Under​ground Facility is uncovered or revealed at or contig​uous to the Site which was not shown or indicated, or not shown or indicated with reasonable accuracy in the Contract Documents, Design/Builder shall, prompt​ly after becom​ing aware thereof and before further disturbing conditions affected thereby or performing any Work in connection therewith (except in an emergency as required by para​graph 6.16.A), identify the owner of such Under​ground Facility and give written notice to that owner and to OWNER.  Owner will promptly review the Under​ground Facility and determine the extent, if any, to which a change is required in the Contract Documents to reflect and document the consequences of the existence or location of the Under​ground Facility.  During such time, Design/Builder shall be responsible for the safety and protection of such Underground Facility.

2.
If Owner concludes that a change in the Contract Documents is required, a Work Change Directive or a Change Order will be issued to reflect and docu​ment such conse​quences.  An equitable adjustment shall be made in the Contract Price or Contract Times, or both, to the extent that they are attributable to the existence or location of any Underground Facility that was not shown or indicated or not shown or indicated with reasonable accuracy in the Contract Documents and that Design/Builder did not know of and could not reasonably have been expected to be aware of or to have anticipated.  If OWNER and Design/Builder are unable to agree on entitlement to or on the amount or extent, if any, of any such adjustment in Contract Price or Contract Times, OWNER or Design/Builder may make a Claim therefor as provided in paragraph 10.05.  In accordance with Government Code Section 4215 the Design/Builder shall not be assessed liquidated damages for delay in completion of the project, when such delay is caused by the failure of the Owner or utility company to provide for the removal or relocation of facilities for which they are the responsible party.

3.
When the Conceptual Drawings or Project Manual indicate that a utility is to be relocated, altered or constructed by others, the OWNER will conduct all negotiations with the utility company and the work will be done at no cost to the Design/Builder.

4.
Temporary or permanent service, relocation or alteration of utilities desired by the Design/Builder for its own convenience shall be the Design/Builder's responsibility and it shall make arrangements and bear all costs.

5.
Except where the owner of a damaged utility has advised that it intends to repair the damage through its own forces or forces that it will retain or has retained, Design/Builder shall, within 24 hours of receipt from the owner of notice to commence correction of damage, notify the Owner in writing if Design/Builder intends to repair the damage. During nights and weekends when work is not in progress, owner may give such notice by telephone or by facsimile transmission to the Design/Builder's facsimile number and such notice will be immediately effective. The Design/Builder's failure to provide timely written notification that it intends to repair the damage shall be deemed its agreement that the owner may repair the damage at Design/Builder's expense without further notice and without prejudice to any other remedy available to owner. In such event, the Design/Builder may observe the Work if this can be done without in any way delaying the progress thereof, but may not contest any element of the expense of repair or the lack of further notice. This provision is in addition to any other remedy, including the remedy provided in 13.08, OWNER May Correct Defective Work.
ARTICLE 5 - BONDS AND INSURANCE

5.01
Counterparts Of The Agreement

A.
Four (4) copies of the contract documents will be prepared by the OWNER.  All copies will be submitted to Design/Builder and Design/Builder shall execute the Agreement, insert executed copies of the required bonds and power of attorney, all insurance, and submit all copies to OWNER within fifteen (15) days after receipt of the documents from OWNER.  All reference to Agreement dates should be left blank.

B.
If all of Design/Builder’s bonds, insurance, and other paperwork are complete and proper, OWNER will execute all copies, insert the date of the Agreement where left blank, and transmit all copies to Design/Builder within ten (10) days after receipt of the documents from Design/Builder for distribution.  Distrib​ution of signed copies will be one (1) copy each to OWNER, Design/Builder, Sureties, and Owner.  Design/Builder shall be respon​sible for distribution of copies to the Surety.

5.02
Performance, Payment, and Other Bonds
A. Design/Builder shall furnish performance and payment bonds, each in an amount at least equal to the Contract Price as security for the faithful perfor​mance and payment of all of Design/Builder’s obligations under the Contract Documents. These bonds shall remain in effect until one year after the date when final payment becomes due or until completion of the correction period specified in Paragraph 14.11, whichever is later, except as provided otherwise by Laws or Regulations or by the Contract Documents. Design/Builder shall also furnish such other bonds as are required by the Contract Documents. 

B. All bonds shall be in the form prescribed by the Contract Documents except as provided other​wise by Laws or Regulations, and shall be executed by such sureties as are named in the current list of “Companies Holding Certificates of Authority as Acceptable Sureties on Federal Bonds and as Acceptable Reinsuring Compa​nies” as pub​lished in Circular 570 (amended) by the Financial Management Service, Surety Bond Branch, U.S. Department of the Treasury. All bonds signed by an agent must be accompanied by a certified copy of the agent’s authority to act.

C. If the surety on any bond furnished by Design/Builder is declared bankrupt or becomes insolvent or its right to do business is terminated in any state where any part of the Project is located or it ceases to meet the requirements of Paragraph 5.02.B, Design/Builder shall promptly notify Owner and Engineer and shall, within 20 days after the event giving rise to such notification, provide another bond and surety, both of which shall comply with the requirements of Paragraphs 5.02.B and 5.03.

5.03
Licensed Sureties and Insurers
A. All bonds and insurance required by the Contract Documents to be purchased and main​tained by Owner or Design/Builder shall be obtained from surety or insurance companies that are duly licensed or authorized in the jurisdiction in which the Project is located to issue bonds or insur​ance policies for the limits and coverages so required. Such surety and insurance companies shall also meet such addi​tional requirements and qualifications as may be provided in the Supple​mentary Conditions.

5.04
Certificates of Insurance
A. Design/Builder shall deliver to Owner, with copies to each additional insured identi​fied in the Supple​mentary Conditions, certificates of insur​ance (and other evidence of insurance request​ed by Owner or any other additional insured) which Design/Builder is required to purchase and main​tain. 

B. Owner shall deliver to Design/Builder, with copies to each additional insured identified in the Supple​mentary Condi​tions, certificates of insurance (and other evi​dence of insur​ance requested by Design/Builder or any other additional insured) which Owner is required to purchase and maintain. 

5.05
Design/Builder’s Liability Insurance
A. Design/Builder shall purchase and main​tain such liability and other insurance as is appro​priate for the Work being performed and as will provide protection from claims set forth below which may arise out of or result from Design/Builder’s performance of the Work and Design/Builder’s other obligations under the Contract Documents, whether it is to be per​formed by Design/Builder, any Subcontractor or Supplier, or by anyone directly or indirectly employed by any of them to perform any of the Work, or by anyone for whose acts any of them may be liable:

1. claims under workers’ compensa​tion, disability benefits, and other similar employ​ee benefit acts;

2. claims for damages because of bodily injury, occupational sickness or disease, or death of Design/Builder’s employees;

3. claims for damages because of bodily injury, sickness or disease, or death of any person other than Design/Builder’s employees;

4. claims for damages insured by reasonably available personal injury liability coverage which are sus​tained:

a. by any person as a result of an offense directly or indirectly related to the em​ploy​ment of such person by Design/Builder, or 

b. by any other person for any other reason;

5. claims for damages, other than to the Work itself, because of injury to or destruc​tion of tangible property wherever located, including loss of use resulting therefrom; and

6. claims for damages because of bodily injury or death of any person or property damage arising out of the ownership, mainte​nance or use of any motor vehicle.

B. The policies of insurance required by this Paragraph 5.05 shall:

1. with respect to insurance re​quired by Paragraphs 5.05.A.3 through 5.05.A.6 inclu​sive, include as additional insured (subject to any customary exclu​sion regarding profession​al liability) Owner, Owner’s Engineer and Resident Project Representative, and any other individuals or entities identified in the Supple​men​tary Condi​tions, all of whom shall be listed as addi​tional insureds, and include coverage for the respec​tive officers, directors, partners, employ​ees, agents, consultants and Subcontractors of each and any of all such addi​tional insureds, and the insurance afforded to these addi​tional insureds shall provide primary coverage for all claims covered thereby;

2. include at least the specific coverages and be written for not less than the limits of liability provid​ed in the Contract Documents or required by Laws or Regulations, whichever is greater;

3. include completed operations insurance;

4. include contractual liability insurance covering Design/Builder’s indemnity obligations under Paragraph 6.22;

5. contain a provision or endorse​ment that the coverage afforded will not be canceled, materi​ally changed or renewal refused until at least 30 days prior written notice has been given to Owner and Design/Builder and to each other addi​tional insured identified in the Supplementary Conditions (and the certificates of insurance furnished by the Design/Builder pursuant to Paragraph 5.04 will so provide);

6. remain in effect at least until final payment and at all times thereafter when Design/Builder may be correcting, removing, or replac​ing defective Work in accordance with Paragraph 13.05; and

7. with respect to completed opera​tions insur​ance, and any insurance coverage written on a claims-made basis, remain in effect for at least two years after final payment.

a. Design/Builder shall furnish Owner and each other additional insured identified in the Supple​mentary Conditions evidence satisfactory to Owner and any such additional insured of continua​tion of such insurance at final payment and two years thereafter.

8. With respect to all insurance required by this paragraph 5.05, Design/Builder agrees to waive all rights of subrogation against Owner, Engineer and Resident Project Representative, and each additional insured identified in the Supplemental Conditions.

C.
The Design/Builder shall maintain limits no less than the following:

1.
General Liability - Two million dollars ($2,000,000) per occurrence for bodily injury, personal injury and property damage.  Three million dollars ($3,000,000) general aggregate.  Three million dollars ($3,000,000) products/completed operations aggregate. Two million dollars ($2,000,000) personal and advertising injury limit.   If Commercial General Liability Insurance or other form with a general aggregate limit or products-completed operations aggregate limit is used, either the general aggregate limit shall apply separately to the project/location (with the ISO CG 2503, or ISO CG 2504, or insurer's equivalent endorsement provided to the OWNER) or the general aggregate limit and products-completed operations aggregate limit shall be twice the required occurrence limit.

2.
Automobile Liability - One million dollars ($1,000,000) for bodily injury and property damage each accident limit.

3.
Professional Liability – One million dollars ($1,000,000) per claim and in the aggregate.proit
Such liability insurance shall indemnify the Design/Builder and his/her subcontractors and design consultants against loss from liability imposed by law upon, or assumed under contract by, the Design/Builder or his/her subcontractors for damages on account of such bodily injury (including death), property damage, personal injury, completed operations, and products liability.

The general liability policy shall cover bodily injury and property damage liability, owned and non-owned equipment, blanket contractual liability, completed operations liability, explosion, collapse, underground excavation, and removal of lateral support.

The automobile liability policy shall cover all owned, non-owned, and hired automobiles.

The Design Builder and all design consultants shall carry this insurance for claims arising from the negligent performance of professional services under this Agreement.
All of the insurance shall be provided on policy forms and through companies satisfactory to the City of Manteca.

Any deductible or self-insured retention must be declared to and approved by the City of Manteca.  At the option of the City of Manteca, the insurer shall either reduce or eliminate such deductibles or self-insured retention’s.

D.
Worker's Compensation and Employer's Liability  -  The Design/Builder and all subcontractors shall insure (or be a qualified self-insured) under the applicable laws relating to workers' compensation insurance, all of their employees working on or about the construction site, in accordance with the "Workers' Compensation and Insurance Act”, Division IV of the Labor Code of the State of California and any Acts amendatory thereof.  The Design/Builder shall provide employer's liability insurance with limits of:

1.
Statutory Limits, or

2.
Each Accident


$1,000,000

3.
Disease - Policy Limit

$1,000,000

4. 
Disease - Each Employee
$1,000,000

E.
It is mandatory that the Design/Builder provides OWNER with a Certificate of Insurance prior to execution of the Agreement.  The Design/Builder shall file with the City of Manteca a certificate of insurance (Accord Form 25-S or equivalent) signed by the insurer’s representative evidencing the coverage required by this Agreement.  Such evidence shall include an additional insured endorsement signed by the insurer's representative and evidence of waiver of rights of subrogation against the City of Manteca (if builder’s risk insurance is applicable).  Such evidence shall also include confirmation that coverage includes or has been modified to include the required limits.  

The Design/Builder shall, upon demand of the City of Manteca, deliver to the City of Manteca such policy or policies of insurance and the receipts for payment of premiums thereon.

F.
DESIGN/BUILDER’s liability insurance shall be the primary liability insurance for all work being done by the Design/Builder for OWNER under this contract.  Evidence of such agreement shall be in the form of a policy endorsement submitted to the OWNER.  All such endorsements are subject to review and approval by the OWNER prior to the start of work.

G.
All insurance must be with Admitted California carriers as listed by the State of California Insurance and have a current A.M. Best rating of no less than A-:VII or equivalent or as otherwise approved by the OWNER.  The Design/Builder shall not change carriers during the course of the work or within one year after completion of any project to a non-admitted carrier or sign any prior work exclusion provision.

5.06
Owner’s Liability Insurance
A. In addition to the insurance required to be provid​ed by Design/Builder under Paragraph 5.05, Owner, at Owner’s option, may purchase and maintain at Owner’s expense Owner’s own liability insurance as will protect Owner against claims which may arise from operations under the Contract Docu​ments.

5.07
Property Insurance
A. Unless otherwise provided in the Supple​menta​ry Conditions, Design/Builder shall purchase and maintain property insurance upon the Work at the Site in the amount of the full replacement cost thereof (subject to such deductible amounts as may be provid​ed in the Supplementary Conditions or required by Laws and Regulations). This insurance shall:

1. include the interests of Owner, Design/Builder, Subcontractors, Owner’s Engineer and Resident Project Representative, and any other individuals or entities identi​fied in the Supplementary Condi​tions, and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them, each of whom is deemed to have an insur​able interest and shall be listed as an insured or additional insured;

2. be written on a Builder’s Risk “all‑risk” or open peril or special causes of loss policy form that shall at least include insurance for physical loss or damage to the Work, tempo​rary buildings, false work, and materials and equipment in transit, and shall insure against at least the following perils or causes of loss: fire, lightning, extended coverage, theft, vandal​ism and malicious mischief, earthquake, collapse, explosion, debris remov​al, demolition occasioned by en​forcement of Laws and Regulations, water dam​age, (other than caused by flood) and such other perils or causes of loss as may be specifi​cal​ly required by the Supplementa​ry Conditions;

3. include expenses incurred in the repair or replacement of any insured property (including but not limited to fees and charges of engineers and archi​tects);

4. cover materials and equipment stored at the Site or at another location that was agreed to in writing by Owner prior to being incorporated in the Work, provided that such materials and equip​ment have been included in an Application for Payment recommended by Engineer;

5. allow for partial utilization of the Work by Owner;

6. include testing and startup; and

7. be maintained in effect until final pay​ment is made unless otherwise agreed to in writing by Owner, Design/Builder, Owner’s Engineer and Resident Project Representative with 30 days written notice to each other addi​tional insured.

B. Design/Builder shall purchase and maintain such boiler and machinery insurance or additional property insur​ance as may be required by the Supplementary Condi​tions or Laws and Regulations which will include the interests of Owner, Design/Builder, Subcontractors, Owner’s Engineer and Resident Project Representative, and any other individuals or entities identified in the Supplementary Conditions, and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them, each of whom is deemed to have an insur​able interest and shall be listed as an insured or addi​tional insured.

C. All the policies of insurance (and the certifi​cates or other evidence thereof) required to be pur​chased and maintained in accordance with Paragraph 5.07 will contain a provision or endorsement that the coverage afforded will not be canceled or materially changed or renewal refused until at least 30 days prior written notice has been given to Owner and Design/Builder and to each other additional insured and will contain waiver provisions in accor​dance with Paragraph 5.08.

D. Owner shall not be responsible for purchas​ing and maintaining any property insurance specified in this Paragraph 5.07 to protect the interests of Design/Builder, Subcontractors, or others in the Work to the extent of any deductible amounts that are identified in the Supple​mentary Conditions. The risk of loss within such identified deductible amount will be borne by Design/Builder, Subcontractors, or others suffering any such loss, and if any of them wishes property insurance cover​age within the limits of such amounts, each may purchase and maintain it at the purchaser’s own expense.

E. If Design/Builder requests in writing that other special insurance be included in the property insurance policies provided under Paragraph 5.07, Owner shall, if possible, include such insurance, and the cost thereof will be charged to Design/Builder by appropri​ate Change Order. Prior to com​mencement of the Work at the Site, Owner shall in writing advise Design/Builder whether or not such other insurance has been procured by Owner.

F.
Installation Floater Insurance.

1.
DESIGN/BUILDER shall purchase and maintain installation floater insurance.

2.
Equipment such as pumps, compressors, motors, switchgear, transformer, valves, panel boards, instrumentation and control equipment, and other similar equipment shall be insured under the installation floater insurance when the aggregate value of the equipment exceeds $10,000.  This insurance shall protect Design/Builder, OWNER, its directors, officers, employees, and authorized volunteers, and Owner’s Engineer, and Resident Project Representative from all insurable risks of physical loss or damage to materials and equipment not otherwise covered under builder's risk insurance, while in warehouses or storage areas, during installation, during testing, and after the Work is completed.  It shall be of the "all risk" type, with coverages designed for the circum​stances, which may occur in the particular Work included in the contract documents.  The coverage shall be for an amount not less than the insurable value of the Work at completion, less the value of materials and equipment insured under builder's risk insurance.  The value shall include the aggregate value of the OWNER‑furnished equipment and materi​als to be erected or installed by Design/Builder not otherwise insured under builder's risk insurance.  Installation floater insurance shall provide for losses to be payable to Design/Builder, OWNER, and Owner’s Engineer, and Resident Project Representative as their interests may appear.  The policy shall contain a provision that in the event of payment for any loss under the coverage provided, the insur​ance company shall have no rights of recovery against the Design/Builder, OWNER, Owner’s Engineer, and Resident Project Representative.

3.
Certific​ates of insurance covering installation floater insurance shall quote the insuring agreement and all exclu​sions as they appear in the policy; or in lieu of certifi​cates, copies of the complete policy may be submitted.

G.
Builders risk and installation floater insurance policies shall contain a provision that the coverage afforded will not be canceled or materially changed until at least thirty (30) days prior written notice has been given to OWNER.

H.
Insured losses under policies of insurance which include OWNER's interests shall be adjusted with OWNER and made payable to OWNER as trustee for the insured, as their interests may appear, subject to the requirements of any applicable mortgage clause, and any direction by arbitrators.  OWNER as trustee shall have the right to adjust and settle losses with the insurers unless one of the parties in interest shall object in writing within five (5) days after the occurrence of loss to OWNER's exercise of this power and, if such objection be made, arbitrators shall be chosen as provided in the General Conditions.   OWNER as trustee shall, in that case, make settlement with the insurers in accordance with the direction of such arbitrators.  If distribution of the insurance proceeds by arbitration is required, the arbitrators will direct such distribution.  OWNER and Design/Builder waive all rights against each other and against Owner’s Engineer, and Resident Project Representative for damages caused by fire or other perils to the extent covered by insurance except such rights as they may have to the proceeds of such insurance held by OWNER as trustee. Design/Builder shall require similar waivers by subcontractors.  Each waiver shall be in favor of all other parties enumerated in this para​graph.

I. The making of progress payments to the Design/Builder shall not be construed as creating an insurable interest by or for the City of Manteca or be construed as relieving the Design/Builder or his/her subcontractors of responsibility for loss from any direct physical loss, damage or destruction occurring prior to final acceptance of the work by the OWNER.


The Design/Builder shall waive all rights of subrogation against the City of Manteca, its directors, officers, employees, or authorized volunteers. 

5.08
Waiver of Rights
A. Owner and Design/Builder intend that all policies purchased in accor​dance with Paragraph 5.07 will protect Owner, Design/Builder, Subcontractors, Owner’s Engineer and Resident Project Representative, and all other individuals or entities identi​fied in the Supple​mentary Condi​tions to be listed as insureds or additional insureds (and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them) in such policies and will provide primary cover​age for all losses and damages caused by the perils or causes of loss covered thereby. All such policies shall contain provisions to the effect that in the event of payment of any loss or damage the insurers will have no rights of recov​ery against any of the insureds or additional insureds thereunder. Owner and Design/Builder waive all rights against each other and their respective officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them for all losses and damages caused by, arising out of or resulting from any of the perils or causes of loss covered by such policies and any other property insurance applica​ble to the Work; and, in addi​tion, waive all such rights against Subcontractors, Owner’s Engineer and Resident Project Representative, and all other individuals or entities identified in the Supple​men​tary Condi​tions to be listed as insured or additional insured (and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them) under such policies for losses and damages so caused. None of the above waivers shall extend to the rights that any party making such waiver may have to the pro​ceeds of insurance held by Owner as trustee or other​wise payable under any policy so issued.

B. Owner waives all rights against Design/Builder, Subcontractors, Owner’s Engineer and Resident Project Representative, and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them for:

1. loss due to business inter​ruption, loss of use, or other consequential loss extending be​yond direct physical loss or damage to Owner’s property or the Work caused by, arising out of, or resulting from fire or other perils whether or not insured by Owner; and

2. loss or damage to the com​pleted Pro​ject or part thereof caused by, arising out of, or resulting from fire or other insured peril or cause of loss covered by any property insurance main​tained on the completed Project or part thereof by Owner during partial utilization pursuant to Paragraph 14.07, after Substan​tial Com​pletion pursuant to Paragraph 14.06, or after final payment pursuant to Paragraph 14.09.

C. Any insurance policy maintained by Owner cover​ing any loss, damage or consequential loss referred to in Paragraph 5.08.B shall contain provisions to the effect that in the event of payment of any such loss, damage, or consequential loss, the insurers will have no rights of recovery against Design/Builder, Subcontractors, Owner’s Engineer or Resident Project Representative, and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them.

5.09
Receipt and Application of Insurance Proceeds
A. Any insured loss under the policies of insurance required by Paragraph 5.07 will be adjusted with Owner and made payable to Owner as fiduciary for the insureds, as their interests may appear, subject to the requirements of any applicable mortgage clause and of Paragraph 5.09.B. Owner shall deposit in a separate account any money so received and shall distribute it in accordance with such agree​ment as the parties in interest may reach. If no other special agreement is reached, the damaged Work shall be repaired or re​placed, the moneys so received applied on account thereof, and the Work and the cost thereof covered by an appropriate Change Order.

B. Owner as fiduciary shall have power to adjust and settle any loss with the insurers unless one of the parties in interest shall object in writing within 15 days after the occurrence of loss to Owner’s exercise of this power. If such objection be made, Owner as fiduciary shall make settlement with the insurers in accordance with such agreement as the parties in interest may reach. If no such agreement among the parties in interest is reached, Owner as fiduciary shall adjust and settle the loss with the insurers and, if required in writing by any party in interest, Owner as fiduciary shall give bond for the proper performance of such duties.

5.10
Acceptance of Bonds and Insurance; Option to Replace
A. If either Owner or Design/Builder has any objection to the coverage afforded by or other provi​sions of the bonds or insurance required to be purchased and maintained by the other party in accor​dance with Article 5 on the basis of non‑conformance with the Contract Documents, the objecting party shall so notify the other party in writing within 10 days after receipt of the certificates (or other evidence requested) required by Paragraph 2.01.B. Owner and Design/Builder shall each provide to the other such additional information in respect of insurance provided as the other may reasonably request. If either party does not purchase or maintain all of the bonds and insurance required of such party by the Con​tract Documents, such party shall notify the other party in writing of such failure to purchase prior to the start of the Work, or of such failure to maintain prior to any change in the required coverage. Without prejudice to any other right or remedy, the other party may elect to obtain equiva​lent bonds or insurance to protect such other party's interests at the expense of the party who was required to provide such coverage, and a Change Order shall be issued to adjust the Contract Price accordingly.

5.11
Partial Utilization, Acknowledgment of Property Insurer
A. If Owner finds it necessary to occupy or use a portion or portions of the Work prior to Sub​stan​tial Completion of all the Work as provided in Paragraph 14.07, no such use or occu​pancy shall commence before the insurers providing the property insurance pursuant to Paragraph 5.07 have acknowledged notice thereof and in writing effected any changes in cover​age necessitated thereby. The insurers providing the proper​ty insurance shall consent by endorse​ment on the policy or policies, but the property insurance shall not be canceled or permitted to lapse on account of any such partial use or occupan​cy.

1. All insurance required by the Contract Documents, or by  laws or regulations shall remain in full force and effect on all phases of the Work, whether or not the Work is occupied or  utilized by Owner, until all Work included in the agreement has been completed and final payment has been made.

2. Nothing contained in the insurance requirements shall be construed as limiting the extent of Design/Builder's responsibility for payment of damages resulting from Design/Builder’s, subcontractors’ or suppliers’ operations under the Contract.  Design/Builder agrees that Design/Builder alone shall be completely responsible for procuring and maintaining full insurance coverage as provided herein or as may be otherwise required by the Contract Documents.  Any approval by Owner or Resident Project Representative shall not operate to the contrary.
ARTICLE 6 – DESIGN/BUILDER'S RESPONSIBILITIEStc "ARTICLE 6 – DESIGN/BUILDER'S RESPONSIBILITIES"
6.01
Design Professional Services tc "6.01  Design Professional Services " \l 2
A.
Standard of Care:  The standard of care for all Design Professional Services performed or furnished by Design/Builder under this Agreement will be the care and skill ordinarily used by members of the subject profession practicing under similar conditions at the same time and in the same locality. 

B.
Preliminary Design Phase:  After the Contract Times commence to run, Design/Builder shall:

1.
Consult with Owner to understand Owner's requirements for the Project and review available data;

2.
Identify and analyze requirements of governmental authorities having jurisdiction to approve the portions of the Project designed or specified by Design/Builder with whom consultation is to be undertaken in connection with the Project;

3.
Obtain such additional geotechnical and related information which it deems necessary for performance of the Work;

4.
On the basis of the Conceptual Documents and Design/Builder's Proposal, prepare ninety percent (90%) complete design documents consisting of final design criteria, drawings, specifications, and written descriptions of the Project;

5.
Furnish the ninety percent (90%) complete design documents to and review them with Owner within the times indicated in the schedules described in Paragraphs 2.07.A.1 and 2.07.A.2; and

6.
Identify any variations in the preliminary design documents from the Contract Documents in accordance with 6.18.B.


C.
Final Design Phase:  
After written acceptance by Owner of the preliminary design phase documents Design/Builder shall:

1.
On the basis of the accepted Preliminary Design Phase documents, prepare final  Drawings showing the scope, extent, and character of the Construction to be performed and furnished by Design/Builder and Specifications (which will be prepared, where appropriate, in general conformance with the format recommended by the Construction Specifications Institute);

2.
Provide technical criteria, written descriptions, and design data required for obtaining approvals of such governmental and other authorities as have jurisdiction to review or approve the final design of the Project and obtain  approval of such governmental and other authorities;

3.
Furnish the above documents, Drawings, and Specifications to and review them with Owner within the times indicated in the schedules described in Paragraphs 2.07.A.1 and 2.07.A.2; and

4.
Identify any deviations from other Contract Documents in accordance with Paragraph 6.18.B.

6.02
Supervision and Superintendence of Construction tc "6.02  Supervision and Superintendence of Construction " \l 2
A.
Design/Builder shall supervise, inspect, and direct the Construction competently and efficiently, devoting such attention thereto and applying such skills and expertise as may be necessary to provide the Construction in accordance with the Contract Documents.  Design/Builder shall be solely responsible for the means, methods, techniques, sequences, and procedures of Construction.  Design/Builder shall be responsible to see that the completed Construction complies fully with the Contract Documents and shall keep Owner advised as to the quality and progress of the Construction.

B.
At all times during the progress of Construction, the Design/Builder shall assign a competent resident superintendent who shall not be replaced without written notice to Owner except under extraordinary circumstances.  

C. Means or methods of work suggested by the OWNER or the OWNER’s Representative, but not specified or required, if adopted or followed by the Design/Builder in whole or in part, shall be used at the risk and responsibility of the Design/Builder. The OWNER and the OWNER’s Representative assume no responsibility therefore, and in no way will be held liable for any defects in the Work which may result from or be caused by use of such plan or method of Work.

6.03
Labor, Working Hours tc "6.03  Labor, Working Hours " \l 2
A.
Design/Builder shall provide competent, suitably qualified personnel to perform the Work as required by the Contract Documents. Design/Builder shall at all times maintain good discipline and order at the Site.

B. The Design/Builder shall normally conduct work on weekdays during normal business hours.  In the absence of any Federal, state or local laws, regulations or  covenants, the Design/Builder may conduct its performance of the Work at the Design/Builder’s sole discretion, except that the cost of any overtime pay or other expense incurred by the Owner for Resident Project Representative and construction observation services, occasioned by the conduct of Work on Saturday, Sunday, any legal holiday, or as overtime on any regular work day, shall be reimbursed to the OWNER by the Design/Builder. Design/Builder shall provide to Owner 72-hour written notice of intent to work outside of regular working hours.
6.04  Services, Materials, and Equipment tc "6.04  Services, Materials, and Equipment " \l 2
A.
Unless otherwise specified in the Contract Documents, Design/Builder shall furnish or cause to be furnished and assume full responsibility for all services, materials, equipment, labor, transportation, construction equipment and machinery, tools, appliances, fuel, power, light, heat, telephone, water, sanitary facilities, temporary facilities, and all other facilities and incidentals necessary for the performance, testing, start-up, and completion of the Work.

B.
All materials and equipment incorporated into the Work shall be as specified by Owner, or in the Drawings or Specifications, or if not specified shall be of good quality and new, except as otherwise provided in the Contract Documents.  All warranties and guarantees specifically called for by the Contract Documents shall expressly run to the benefit of Owner.  If required by Owner, Design/Builder shall furnish satisfactory evidence (including reports of required tests) as to the source, kind, and quality of materials and equipment.  
C. All materials and equipment shall be stored, applied, installed, connected, erected, protected, used, cleaned, and conditioned in accordance with instructions of the applicable Supplier, except as otherwise provided in the Contract Documents.

1. Materials and equipment, if furnished by the Owner, will be made available as designated in the General Requirements. The cost of unloading, hauling and handling, and placing Owner‑furnished materials and equipment shall be considered as included in the price bid for the Contract item involving such Owner‑furnished material.

2. Design/Builder shall inspect and assure itself of the amount and soundness of such materials and equipment.

3. The Design/Builder will be held responsible for all materials and equipment furnished to it and received by it, and shall pay all demurrage and storage charges. City‑furnished materials and equipment lost or damaged from any cause whatsoever shall be replaced by the Design/Builder. The Design/Builder will be liable to the Owner for the cost of replacing Owner‑furnished material and equipment and such costs may be deducted from any moneys due or to become due the Design/Builder.

D. Where the Work requires equipment be furnished, due to the lack of standardization of equipment as produced by the various manufacturers, it may become necessary to make modifications in the structures, buildings, piping, mechanical work, electrical work, accessories, controls, or other work, to accommodate the particular equipment offered. Design/Builder’s bid price for any equipment offered shall include the cost of making any necessary changes subject to the approval of Owner.

6.05
Progress Schedule tc "6.05  Progress Schedule " \l 2
A.
Design/Builder shall adhere to the progress schedule established in accordance with Paragraph 2.07.A as it may be adjusted from time to time as provided below: 

1.
Design/Builder shall submit to Owner for acceptance proposed adjustments in the progress schedule that will not change the Contract Times (or Milestones).  Such adjustments will conform generally to the progress schedule then in effect.

2.
Proposed adjustments in the progress schedule that will change the Contract Times (or Milestones) shall be submitted in accordance with the requirements of Article 11.02.  Such adjustments may only be made by a Change Order.

3.
Design/Builder shall provide weekly updates of on-going daily construction activities to the OWNER’s representative and provide printed updated monthly project schedules (in Microsoft Project or equal format) and shall attend weekly progress meetings at the request of the OWNER’s representative.

6.06
Substitutes and “Or‑Equals”
A. Whenever an item of material or equip​ment is specified or described in the Con​tract Docu​ments by using the name of a propri​etary item or the name of a particular Supplier, the specifica​tion or description is intended to establish the type, func​tion, appearance, and quality required. Unless the specifica​tion or description con​tains or is followed by words reading that no like, equivalent, or “or‑equal” item or no substitution is permitted, other items of material or equipment or material or equipment of other Suppli​ers may be submitted to Owner’s Engineer for review under the circum​stances described below.

1. “Or‑Equal” Items: If in Owner’s Engineer’s sole discretion an item of material or equip​ment pro​posed by Design/Builder is function​ally equal to that named and sufficiently similar so that no change in related Work will be required, it may be con​sidered by Owner’s Engineer as an “or‑equal” item, in which case review and approval of the proposed item may, in Owner’s Engineer’s sole discre​tion, be accom​plished without compliance with some or all of the require​ments for approval of proposed substi​tute items. For the purposes of this Paragraph 6.05.A.1, a proposed item of material or equipment will be considered functionally equal to an item so named if: 

a. in the exercise of reasonable judgment Owner’s Engineer determines that: 

1) it is at least equal in materials of construction, quality, durability, appearance, strength, and design characteristics; 

2) it will reliably perform at least equally well the function and achieve the results imposed by the design concept of the completed Project as a functioning whole, 

3) it has a proven record of performance and availability of responsive service; and

b. Design/Builder certifies that, if approved and incorporated into the Work: 

1) there will be no increase in cost to the Owner or increase in Contract Times, and 

2) it will conform substantially to the detailed requirements of the item named in the Contract Documents.

2. Substitute Items 

a. If in Owner’s Engineer’s sole discretion an item of materi​al or equipment pro​posed by Design/Builder does not qualify as an “or‑equal” item under Paragraph 6.06.A.1, it will be considered a proposed substitute item. 

b. Design/Builder shall submit suffi​cient infor​ma​tion as provided below to allow Owner’s Engineer to determine that the item of material or equipment proposed is essentially equiva​lent to that named and an accept​able substitute therefor. Re​quests for review of proposed substitute items of materi​al or equipment will not be accepted by Owner’s Engineer from anyone other than Design/Builder. 

c. The requirements for review by Owner’s Engineer will be as set forth in Paragraph 6.06.A.2.d, as supplemented in the General Requirements and as Owner’s Engineer may decide is appropriate under the circumstances. 

d. Design/Builder shall make written applica​tion to Owner’s Engineer for review of a proposed substitute item of material or equipment that Design/Builder seeks to furnish or use. The application: 

1) shall certify that the proposed substi​tute item will: 

a) perform ade​quately the functions and achieve the results called for by the general design, 

b) be similar in substance to that specified, and

c) be suited to the same use as that specified; 


2) will state:

a) the extent, if any, to which the use of the pro​posed substitute item will preju​dice Design/Builder’s achievement of Substan​tial Comple​tion on time;

b) whether or not use of the proposed substitute item in the Work will re​quire a change in any of the Contract Docu​ments (or in the provisions of any other direct contract with Owner for other work on the Project) to adapt the de​sign to the proposed substi​tute item; and

c) whether or not incorporation or use of the proposed substi​tute item in con​nection with the Work is sub​ject to payment of any license fee or royalty;

3) will identify: 

a) all variations of the pro​posed substitute item from that specified , and 

b) available engineering, sales, maintenance, repair, and replacement services; 

4) and shall contain an itemized esti​mate of all costs or credits that will result directly or indi​rectly from use of such substitute item, including costs of rede​sign and claims of other con​tractors affected by any resulting change,

B. Substitute Construction Methods or Proce​dures: If a specific means, method, technique, se​quence, or procedure of construction is expressly required by the Contract Documents, Design/Builder may furnish or utilize a substitute means, meth​od, technique, sequence, or procedure of con​struction approved by Owner’s Engineer. Design/Builder shall submit sufficient information to allow Owner’s Engineer, in Owner’s Engineer’s sole discre​tion, to determine that the substitute proposed is equivalent to that expressly called for by the Contract Docu​ments. The requirements for review by Owner’s Engineer will be similar to those provided in Paragraph 6.06.A.2.

C. Owner’s Engineer’s Evaluation: Owner’s Engineer will be allowed a reasonable time within which to evaluate each propos​al or submittal made pursuant to Paragraphs 6.05.A and 6.06.B. Owner’s Engineer may require Design/Builder to furnish additional data about the pro​posed substitute item. Owner’s Engineer will be the sole judge of accept​abili​ty. No “or equal” or substitute will be or​dered, installed or utilized until Owner’s Engineer’s review is complete, which will be evidenced by either a Change Order for a substitute or an approved Shop Drawing for an “or equal.” Owner’s Engineer will advise Design/Builder in writing of any negative determination.

D. Special Guarantee: Owner may require Design/Builder to furnish at Design/Builder’s ex​pense a special performance guarantee or other surety with respect to any substitute. 

E. Engineer’s Cost Reimbursement: Owner’s Engineer will record Owner’s Engineer’s costs in evalu​ating a substitute proposed or submitted by Design/Builder pursuant to Paragraphs 6.06.A.2 and 6.06.B. Whether or not Owner’s Engineer approves a substitute item so pro​posed or submitted by Design/Builder, Design/Builder shall reimburse Owner for the charges of Owner’s Engineer for evaluat​ing each such proposed substi​tute. Design/Builder shall also reimburse Owner for the charges of Owner’s Engineer for making changes in the Contract Documents (or in the provisions of any other direct contract with Owner) resulting from the acceptance of each proposed substitute.

F. Design/Builder’s Expense: Design/Builder shall provide all data ​in support of any pro​posed substitute or “or‑equal” at Design/Builder’s expense.

6.07
Concerning Subcontractors, Suppliers, and Others tc "6.06  Concerning Subcontractors, Suppliers and Others " \l 2
A.
Design/Builder shall not employ any Subcontractor, Supplier, or other individual or entity against whom Owner may have reasonable objection.  Design/Builder shall not be required to employ any Subcontractor, Supplier, or other individual or entity to furnish or perform any of the Work against whom Design/Builder has reasonable objection.

B.
Design/Builder shall be fully responsible to Owner for all acts and omissions of the Subcontractors, Suppliers, and other individuals or entities performing or furnishing any of the Work just as Design/Builder is responsible for Design/Builder's own acts and omissions.  Nothing in the Construction Documents:

1.   shall create for the benefit of any such Subcontractor, Supplier, or other individual or entity any contractual relationship between Owner and any such Subcontractor, Supplier, or other individual or entity; 
2.   shall create any obligation on the part of Owner to pay or to see to the payment of any moneys due any such Subcontractor, Supplier, or other individual or entity except as may otherwise be required by Laws or Regulations.

C.
Design/Builder shall be solely responsible for scheduling and coordinating Subcontractors, Suppliers, and other individuals and entities performing or furnishing any of the Work under a direct or indirect contract with Design/Builder.

D.
Design/Builder shall require all Subcontractors, Suppliers, and such other individuals and entities performing or furnishing any of the Work to communicate with the Owner through Design/Builder.

E.
All Work performed for Design/Builder by a Subcontractor or Supplier will be pursuant to an appropriate Design Subagreement or Construction Subagreement between Design/Builder and the Subcontractor or Supplier which specifically binds the Subcontractor or Supplier to the applicable terms and conditions of the Contract Documents for the benefit of Owner.  Whenever any such agreement is with a Subcontractor or Supplier who is listed as a loss payee on the property insurance provided in Paragraph 5.07, the agreement between the Design/Builder and the Subcontractor or Supplier will contain provisions whereby the Subcontractor or Supplier waives all rights against Owner, Design/Builder, Owner's Consultant, and all other loss payees (and their officers, directors, members, partners, employees, agents, and other consultants and Subcontractors of each and any of them) for all losses and damages caused by any of the perils or causes of loss covered by such policies and any other property insurance applicable to the Work.  If the insurers on any such policies require separate waiver forms to be signed by any Subcontractor or Supplier, Design/Builder will obtain the same.

F. All Subcontractors shall have a minimum of five years of experience in their respective trades as a business entity (sole proprietorship, partnership, corporation).

6.08
Patent Fees and Royalties tc "6.07  Patent Fees and Royalties " \l 2
A.
Design/Builder shall pay all license fees and royalties and assume all costs incident to the use in the performance of the Work or the incorporation in the Work of any invention, design, process, product or device which is the subject of patent rights or copyrights held by others.  If a particular invention, design, process, product, or device is specified in the Conceptual Documents for use in the performance of the Construction and if to the actual knowledge of Owner its use is subject to patent rights or copyrights calling for the payment of any license fee or royalty to others, the existence of such rights shall be disclosed by Owner in the Conceptual Documents.

B.
To the fullest extent permitted by Laws or Regulations, Design/Builder shall indemnify and hold harmless Owner and Owner’s Consultant, and the officers, directors, partners, employees or agents, and other consultants of each and any of them from and against all claims, costs, losses and damages (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) arising out of or resulting from any infringement of patent rights or copyrights incident to the use in the performance of the Work or resulting from the specification or incorporation in the Work of any invention, design, process, product or device except those required by the Conceptual Documents.

C.
To the fullest extent permitted by Laws or Regulations, Owner shall indemnify and hold harmless Design/Builder and its officers, directors, members, partners, employees or agents, Subcontractors and Suppliers from and against all claims, costs, losses and damages (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) arising out of or resulting from any infringement of patent rights or copyrights incident to the use in the performance of the Work or resulting from the incorporation in the Work of any invention, design, process, product or device required by the Conceptual Documents, but not identified by Owner as being subject to payment of any license fee or royalty to others required by patent rights or copyrights.  

6.09
Permits tc "6.08  Permits " \l 2
A.
Unless otherwise provided in the Contract Documents, Design/Builder shall obtain and pay for all necessary permits, licenses, and approvals of governmental authorities having jurisdiction over the Work. Owner shall assist Design/Builder, when necessary, in obtaining such permits, licenses and approvals.  Design/Builder shall pay all governmental charges and inspection fees necessary for the performance of the Work, which are applicable on the last day for receipt of Proposals.  Design/Builder shall pay all charges of utility owners for connections for providing permanent service to the Work, and Owner shall pay all charges of such utility owners for capital costs related thereto.

6.10
Laws, Ordinance, Rules, and Regulations tc "6.09  Laws or Regulations " \l 2
A.
Design/Builder shall give all notices required by and comply with all Laws, Ordinance, Rules, and Regulations applicable to the performance of the Work.  Except where otherwise expressly required by applicable Laws and Regulations, Owner shall not be responsible for monitoring Design/Builder's compliance with any Laws or Regulations.

B.
If Design/Builder performs any Work that it is contrary to Laws or Regulations, Design/Builder shall bear all claims, costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs) arising out of or relating to such Work.

C.
Changes in Laws or Regulations after the Effective Date having an effect on the cost or time of performance may be the subject of a change in Contract Price or Contract Times.

6.11
Taxes tc "6.10  Taxes " \l 2
A.
Design/Builder shall pay all sales, consumer, use, and other similar taxes required to be paid by Design/Builder in accordance with the Laws or Regulations of the place of the Project which are applicable during the performance of the Work. 

6.12
Use of Site and Other Areas tc "6.11  Use of Site and Other Areas " \l 2
A.
Limitation on Use of Site and Other Areas.

1.
Design/Builder shall confine construction equipment, the storage of materials and equipment, and the operations of construction workers to the Site and other areas permitted by Laws or Regulations, and shall not unreasonably encumber the Site and other areas with construction equipment or other materials or equipment.  Design/Builder shall assume full responsibility for any damage to any such land or area, or to the owner or occupant thereof or of any adjacent land or areas, resulting from the performance of the Work.

2.
Should any claim be made by any such owner or occupant because of the performance of Work, Design/Builder shall promptly settle with such other party by negotiation or otherwise resolve the claim by arbitration or other dispute resolution proceeding or at law.

3.
To the fullest extent permitted by Laws or Regulations, Design/Builder shall indemnify and hold harmless Owner, Owner's Consultants and anyone directly or indirectly employed by any of them from and against all claims, costs, losses and damages (including, but not limited to, fees of engineers, architects, attorneys and other professionals and court and arbitration or other dispute resolution costs) arising out of or resulting from any claim brought by any such owner or occupant against Owner, or any other party indemnified hereunder to the extent caused by or based upon Design/Builder's performance of the Construction.

B.
Removal of Debris:  During the performance of the Construction, Design/Builder shall keep the premises free from accumulations of waste materials, rubbish, and other debris resulting from the Construction.  Removal and disposal of such waste materials, rubbish, and other debris shall conform to applicable Laws or Regulations.

C.
Cleaning:  Prior to Substantial Completion, Design/Builder shall clean the Site and make it ready for utilization by Owner.  At completion of Construction, Design/Builder shall remove all tools, appliances, construction equipment, temporary construction and machinery, and surplus materials and shall restore to original condition all property not designated for alteration by the Contract Documents.

D.
Loading Structures:  Design/Builder shall not load nor permit any part of any structure to be loaded in any manner that will endanger the structure, nor shall Design/Builder subject any part of the Construction or adjacent property to stresses or pressures that will endanger it.

6.13
Record Documents tc "6.12  Record Documents " \l 2
A.
Design/Builder shall maintain in a safe place at the Site one record copy of all Drawings, Specifications, Addenda, Change Orders, Field Orders and Work Change Directives in good order and annotated to show all changes made during performance of the Work.  These record documents together with all approved Submittals will be available to Owner for reference and shall be current at the time of Design/Builder’s submission of Application for Payment as a condition precedent for Owner’s recommendation of payment.  Upon completion of the Work, these record documents and Submittals will be delivered to Owner. 
Design/Builder shall include accurate locations for buried and imbedded items.
B. DESIGN/BUILDER shall record on a set of working drawings, showing installed dimensioned locations of all buried and concealed piping, conduit, valves, stub-outs, etc., and shall deliver same to the OWNER upon completion of the job.  Said drawings shall also show all changes made in actual construction from that shown on the Contract drawings.  These drawings shall have all dimensions and corrections shown. Design/Builder shall keep an updated set of working drawings as noted above to be available for review during the construction period.

C. The Contactor shall prepare record drawings using red ink on a clean set of prints of original contract drawings with revisions and annotations clearly and neatly written.  The OWNER will reject record drawings that are dirty, messy, illegible, or incomplete and return to Contactor to correct these deficiencies.  The Design/Builder shall keep the record drawings up to date over the course of the project.  The OWNER may hold progress payments if the Design/Builder is not adequately maintaining and updating the record drawings.

D. Design/Builder shall provide coordinates and top of pipe elevation for all buried yard piping on a site plan. Coordinates and elevation shall be provided for all fittings, bends, and specials.
6.14
Safety and Protection   tc "6.13  Safety and Protection   " \l 2
A.
DESIGN/BUILDER shall be solely responsible for initiating, maintaining and supervising all safety precau​tions and programs in connection with the Work in accordance with all applicable safety codes. The Design/Builder shall execute and maintain his/her work so as to avoid injury or damage to any person or property.  The Design/Builder shall comply with the requirements of the specifications relating to safety measures applicable in particular operations or kinds of work. Design/Builder shall take all necessary precautions for the safety of, and shall provide the necessary protection to prevent damage, injury or loss to:

1.
all persons on the  Site or who may be affected by the Work;

2.
all the Work and materials and equip​ment to be incorporated therein, whether in storage on or off the Site; and

3.
other property at the Site or adjacent thereto, including trees, shrubs, lawns, walks, pave​ments, roadways, structures, utilities, and Under​ground Facili​ties not designated for removal, reloca​tion, or replacement in the course of construc​tion.

B. Design/Builder shall comply with all applica​ble Laws and Regulations relating to the safety of persons or property, or to the protection of persons or property from damage, injury, or loss; and shall erect and main​tain all necessary safeguards for such safety and protec​tion. Design/Builder shall notify owners of adjacent property and of Underground Facilities and other utility owners when prosecution of the Work may affect them, and shall cooperate with them in the protection, remov​al, relocation, and replacement of their property.  All damage, injury, or loss to any proper​ty referred to in paragraph 6.14.A.2 or 6.14.A.3 caused, directly or indirectly, in whole or in part, by Design/Builder, any Subcontractor, Supplier, or any other individual or entity directly or indirect​ly em​ployed by any of them to perform any of the Work, or anyone for whose acts any of them may be liable, shall be remedied by Design/Builder (except damage or loss attributable to the acts or omissions of OWNER or Resident Project Representative, or Owner’s Engineer, or anyone employed by any of them, or anyone for whose acts any of them may be liable, and not attributable, directly or indirectly, in whole or in part, to the fault or negligence of Design/Builder or any Subcontractor, Supplier, or other individual or entity directly or indirectly em​ployed by any of them). Design/Builder’s duties and responsibil​ities for safety and for protection of the Work shall continue until such time as all the Work is completed and Owner has issued a notice to Design/Builder in accordance with paragraph 13.10 that the Work is accept​able (except as otherwise ex​pressly provided in connection with Substantial Comple​tion).

C.
The Design/Builder shall establish, implement, and maintain a written injury prevention program as required by Labor Code Section 6401.7. This written program shall be submitted to the Owner within five (5) days of Notice to Proceed. The Design/Builder's injury prevention program will not be reviewed for approval. 
Before proceeding with any construction work, the Design/Builder shall take the necessary action to comply with all provisions for safety and accident prevention. 
The Design/Builder shall develop and maintain for the duration of this Contract, a safety program that will effectively incorporate and implement all required safety provisions. The Design/Builder, as a part of its safety program, shall maintain at its office or other well‑known place at the Site, safety equipment applicable to the Work as prescribed by the aforementioned authorities, all items necessary for giving first aid to the injured, and shall establish the procedure for the immediate removal to a hospital or a doctor's care of persons who may be injured on the jobsite.

1. 
If death or serious injuries or serious damages are caused, the accident shall be reported immediately by telephone or messenger to both the Resident Project Representative and the OWNER. In addition, the Design/Builder must promptly report in writing to the Owner all accidents whatsoever arising out of, or in connection with, the performance of the Work whether on, or adjacent to, the Site, giving full details and statements of witnesses. The Design/Builder shall make all reports as are, or may be, required by any authority having jurisdiction, and permit all safety inspections of the work being performed under this Contract.

2.
If a claim is made by anyone against the Design/Builder or any Subcontractor on account of any accident, the Design/Builder shall promptly report the facts in writing to the Owner, giving full details of the claim.

6.15
Safety Representative tc "6.14  Safety Representative " \l 2
A.
Design/Builder shall designate a qualified and experienced safety representative at the Site whose duties and responsibilities shall be the prevention of accidents and the maintaining and supervising of safety precautions and programs.

6.16
Hazard Communication Programs tc "6.15  Hazard Communication Programs " \l 2
A.
Design/Builder shall be responsible for coordinating any exchange of material safety data sheets or other hazard communication information required to be made available to or exchanged between or among employers at the Site in accordance with Laws or Regulations.

6.17
Emergencies tc "6.16  Emergencies " \l 2
A.
In emergencies affecting the safety or protection of persons or the Work or property at the Site or adjacent thereto, Design/Builder is obligated to act to prevent threatened damage, injury or loss.  Design/Builder shall give Owner prompt written notice if Design/Builder believes that any significant changes in the Work or variations from the Contract Documents have been caused thereby or are required as a result thereof.  If Owner determines a change in the Contract Documents is required because of the action taken by Design/Builder in response to such an emergency, a Work Change Directive or Change Order will be issued.

B. If Design/Builder fails to take appropriate action in an emergency, the OWNER also reserves the right to perform any portion of the work that threatens the safety or health of the public or OWNER, and the safety of the work or any property or equipment. In the event the OWNER performs work in an emergency, an appropriate Change Order shall be issued unilaterally deducting from the payments then or thereafter due the Design/Builder the cost for performing such Work, including compensation for the Resident Project Representative’s, and OWNER's additional services made necessary by such  emergency.
6.18
Submittals tc "6.17  Submittals " \l 2
A.
Owner will review and approve Submittals in accordance with the schedule of required Submittals accepted by Owner as required by Paragraph 2.07.A.  Owner's review and approval will be only to determine if the items covered by the Submittals will, after installation or incorporation in the construction, conform to the information given in the Contract Documents and be compatible with the design concept of the completed Project as a functioning whole as indicated by the Contract Documents.  Owner's review and approval will not extend to means, methods, techniques, sequences, or procedures of construction (except where a particular means, method, technique, sequence, or procedure of construction is specifically and expressly called for by the Contract Documents) or to safety precautions or programs incident thereto.  The review and approval of a separate item as such will not indicate approval of the assembly in which the item functions.

B.
Owner's review and approval of Submittals shall not relieve Design/Builder from responsibility for any variation from the requirements of the Contract Documents unless Design/Builder has in a separate written communication at the time of submission called Owner's attention to each such variation and Owner has given written approval.

C.
Construction prior to Owner's review and approval of any required Submittal will be at the sole risk of Design/Builder, but in no case shall construction begin without a Notice To Proceed For Construction.

D. Submittals shall be transmitted and reviewed in accordance with procedures stated in the Supplementary Conditions and Project Manual.

6.19  Continuing the Work
tc "6.18  Continuing the Work " \l 2
A.
Design/Builder shall continue the Work and adhere to the progress schedule during all disputes or disagreements with Owner.  No Work shall be delayed or postponed pending resolution of any disputes or disagreements, except as Design/Builder and Owner may otherwise agree in writing.

6.20
Post-Construction Phase tc "6.19  Post-Construction Phase " \l 2  

A.
Design/Builder shall:

1.
Provide assistance in connection with the start-up, testing, refining and adjusting of any equipment or system.

2.
Assist Owner in training staff to operate and maintain the Work.

3.
Assist Owner in developing systems and procedures for control of the operation and maintenance of and record keeping for the Work.

B. Post-Construction Phase work shall be performed in accordance with procedures stated in the Supplementary Conditions and Project Manual.

6.21
Design/Builder's General Warranty and Guarantee tc "6.20  Design/Builder's General Warranty and Guarantee " \l 2
A.
Design/Builder warrants and guarantees to Owner for a period of two (2) years, that all Construction will be in accordance with the Contract Documents and will not be defective.  The warranty period shall commence at Final Completion.
B. Design/Builder's warranty and guarantee hereunder excludes defects or damage caused by: 

1.
abuse, modification or improper maintenance or operation by persons other than Design/Builder, Subcontractors, or Suppliers or any other individual or entity for whom Design/Builder is responsible; or

2.
normal wear and tear under normal usage.

C.
Design/Builder's obligation to perform and complete the Work in accordance with the Contract Documents shall be absolute.  None of the following will constitute an acceptance of Work that is not in accordance with the Contract Documents or a release of Design/Builder's obligation to perform the Work in accordance with the Contract Documents:

1.
Observations or recommendations by Owner;

2.
The making of any progress or final pay​ment;

3.
The issuance of a certificate of Substantial Completion;

4.
Use or occupancy of the Work or any part thereof by Owner;

5.
Any review and approval of a Submittal; 

6.
Any inspection, test, or approval by others; or

7.
Any correction of defective Construction by Owner.

8.
Any acceptance by Owner or any failure to do so.

6.22
Indemnification   tc "6.21  Indemnification   " \l 2
A. To the fullest extent permitted by Laws and Regula​tions, Design/Builder shall indemnify and hold harmless Owner, Resident Project Representative and Owner’s Engineer, and the officers, directors, partners, employees, agents, consultants and subcontractors of each and any of them from and against all claims, costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs) arising out of or relating to the perfor​mance of the Work, provided that any such claim, cost, loss, or damage is attributable to bodily injury, sickness, disease, or death, or to injury to or destruction of tangible property (other than the Work itself), includ​ing the loss of use resulting therefrom but only to the extent caused by any act or omission of Design/Builder, any Subcontrac​tor, any Supplier, or any individual or entity directly or indirect​ly employed by any of them to perform any of the Work or anyone for whose acts any of them may be liable .

B. In any and all claims against Owner or Owner’s Engineer or any of their respective consultants, agents, officers, directors, partners, or employees by any employ​ee (or the survivor or personal representative of such employee) of Design/Builder, any Subcontractor, any Supplier, or any individual or entity directly or indirect​ly employed by any of them to perform any of the Work, or anyone for whose acts any of them may be liable, the indemnification obligation under Paragraph 6.22.A shall not be limited in any way by any limitation on the amount or type of damages, compensation, or benefits payable by or for Design/Builder or any such Subcontractor, Suppli​er, or other individual or entity under workers’ compen​sation acts, disability benefit acts, or other employee benefit acts.

C. The indemnification obligations of Design/Builder under Paragraph 6.22.A shall not extend to the liability of Resident Project Representative and Owner’s Engineer and their respective officers, directors, partners, employ​ees, agents, consultants and subcontractors arising out of:

1. the preparation or approval of, or the failure to prepare or approve, maps, Drawings, opinions, reports, surveys, Change Orders, designs, or Specifica​tions; or

2. giving directions or instructions, or failing to give them, if that is the primary cause of the injury or damage.

6.23
Requirements Of California Law For Public Contracts

The Work shall comply with the applicable statutes of the State of California.  All parties to this contract shall determine the contents of all applicable statutes and comply with their provision throughout the performance of the contract.

A.
Apprentices- Section 1773.3 of the California Labor Code requires the OWNER to notify the Division of Apprenticeship Standards of award of public work contracts which fall within the jurisdiction of Section 1777.5 of the Labor Code.  The Design/Builder's attention is directed to Sections 1777.5, 1777.6, and 1777.7 of the Labor Code concerning employment of apprentices by the Design/Builder and his Subcontractors.  The Design/Builder shall comply with the requirements of these sections and will be solely responsible for performing all work under the contract in compliance with Section 1777.5.

In general, Section 1777.5 requires that the Design/Builder and Subcontractors follow specific procedures to determine the number of apprentices that must be employed and, under certain conditions, to contribute to funds established for administration of apprenticeship programs.

Excerpts from the California Labor Code and other information regarding the employment of apprentices on public work may be obtained from the Division of Apprenticeship Standards, 455 Golden Gate Avenue, San Francisco, California, or one of its branch offices.

B.
Labor Discrimination and Unlawful Employment Practices - Attention is directed to Section 1735 of the Labor Code which states:

"No discrimination shall be made in the employment of persons upon public works because of the race, religious creed, color, national origin, ancestry, physical handicap, medical condition, marital status, or sex of such persons, except as provided in Section 12940 of the California Government Code, and every Design/Builder for public works violating this section is subject to all the penalties imposed for violation of this chapter."

Attention is also directed to Section 12940 of the California Government Code which, although not specifically concerned with public works contracts, enumerates unlawful employment practices applicable to all employers in the State of California.

C.
Hours of Labor- Eight (8) hours labor constitutes a legal days work.  The Design/Builder shall forfeit, as penalty to the OWNER, $25.00 for each worker employed in the execution of the contract, by him or by any Subcontractor under him, for each calendar day during which any worker is required or permitted to labor more than eight (8) hours in violation of the provisions of the Labor Code and, in particular, Section 1810 to Section 1815 thereof, inclusive.

D. Prevailing Wages and Payroll Records 
1. In accordance with Section 1770 of the Labor Code, the City has ascertained and does hereby specify that the prevailing wage rates shall be those provided in Article 00100‑22.00, WAGE RATES. The said rates shall include all employer payments that are required by Section 1773.1 of the Labor Code. The City will furnish to the Design/Builder, upon request, a copy of such prevailing rates. It shall be the duty of the Design/Builder to post a copy of such prevailing wages at the job site.

2. For each worker paid less than the stipulated rate in the execution of the Contract by the Design/Builder, or any subcontractor under it, in violation of the provisions of the Labor Code, and in particular, Section 1770 to Section 1780, inclusive, the Design/Builder shall be subject to the provisions and penalties of Section 1775 of the Labor Code. In addition to said penalty, and pursuant to said Section 1775, the difference between such stipulated prevailing wage rates and the amounts paid to each worker for each calendar day, or portion thereof, for which each worker was paid less than the stipulated prevailing rate shall be paid to each worker by the Design/Builder.

3. The wage rates set forth are the minimum that may be paid by the Design/Builder. Nothing herein contained shall be construed as preventing the Design/Builder from paying more than the minimum set forth.

4. No extra compensation whatever shall be allowed by the City due to the inability of the Design/Builder to hire labor at the minimum rate nor for any necessity for payment by the Design/Builder for subsistence, travel time, overtime, or other added compensation, all of which possibilities are elements to be considered and ascertained to the Design/Builder's own satisfaction in preparing the bid.

5. If it becomes necessary to employ a craft other than those listed in the prevailing rates, the Design/Builder shall notify the City immediately and the City will obtain the additional prevailing rate from the Director of the Department of Industrial Relations and the rate thus determined shall be applicable as a minimum at the time of initial employment.

6. The Design/Builder shall pay travel and subsistence payments to workers needed to execute the work as such travel and subsistence payments are defined in the applicable collective bargaining agreement filed with the Department of Industrial Relations pursuant to Labor Code Section 1773.8.

7. City and Design/Builder stipulate that Labor Code Section 1775 will be complied with.

8. The City will consider the type of work performed by classification traditionally employed to perform said work in San Joaquin County when determining appropriate craft, classification or type of worker under Section 1733.2 of the California Labor Code.

9. The City has determined that all installation of mechanical, pressure and/or process piping; soil, waste and vent piping, potable and non-potable piping shall be paid at the prevailing wage for a Plumber and/or Pipefitter.

10. Certified Payrolls ‑ In accordance with Section 1776 of the Labor Code, each Design/Builder and subcontractor shall keep an accurate payroll record, showing the name, address, social security number, work classification, straight time, and overtime hours worked each day and week, and the actual per diem wages paid to each journeyman, apprentice, worker, or other employee employed by the Design/Builder or the subcontractor in connection with the project.

11. The payroll records shall be certified and shall be available for inspection at all reasonable hours at the principal office of the Design/Builder on the following basis:

12. A certified copy of an employee's payroll record shall be made available for inspection or furnished to the employee or its authorized representative on request.

13. A certified copy of all payroll records shall be made available for inspection or furnished upon request to a representative of the City, the Division of Labor Standards Enforcement, and the Division of Apprenticeship Standards of the Department of Industrial Relations.

14. A certified copy of all payroll records shall be made available upon request by the public in accordance with Section 1776 of the Labor Code.

15. The Design/Builder is responsible for its and its subcontractors’ compliance with the provisions of Section 1776 of the Labor Code.

16. Overtime Requirements ‑ The Contractor shall forfeit, as a penalty to the City, the penalty as provided in Section 1813 of the Labor Code for each worker employed in the execution of the Contract by the Design/Builder, or any subcontractor under the Design/Builder, for each day during which such worker is required or permitted to work more than eight (8) hours in any one day and forty (40) hours in any one week, in violation of the provisions of the Labor Code, and in particular, Section 1810 to Section 1815 thereof, inclusive, except that work performed by employees of Design/Builders in excess of eight (8) hours a day and forty (40) hours during one week, shall be permitted upon compensation for all hours worked in excess of eight (8) hours per day, at not less than one and a half (1.5) times the basic rate of pay as provided for in Section 1815 of the Labor Code.

17. Apprentice and Trainee ‑ Attention is directed to the provisions in Section 1777.5 of the Labor Code and in accordance with the regulations of the California Apprenticeship Council concerning the employment of apprentices by the Design/Builder or any subcontractor under the Design/Builder.

18. Section 1777.5 requires the Design/Builder or subcontractors employing tradespersons in any apprenticeable occupation to apply to the joint apprenticeship committee nearest the site of the project that administers the apprenticeship program in that trade for a certificate of approval. The Design/Builder and subcontractors are required to submit contract award information to the applicable joint apprenticeship committee. As provided for in Section 1777.5 of the Labor Code, the Contractor is required to make contributions to funds established for the administration of apprenticeship programs.

19. It shall be the responsibility of the Design/Builder to abide by the provisions of Section 1777.5 of the Labor Code and to require all subcontractors employed by or contracting with the Design/Builder to abide by said provisions. The Design/Builder shall furnish the City any and all evidence of compliance with this code section when requested by the City.

20. For failure to comply with Section 1777.5 of the Labor Code, the Design/Builder shall be subject to the penalties in Section 1777.7 of the Labor Code. The provisions of this paragraph apply only to the extent not preempted by Federal law.

21. Workers' Compensation Insurance ‑ The Design/Builder is required to secure the payment of compensation to its employees in accordance with the provisions of Sections 1860 and 3700 of the Labor Code and Paragraph 00820‑2.40, Workers' Compensation Insurance.

E.
Assignment of Claims - California Government Code Section 4551 requires that the following provision be included in public works contracts:

"In entering into a public works contract or a subcontract to supply goods, services, or materials pursuant to a public works contract, the Design/Builder or Subcontractor offers and agrees to assign to the awarding body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2 commencing with Section 16700 of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, services, or materials pursuant to the public works contract or the subcontract.  This assignment shall be made and become effective at the time the awarding body tenders final payment to the Design/Builder, without further acknowledgment by the parties."

F.
Trench Safety Plan- In accordance with Section 6705 of the California Labor Code, for trenches 5 feet or more in depth, the Design/Builder shall submit to and receive from the OWNER the acceptance of a detailed plan showing design of shoring, bracing, sloping, or other provisions to be made for worker protection from the hazards of caving ground.  Such plan shall be submitted at least five (5) days before the Design/Builder intends to begin work on the trenches.

If such plan varies from the shoring system standards established by the Construction Safety Orders, the plan shall be prepared by a registered civil or structural engineer certifying that the plan is not less effective than the shoring, bracing, sloping or other provisions of the Safety Orders
In no event shall the Design/Builder use a shoring, sloping, or protective system less effective than that required by said Construction Safety Orders.  Submission of this plan in no way relieves the Design/Builder of the requirement to maintain safety in all areas.  If excavations or trench work requiring a Cal/OSHA permit are to be undertaken, the Design/Builder shall submit his/her permit with the excavation/trench work safety plan to the OWNER before work begins.
Nothing herein shall be deemed to allow the use of shoring, sloping, or protective system less effective than that required by the Construction Safety Orders of the Division of Industrial Safety.

6.24
Notification of Construction
A.
The Design/Builder shall notify property owners adjacent to construction activities a minimum of forty-eight (48) hours prior to conducting any portions of Work on or adjacent to private properties.  The Design/Builder shall provide adequate notice to property owners for removal of animals, vehicles, or any other private property located within the permanent or temporary easement limits.

B.
Property shall be restored to pre-project conditions after completion of the Work on private property unless an otherwise written agreement is obtained from the property owner.

6.25
Construction Water
The availability and supply of construction water, or lack thereof, by OWNER is stated in the Supplementary Conditions.

6.26
Existing Improvements

 A. At least forty eight (48) hours before performing any excavation work or other work that could damage existing improvements within, or adjacent to, the Work area, the Design/Builder shall notify the owners of properties adjacent to the Work area of intended commencement of such Work and request that such owners mark or otherwise indicate the location of underground improvements of which they are aware or other improvements not readily apparent from visual inspection of the adjacent property, such as survey points and utility service installations not owned by the appropriate utility. The Design/Builder shall also give forty eight (48) hours notice to occupants or owners of adjacent property to permit them to salvage or relocate plants, trees, fences, sprinklers, and other improvements within the right‑of‑way that are designated for removal or would be destroyed because of the Work. Design/Builder shall furnish to the Owner written documentation of its contact(s) with property owners (1) requesting them to mark or otherwise indicate the location of their respective facilities, and (2) notifying them to salvage or relocate landscaping or improvements within or adjacent to the Work area within forty eight (48) hours after such contact(s).

B.
It shall be the Design/Builder's responsibility to determine the exact location (including depth for underground improvements) and to document the existing condition of all existing improvements which are not designated for removal (e.g., curbs, sidewalks, survey points, fences, walls, signs, utility installations, pavements, structures, etc.) which the Design/Builder believes may affect or be affected by Design/Builder's operations.

C.
In the event that existing improvements are found that have not been identified in the Contract Documents or indicated by the respective property owner, or are found to exist in a substantially different location than so indicated, the Design/Builder shall (1) immediately notify the Owner thereof in writing, and (2) take steps to avoid damaging such improvements, including ascertaining their exact location if not yet known.

D.
The Design/Builder shall immediately notify the Owner and the property owner of any damage to any existing improvements that have not been designated to be removed. The Design/Builder shall be responsible for the cost of repairing or restoring all existing improvements which are not designated for removal (e.g., curbs, sidewalks, survey points, fences, walls, signs, utility installations, pavements, structures, etc.) and are damaged or removed as a result of its operations. Repairs and replacements shall be at least equal to existing improvements and shall match them in finish and dimension.


The Design/Builder shall protect from damage all landscaping (e.g., trees, lawns, shrubbery, etc.) adjacent to the Work area or within the Work area that have not been designated to be removed. The Design/Builder shall immediately notify the Owner and the property owner of any damage to any such landscaping which is not designated for removal. The Design/Builder shall be responsible for the cost of restoring or replacing such landscaping in as nearly the original conditions and location as it is reasonably possible. Lawns shall be re‑seeded and covered with suitable mulch.

E.
Except where an owner of damaged improvements or landscaping has advised that he or she intends to repair the damage himself or through forces that he or she will retain or has retained, Design/Builder shall, within 24 hours of receipt from the owner of notice to commence correction of damage, notify the Owner in writing if Design/Builder intends to repair the damage. During nights and weekends when work is not in progress, owner may give such notice by telephone or by facsimile transmission to the Design/Builder's facsimile number designated and such notice will be immediately effective. The Design/Builder’s failure to provide timely written notification that it intends to repair the damage shall be deemed its agreement that the owner may repair the damage at Design/Builder's expense without further notice and without prejudice to any other remedy available to OWNER. In such event, the Design/Builder may observe the Work if this can be done without in any way delaying the progress thereof, but may not contest any element of the expense of repair or the lack of further notice. This provision is in addition to any other remedy, including the remedy provided in 13.09, OWNER May Correct Defective Work

6.26
Communications to Owner and Resident Project Representative

A.
Except as other​wise provided in these General Condi​tions, Design/Builder shall issue all communi​cations to OWNER and Owner’s Engineer through Resident Project Representative.

B. Project communication systems and procedures shall be in accordance with communication systems and procedures stated in the Supplementary Conditions or Project Manual.

ARTICLE 7 – OTHER CONSTRUCTIONtc "ARTICLE 7 – OTHER CONSTRUCTION"
7.01
Related Work at Site tc "7.01  Related Work at Site " \l 2
A.
Owner may perform other Work related to the Project at the Site with Owner's employees, or through other direct contracts therefor, or have other work performed by utility owners.  If such other work is not noted in the Contract Documents, then:

1.
Written notice thereof will be given to Design/Builder prior to starting any such other work; and

2.
if Owner and Design/Builder are unable to agree on entitlement to or on the extent, if any, of any adjustment in the Contract Price or Contract Times that should be allowed as a result of such other work, Design/Builder may make a Claim therefor as provided in Article 10. 

B.
Design/Builder shall afford each other Contractor who is a party to such a direct contract and each utility owner (and Owner, if Owner is performing the additional work with Owner's employees) proper and safe access to the Site and a reasonable opportunity for the introduction and storage of materials and equipment and the execution of such other work and shall properly connect and coordinate the Work with theirs.  Unless otherwise provided in the Contract Documents, Design/Builder shall do all cutting, fitting, and patching of the Work that may be required to make its several parts come together properly and integrate with such other work.  Design/Builder shall not endanger any work of others by cutting, excavating, or otherwise altering such work; provided, however, that Design/Builder may cut or alter others' work with the written consent of Owner and the others whose work will be affected.  The duties and responsibilities of Design/Builder under this paragraph are for the benefit of such utility owners and other Contractors to the extent that there are comparable provisions for the benefit of Design/Builder in said direct contracts between Owner and such utility owners and other Contractors.

C.
If the proper execution or results of any part of Design/Builder's Work depends upon work performed or services provided by others under this Article 7, Design/Builder shall inspect such other work and appropriate instruments of service and promptly report to Owner in writing any delays, defects or deficiencies in such other work or services that render it unavailable or unsuitable for the proper execution and results of Design/Builder's Work.  Design/Builder's failure so to report will constitute an acceptance of such other work as fit and proper for integration with Design/Builder's Work except for latent or nonapparent defects and deficiencies in such other work.

7.02
Coordination tc "7.02  Coordination " \l 2
A.
If Owner intends to contract with others for the performance of other work on the Project at the Site, the following will be set forth in Supplementary Conditions:

1.
The individual or entity who will have authority and responsibility for coordination of the activities among the various prime Design/Builders will be identified;

2.
The specific matters to be covered by such authority and responsibility will be itemized; and

3.
The extent of such authority and responsi​bilities will be provided.  

B.
Unless otherwise provided in the Supplementa​ry Conditions, Owner shall have sole authority and responsibility in respect of such coordination.

7.03  Legal Relationships 
A.
Paragraphs 7.01.A and 7.02 are not applicable for utilities not under the control of Owner.

B.
Each other direct contract of Owner under Paragraph 7.01.A shall provide that the other Design/Builder is liable to Owner and Design/Builder for the reasonable direct delay and disruption costs incurred by Design/Builder as a result of the other Design/Builder’s wrongful actions or inactions.

C.
Design/Builder shall be liable to Owner and any other Design/Builder under direct contract to Owner for the reasonable direct delay and disruption costs incurred by such other Design/Builder as a result of Design/Builder’s wrongful action or inactions.

ARTICLE 8 – OWNER'S RESPONSIBILITIEStc "ARTICLE 8 – OWNER'S RESPONSIBILITIES"
8.01
Communications to Design/Builder
A.
Except as other​wise provided in these General Condi​tions, OWNER shall issue all communi​cations to Design/Builder through Resident Project Representative.

B. Project communication systems and procedures shall be in accordance with communication systems and procedures stated in the Supplementary Conditions or Project Manual.

8.02
Furnish Data

A.
OWNER shall promptly furnish the data required of OWNER under the Contract Documents.

8.03
Pay Promptly When Due

A.
OWNER shall make payments to Design/Builder prompt​ly when they are due but no later than 30 days after acceptance of progress payment application.

8.04
Lands and Easements; Reports and Tests
A.
OWNER’s duties in respect of providing lands and easements and providing engineering surveys to establish reference points are set forth in paragraphs 4.01.  Paragraph 4.02 refers to OWNER’s identifying and making available to Design/Builder copies of reports of explora​tions and tests of subsurface conditions and drawings of physical conditions in or relating to existing surface or subsurface structures at or contigu​ous to the Site that have been utilized by Owner’s Engineer in preparing the Contract Documents.

8.05
Insurance

A.
OWNER’s responsibilities, if any, in respect to pur​chasing and maintaining liability and property insur​ance are set forth in Article 5.

8.06
Change Orders

A.
OWNER is obligated to execute Change Orders as indicated in Article 12.

8.07
Inspections, Tests, and Approvals

A.
OWNER’s responsibility in respect to certain inspec​tions, tests, and approvals is set forth in Article 13.

8.08
Limitations on OWNER’s Responsibilities

A.
The OWNER shall not supervise, direct, or have control or authority over, nor be responsible for, Design/Builder’s means, methods, techniques, se​quences, or procedures of construction, or the safety precautions and programs incident thereto, or for any failure of Design/Builder to comply with Laws and Regulations applica​ble to the perfor​mance of the Work.  OWNER will not be responsible for Design/Builder’s failure to perform the Work in accordance with the Contract Documents.

8.9
Undisclosed Hazardous Environmental Condition

A.
OWNER’s responsibility in respect to an undis​closed Hazard​ous Environmental Condition is set forth in paragraph 4.05.

8.10
Evidence of Financial Arrangements

A.
If and to the extent OWNER has agreed to furnish Design/Builder reasonable evi​dence that financial arrangements have been made to satisfy OWNER’s obligations under the Contract Documents, OWNER’s responsibility in respect thereof will be as set forth in the Supplementary Conditions.

ARTICLE 9 – RESIDENT PROJECT REPRESENTATIVE’S AND OWNER’S ENGINEER’S STATUS DURING DESIGN AND CONSTRUCTIONtc "ARTICLE 9 – CHANGES IN THE WORK; CLAIMS"
9.01
Owner’s Representative
A. Resident Project Representative and Owner’s Engineer will be Owner’s representa​tives during the design and construction period. The duties and responsi​bilities and the limitations of authority of Resident Project Representative and Owner’s Engineer as Owner’s representatives during design and construction are set forth in the Contract Documents and will not be changed without written consent of Owner, Resident Project Representative and Owner’s Engineer.

9.02
Visits to Site
A. Owner’s Engineer may make visits to the Site at inter​vals appropriate to the various stages of construc​tion as Owner’s Engineer deems necessary in order to observe as an experienced and qualified design profes​sional the progress that has been made and the quality of the various aspects of Design/Builder’s executed Work. Based on informa​tion obtained during such visits and observations, Owner’s Engineer, for the benefit of Owner, will determine, in general, if the Work is proceeding in accordance with the Con​struction Documents. Owner’s Engineer will not be required to make exhaustive or continuous inspections on the Site to check the quality or quantity of the Work. Owner’s Engineer’s efforts will be directed toward provid​ing for Owner a greater degree of confidence that the completed Work will conform generally to the Con​tract Documents. On the basis of such visits and observations, Owner’s Engineer will endeav​or to guard Owner against defective Work.

B. Resident Project Representative will make visits to the Site at inter​vals appropriate to the various stages of construc​tion as Resident Project Representative deems necessary in order to observe the progress that has been made and the quality of the various aspects of Design/Builder’s executed Work. Based on informa​tion obtained during such visits and observations, Resident Project Representative, for the benefit of Owner, will determine, in general, if the Work is proceeding in accordance with the Con​tract Documents. Resident Project Representative will not be required to make exhaustive or continuous inspections on the Site to check the quality or quantity of the Work. Resident Project Representative’s efforts will be directed toward provid​ing for Owner a greater degree of confidence that the completed Work will conform generally to the Con​tract Documents. On the basis of such visits and observations, Resident Project Representative will keep Owner informed of the progress of the Work, and will endeav​or to guard Owner against defective Work.

C. Owner’s Engineer’s and Resident Project Representative’s visits and obser​vations are subject to all the limitations on Owner’s Engineer’s authori​ty and responsibility set forth in Paragraph 9.09. Particu​larly, but without limitation, during or as a result of Owner’s Engineer's visits or observations Resident Project Representative’s visits or observations of Design/Builder's Work, Owner’s Engineer and Resident Project Representative’s visits will not supervise, direct, control, or have authority over or be responsible for Design/Builder’s means, meth​ods, techniques, sequences, or procedures of construc​tion, or the safety precautions and programs incident thereto, or for any failure of Design/Builder to comply with Laws and Regulations applicable to the performance of the Work.

9.03
Resident Project Representative
A. Resident Project Representative shall not authorize any deviation from the Contract Documents or substitutions of materials or equipment. 
B.  If Owner designates another represen​tative or agent to represent Owner at the Site who is not Resident Project Representative’s consultant, agent or em​ployee, the responsibilities and authority and limitations thereon of such other individual or entity will be as provid​ed in Article 9.
9.04
Authorized Variations in Work
A. Resident Project Representative or Owner’s Engineer may authorize minor varia​tions in the Work from the requirements of the Construction Documents which do not involve an adjust​ment in the Contract Price or the Contract Times and are compat​i​ble with the design concept of the com​pleted Project as a functioning whole as indicated by the Construction Docu​ments. These may be accomplished by a Field Order and will be binding on Owner and also on Design/Builder, who shall perform the Work in​volved promptly. If Owner or Design/Builder believes that a Field Order justifies an adjustment in the Contract Price or Contract Times, or both, and the parties are unable to agree on entitlement to or on the amount or extent, if any, of any such adjustment, a Claim may be made therefor as provided in Paragraph 10.03.

9.05
Rejecting Defective Work
A. Resident Project Representative will have authority to reject Work which Resident Project Representative or Owner’s Engineer believes to be defective, or that Resident Project Representative or Owner’s Engineer believes will not produce a completed Project that conforms to the Contract Documents or that will prejudice the integri​ty of the design concept of the completed Project as a functioning whole as indicated by the Contract Documents. Resident Project Representative will also have authority to require special inspec​tion or testing of the Work as provided in Paragraph 13.03, whether or not the Work is fabricated, installed, or completed.

B. The acceptance at any time of materials or equipment by or on behalf of Owner shall not be a bar to future rejection if they are subsequently found to be defective, inferior in quality, or not equal to the material or equipment specified, or are not as represented to Resident Project Representative, Owner’s Engineer or Owner.

9.06
Shop Drawings, Change Orders and Payments
A. In connection with Owner’s Engineer’s authority, and limitations thereof, as to Design Drawings, Specifications, Shop Drawings and Sample Submittals, see Paragraph 6.18.

B. In connection with Owner’s Engineer’s and Resident Project Representative’s authority as to Change Orders, see Articles 10, 11, and 12.

C. In connection with Resident Project Representative’s authority as to Applications for Payment, see Article 14.

9.07
Determinations for Unit Price Work
A. Resident Project Representative will determine the actual quanti​ties and classifications of Unit Price Work per​formed by Design/Builder. Resident Project Representative will review with Design/Builder the Owner’s Engineer’s preliminary determina​tions on such matters before rendering a written deci​sion thereon (by recommendation of an Application for Pay​ment or otherwise). Resident Project Representative’s written decision thereon will be final and binding (except as modified by Resident Project Representative to reflect changed factual conditions or more accurate data) upon Owner and Design/Builder, subject to the provisions of Paragraph 10.05.

9.08
Decisions on Requirements of Contract Documents and Acceptability of Work
A. Owner’s Engineer will be the initial inter​preter of the requirements of the Contract Documents with respect to matters of design intent.  Resident Project Representative will be the initial interpreter of the requirements of the Contract Documents with respect to administrative matters and judge of the acceptability of the Work thereunder. All matters in question and other matters between Owner and Design/Builder arising prior to the date final payment is due relating to the acceptability of the Work, and the interpretation of the requirements of the Contract Documents pertaining to the performance of the Work, will be referred initially to Resident Project Representative in writing within 30 days of the event giving rise to the question.

B. Resident Project Representative or Owner’s Engineer through Resident Project Representative will, with reasonable promptness, render a written decision on the issue referred. If Owner or Design/Builder believe that any such decision entitles them to an adjustment in the Contract Price or Contract Times or both, a Claim may be made under Paragraph 10.03. The date of Resident Project Representative’s or Owner’s Engineer’s decision shall be the date of the event giving rise to the issues referenced for the purposes of Paragraph 10.03.

C. Resident Project Representative’s or Owner’s Engineer’s written decision on the issue referred will be final and binding on Owner and Design/Builder, subject to the provisions of Paragraph 10.03.

D. When functioning as interpreter and judge under this Paragraph 9.08, Resident Project Representative and Owner’s Engineer will not show partiality to Owner or Design/Builder and will not be liable in connection with any interpretation or decision rendered in good faith in such capacity. 

9.09
Limitations on Resident Project Representative’s and Owner’s Engineer’s Authority and Responsibilities
A. Neither Resident Project Representative’s and Owner’s Engineer’s authority or respon​sibility under this Article 9 or under any other provi​sion of the Contract Documents nor any decision made by Resident Project Representative or Owner’s Engineer in good faith either to exercise or not exer​cise such authority or respon​sibility or the undertak​ing, exercise, or performance of any authority or respon​sibility by Resident Project Representative or Owner’s Engineer shall create, impose, or give rise to any duty in contract, tort, or otherwise owed by Resident Project Representative or Owner’s Engineer to Design/Builder, any Subcon​tractor, any Supplier, any other individual or entity, or to any surety for or employ​ee or agent of any of them.

B. Resident Project Representative and Owner’s Engineer will not supervise, direct, control, or have authority over or be responsible for Design/Builder’s means, meth​ods, techniques, se​quences, or procedures of construction, or the safety precautions and programs incident thereto, or for any failure of Design/Builder to comply with Laws and Regulations applicable to the perfor​mance of the Work. Resident Project Representative and Owner’s Engineer will not be respon​sible for Design/Builder’s failure to perform the Work in accor​dance with the Contract Documents.

C. Resident Project Representative and Owner’s Engineer will not be responsible for the acts or omissions of Design/Builder or of any Subcontrac​tor, any Supplier, or of any other individual or entity performing any of the Work.

D. Resident Project Representative’s review of the final Applica​tion for Payment and accompanying documentation and all mainte​nance and operat​ing instructions, schedules, guarantees, bonds, certificates of inspection, tests and approvals, and other documen​tation required to be delivered by the Contract Documents will only be to determine gener​ally that their content complies with the require​ments of, and in the case of certificates of in​spections, tests, and approvals that the results certified indicate compli​ance with the Contract Documents.

E. The limitations upon authority and responsi​bil​i​ty set forth in this Paragraph 9.09 shall also apply to, the Resident Project Repre​sentative, if any, and assistants, if any.

ARTICLE 10 – CHANGES IN THE WORK; CLAIMStc "ARTICLE 9 – CHANGES IN THE WORK; CLAIMS"
10.01

Authorized Changes in the Work tc "9.01  Authorized Changes in the Work " \l 2
A.
Without invalidating the Contract and without notice to any surety, Owner may, at any time or from time to time, order additions, deletions, or revisions in the Work within the general scope of the Contract by a Change Order or a Work Change Directive.  Upon receipt of any such document, Design/Builder shall promptly proceed with the Work involved which will be performed under the applicable conditions of the Contract Documents (except as otherwise specifically provided).  
1.  When OWNER requests Design/Builder to present a proposal to accomplish a change in the Work, the request will be made in the form of a Proposed Change Order (PCO) prepared by Resident Project Representative. The PCO will describe the change and request Design/Builder to propose a cost and/or Contract Time change. Design/Builder will propose cost and/or time changes, if any, sign the PCO and return it to Resident Project Representative. If requested by OWNER or Resident Project Representative, Design/Builder shall provide an itemized breakdown of the cost of the change. Resident Project Representative will make recommendations to OWNER concerning acceptance. If the PCO is approved by OWNER, the PCO will be finalized into a Change Order. Design/Builder is not authorized to proceed with a change contained in a PCO until the Change Order is properly signed and issued.

2. 
When the Design/Builder desires to propose changes to the Work, it may initiate a PCO in the same form as provided in Paragraph 10.01A.1 and submit the PCO to the Resident Project Representative for the Owner’s Engineer’s review and recommendation.
10.02

Unauthorized Changes in the Work tc "9.02  Unauthorized Changes in the Work " \l 2
A.
Design/Builder shall not be entitled to an increase in the Contract Price or an extension of the Contract Times with respect to any Work performed that is not required by the Contract Documents as amended, modified and supplemented as provided in Paragraph 3.04, except in the case of an emergency as provided in Paragraph 6.17 or in the case of uncover​ing Construction as provided in Paragraph 13.04.

10.03

Claims tc "9.03  Claims " \l 2
A.
 Notice: If Owner and Design/Builder are unable to agree on entitlement to, or on the amount or extent, if any, of an adjust​ment in the Contract Price or an adjustment of the Contract Times that should be allowed as a result of any order of Owner pursuant to Paragraph 10.01.A or other occurrence for which the Contract Documents provide that such adjustment(s) may be made, a Claim may be made therefor.  Written notice of intent to make such a Claim shall be submitted to the other party promptly and in no event more than 15 days after the start of the occurrence or event giving rise to the Claim.

2.
The OWNER as a local public agency shall respond to claims according to the procedure set forth in Section 20104 Article 1.5 (amended) "Resolution of Construction Claims" of the Public Contract Code.
3.
A Claim for an adjustment in Contract Price shall be prepared in accordance with the provisions of paragraph 12.01.B.  A Claim for an adjustment in Contract Time shall be prepared in accordance with the provisions of paragraph 12.02.  Each Claim shall be accom​panied by claimant's written statement that the adjust​ment claimed is the entire adjustment to which the claimant believes it is entitled as a result of said event.  The opposing party shall submit any response to Resident Project Representative and the claimant within 30 days after receipt of the claimant’s last submittal (unless Resident Project Representative allows additional time).

B.
Documentation:  Substantiating documentation shall be submitted by the claiming party within 30 days after delivery of the notice required by Paragraph 10.03.A.

C.
Decision:  The other party shall render a decision on the Claim no more than 30 days after the receipt of the substantiating documentation required by Paragraph 10.03.B.  This decision will be final and binding unless the claiming party gives notice of intention to exercise its rights under Article 10 within 30 days of receipt of the decision and exercises such rights within 30 days of giving the notice of intent.  No response to the Claim signifies the Claim is denied.
D.
Time Limit Extension:  The time limits of Paragraphs 10.03.B and 10.03.C may be extended by mutual agreement.

10.04

Execution of Change Orders tc "9.04  Execution of Change Orders " \l 2
A.
Owner and Design/Builder shall execute appropriate Change Orders covering:

1.
Changes in the Work which are (i) ordered by Owner pursuant to Paragraph 10.01, (ii) required because of acceptance of defective Construction under Paragraph 13.07 or Owner's correction of defective Work under Paragraph 13.08 or (iii) agreed to by the parties; and

2.
Changes in the Contract Price or Contract Times which are agreed to by the parties, including any undisputed sum or amount of time for Work actually performed in accordance with a Work Change Directive.

10.05

Notice to Sureties tc "9.05  Notice to Sureties " \l 2
A.
If notice of any change affecting the general scope of the Work or the provisions of the Contract Documents (including, but not limited to, Contract Price or Contract Times) is required by the provisions of any Bond to be given to a surety, the giving of any such notice will be Design/Builder's responsibili​ty.  The amount of each applicable Bond will be adjusted to reflect the effect of any such change.

ARTICLE 11 – COST OF THE WORK; CASH ALLOWANCES; UNIT PRICE WORKtc "ARTICLE 10 – COST OF THE WORK; CASH ALLOWANCES; UNIT PRICE WORK"
11.01
Cost of the Work tc "10.01  Cost of the Work " \l 2
A.
Costs Included: The term Cost of the Work means the sum of all costs necessarily incurred and paid by Design/Builder in the proper perfor​mance of the Work or reasonable cost that would have been incurred in the case of deleted work. When the value of Work covered by a Change Order or when a Claim for an adjustment in Contract Price is determined on the basis of Cost of the Work, the costs to be reimbursed to Design/Builder will be only those additional or incremental costs required because of the change of the Work or because of the event giving rise to the Claim.  Except as otherwise may be agreed to in writing by Owner, such costs shall be in amounts no higher than those prevailing in the locality of the Project, and shall not include any of the costs itemized in Paragraph 11.01.B, and shall include only the following items:

1.
Payroll costs for employees in the direct employ of Design/Builder in the performance of the Work under schedules of job classifications agreed upon by Owner and Design/Builder.

a.
Such employees shall include without limitation superintendents, foremen, and other personnel employed full-time at the Site.  Payroll costs for employees not employed full time on the Work shall be apportioned on the basis of their time spent on the Work.  Payroll costs shall be limited to sala​ries and wages plus the cost of fringe benefits which shall include social security contributions, unemployment, excise and payroll taxes, workers' compensation, training, health and retirement benefits, bonuses, sick leave, vacation and holiday pay applicable thereto.  The expenses of performing Work after regular working hours, on Saturday, Sunday or legal holidays, shall be included in the above to the extent authorized by Owner. For Change Order Pricing, payroll costs shall be calculated as follows:

i.
Based on certified payroll as follows:  The summation of the Gross Amount Earned, payroll taxes (employer’s contribution), and fringe benefits as reported on the certified payroll.  Benefits not reported on certified payroll are not reimbursable.
ii.
For employees not reported on certified payroll, based on payment stub as follows:   The summation of the Gross Amount Earned and payroll taxes (employer’s contribution). Benefits not reported on the payment stub payroll are not reimbursable.

b.
Such employees shall also include engineers, engineering technicians, architects, and others provid​ing Design Professional Services.  For purposes of this Paragraph 11.01.A.1, Design/Builder shall be entitled to pay​ment for such employees an amount equal to salary costs times a factor of 2.5, for all services performed or furnished by such employees engaged on the Project.

2.
Cost of all materials and equipment fur​nished and incorporated in the Work, including costs of transportation and storage thereof, and Suppliers' field services required in connection therewith.  All cash discounts shall accrue to Design/Builder unless Owner deposits funds with Design/Builder with which to make payments, in which case the cash discounts shall accrue to Owner.  All trade discounts, rebates and refunds and returns from sale of surplus materials and equipment shall accrue to Owner, and Design/Builder shall make provisions so that they may be obtained.

3.
Payments made by Design/Builder to Subcontractors (excluding payments for Design Professional Services pursuant to Paragraph 11.01.A.4) for Work performed or furnished by Subcontractors. If required by OWNER, Design/Builder shall obtain competi​tive bids from Subcontractors acceptable to OWNER and Design/Builder and shall deliver such bids to OWNER, who will then determine, with the advice of Resident Project Representative, which bids, if any, will be acceptable. If any subcontract provides that the Subcontractor is to be paid on the basis of Cost of the Work plus a fee, the Subcontractor's Cost of the Work and fee shall be determined in the same manner as Design/Builder's Cost of the Work and fee.    

4.
Payments made by Design/Builder for Design Professional Services provid​ed or furnished under a Design Subagreement.

5.
Costs of special consultants (including but not limited to engineers, architects, testing laboratories, surveyors, attorneys, and accountants) employed for services specifically related to the Work.

6.
Supplemental costs including the following items:

a.
The proportion of necessary transporta​tion, travel and subsistence expenses of Design/Builder's employees incurred in discharge of duties connected with the Work.

b.
Cost, including transportation and maintenance, of all materials, supplies, equip​ment, machinery, appliances, office and tempo​rary facilities at the Site and hand tools not owned by the workers, which are consumed in the performance of the Work, and cost, less market value, of such items used but not con​sumed which remain the property of Design/Builder.

c.
Rentals of all construction equip​ment and machinery, and the parts thereof wheth​er rented from Design/Builder or others and the equipment rental and operation rates shall be per the latest edition of the Department of Transportation, Division of Construction, Equipment Rental Rates, and the costs of transportation, loading, unload​ing, assembly, dismantling, and removal there​of. For equipment and machinery not covered by the Department of Transportation, Division of Construction, Equipment Rental Rates such costs shall be in accordance with the terms of the rental agree​ments. The rental of any such equip​ment, ma​chinery, or parts shall cease when the use thereof is no longer necessary for the Work.

d.
Sales, consumer, use, and other similar taxes related to the Work, and for which Design/Builder is liable, imposed by Laws or Regulations.

e.
Deposits lost for causes other than negligence of Design/Builder, any Subcontractor or anyone directly or indirectly em​ployed by any of them or for whose acts any of them may be liable, and royalty payments and fees for permits and licenses.

f.
Losses, damages, and related expenses caused by damage to the Work not compensated by insurance or otherwise, sustained by Design/Builder in connection with the furnishing and performance of the Work pro​vided they have resulted from causes other than the negligence of Design/Builder, any Subcontractor, or anyone directly or indirectly employed by any of them or for whose acts any of them may be liable.  Such losses shall include settlements made with the written consent and approval of Owner.  No such losses, damages, and expenses shall be included in the Cost of the Work for the purpose of determining Design/Builder's fee.

g.
The cost of utilities, fuel, and sanitary facilities at the Site.

h.
Minor expenses such as long distance telephone calls, telephone service at the Site, express and courier services, and similar petty cash items in connection with the Work.

i.
Cost of premiums for all Bonds and insurance Design/Builder is required by the Contract Documents to purchase and maintain. For Change Order pricing, bonds and insurance shall be 1 percent of the Change Order value for both additive and credit changes that are above the original Contract value and 0 percent of the Change Order value for both additive and credit changes that are below the original Contract value.
B.
Costs Excluded:  



The term Cost of the Work shall not include any of the following items:

1.
Payroll costs and other compensation of Design/Builder's officers, executives, princi​pals (of partnerships and sole proprietorships), general managers, engineers, architects, estimators, attorneys, auditors, accountants, purchasing and contracting agents, expediters, timekeepers, clerks and other personnel employed by Design/Builder whether at the Site or in Design/Builder's principal or a branch office for general administration of the Work and not specifically included in the agreed upon schedule of job classifications referred to in Paragraph 11.01.A.1, all of which are to be considered administrative costs covered by the Design/Builder's fee.

2.
Expenses of Design/Builder's princi​pal and branch offices other than Design/Builder's office at the Site.

3.
Any part of Design/Builder's capital expenses, including interest on Design/Builder's capital employed for the Work and charges against Design/Builder for delinquent payments.

4.
Costs due to the negligence of Design/Builder, any Subcontractor, or anyone directly or indirectly employed by any of them or for whose acts any of them may be liable, including but not limited to the correction of defective Work, disposal of materials or equipment wrongly sup​plied, and making good any damage to property.

5.
Other overhead or general expense costs of any kind and the costs of any item not specifically and expressly included in Paragraph 11.01.A.

C.
Design/Builder's Fee:  When all the Work is performed on the basis of cost-plus, Design/Builder's fee shall be as set forth in the Agreement.  When the value of the Work covered by a Change Order is determined on the basis of Cost of the Work, Design/Builder's fee shall be determined as set forth in Paragraph 11.01.C.

D.
Documentation:  Whenever the cost of any Work is to be determined pursuant to Paragraph 11.01.A and 11.01.B, Design/Builder will estab​lish and maintain records thereof in accordance with generally accepted accounting practices and submit in a form acceptable to Owner an itemized cost breakdown together with supporting data. 

1.
Regarding force account work, for each day that work is performed on a force account basis, the Design/Builder shall complete a Daily Force Account Record.  The Daily Force Account Record shall list all labor, materials, equipment, and other resources that were used for that day’s work on the force account work.  The Daily Force Account Record shall be signed by the Design/Builder and will be signed by the Resident Project Representative in agreement. The Daily Force Account Record shall be provided to the Resident Project Representative at the end of each day corresponding work is performed.
11.02
Cash Allowances tc "10.02  Cash Allowances " \l 2
A.
The Contract Price includes all allowances so named in the Contract Documents.  Design/Builder shall cause the Work so covered to be performed for such sums as may be acceptable to Owner.  Design/Builder agrees that:

1.
The allowances include the cost to Design/Builder (less any applicable trade dis​counts) of materials and equipment required by the allowances to be delivered at the Site, and all applicable taxes; and

2.
Except as set forth in the Contract Docu​ments, Design/Builder's costs for unloading and handling on the Site, labor, installation costs, overhead, profit, and other expenses contemplated for the allowances have been included in the Contract Price and not in the allowances, and no demand for additional payment on account of any of the foregoing will be valid.

B.
Prior to final payment, an appropriate Change Order will be issued to reflect actual amounts due Design/Builder on account of Work covered by allowances, and the Contract Price shall be corre​spondingly adjusted.

11.03
Unit Prices tc "10.03  Unit Prices " \l 2
A.
Where the Contract Documents provide that all or part of the Work is to be Unit Price Work, initially the Contract Price will be deemed to include for all of Unit Price Work an amount equal to the sum of the established unit prices for each separately identified item of Unit Price Work times the estimated quantity of each item as indicated in the Agreement.  The estimated quantities of items of Unit Price Work are not guaranteed and are solely for the purpose of comparison of Bids and determining an initial Contract Price.  Determinations of the actual quantities and classifications of Unit Price Work performed by Design/Builder will be made by Owner.

B. Each unit price will be deemed to include an amount considered by Design/Builder to be adequate to cover Design/Builder's overhead and profit for each separately identified item. Work described in the Contract Documents, or reasonably inferred as required for a functionally complete installation, but not identified in the listing of unit price items shall be considered incidental to unit price work listed and the cost of incidental work included as a part of the unit price.

C.
Design/Builder or Owner may make a Claim for an adjustment in the Contract Price in accordance with Article 10 if:

1.
the quantity of Work with respect to any item covered by a unit price differs by plus or minus 33% from the quantity of such Work indicat​ed in the contract documents, an appropriate change order shall be issued on recommendation of Resident Project Representative to adjust the unit price, provided that no adjustment will be made for an item for which the amount is less than 2% of the Contract Price.  For quantities exceeding the amount stated in the Bid Schedule, the adjusted unit price shall apply to the quantity in excess of 133% only.  For quantities less than 67% of the amount stated in the Bid Schedule, the adjusted unit price shall apply to the actual quantity of work performed, provided that the total amount paid under the adjusted unit price shall not exceed 67% of the total amount for that pay item in the Bid Schedule.  Exceptions to this are listed as specific bid items which may vary by plus or minus 100%; and 

2.
there is no corresponding adjustment with respect to any other item of Work; and

3.
Design/Builder believes that it is entitled to an increase in Contract Price as a result of having incurred additional expense or Owner believes it is entitled to a decrease in Contract Price and the parties are unable to agree as to the amount of any such increase or decrease. 

ARTICLE 12 – CHANGE OF CONTRACT PRICE; CHANGE OF CONTRACT TIMES
 
tc "ARTICLE 11 – CHANGE OF CONTRACT PRICE; CHANGE OF CONTRACT TIMES 
"
12.01
Change of Contract Price tc "11.01  Change of Contract Price " \l 2
A.
The Contract Price may only be changed by a Change Order.  Any Claim for an adjustment in the Contract Price shall be based on written notice delivered by the party making the Claim to the other party promptly in accordance with Paragraph 10.03.A.   

B.
The value of any Work covered by a Change Order or of any Claim for an adjustment in the Con​tract Price will be determined as follows:

1.
Where the Work involved is covered by unit prices contained in the Contract Documents, by application of such unit prices to the quantities of the items involved (subject to the provisions of Paragraph 11.03); or

2.
Where the Work involved is not covered by unit prices contained in the Contract Documents, by a mutually agreed lump sum (which may include an allowance for overhead and profit not necessarily in accordance with Paragraph 12.01.C.2) and shall include the cost of any secondary impacts that are foreseeable at the time of pricing the cost of extra Work; or

3.
Where the Work involved is not covered by unit prices contained in the Contract Documents and agreement to a lump sum is not reached under Paragraph 11.01.B.2, on the basis of the Cost of the Work (determined as provided in Paragraph 10.01) plus a Design/Builder's Fee for over​head and profit (determined as provided in Para​graph 11.01.C).

C.
Design/Builder's Fee:  The Design/Builder's fee for overhead and profit on Change Orders shall be determined as follows:

1.
A mutually acceptable fixed fee; or 

2.
If a fixed fee is not agreed upon, then a fee based on the following percentages of the various portions of the Cost of the Work:

a.
For costs incurred under Paragraphs 10.01.A.1.a and 10.01.A.2, the Design/Builder's fee shall be fifteen percent (15%);

b.
For costs incurred under Paragraph 10.01.A.3 10.01.A.4, 10.01.A.5 and 10.01.A.6, the Design/Builder's fee shall be five percent (5%);

c.
Where one or more tiers of subcon​tracts are on the basis of Cost of the Work plus a fee and no fixed fee is agreed upon, the intent of Paragraphs 12.01.C.1 and 12.01.C.2.a is that the Subcontractor who actually performs or furnishes Work, at whatever tier, will be paid a fee of 15 percent of the costs incurred by such Subcontractor under Para​graphs 11.01.A.1 and 11.01.A.2 and that any higher tier Subcontractor and Design/Builder will each be paid a fee of five percent of the amount paid to the next lower tier Subcontractor;

d.
The amount of credit to be allowed by Design/Builder to Owner for any change which results in a net decrease in cost will be the amount of the actual net decrease in cost plus a deduction in Design/Builder's fee by an amount equal to five percent of such net decrease; and

e.
When both additions and credits are involved in any one change, the adjustment in Design/Builder's fee shall be computed on the basis of the net change in accordance with Paragraphs 12.01.C.2.a through 12.01.C.2.d, inclusive.

12.02
Change of Contract Times tc "11.02  Change of Contract Times " \l 2
A.
The Contract Times (or Milestones) may only be changed by a Change Order.  Any Claim for an adjustment of the Contract Times (or Milestones) shall be based on written notice pursuant to Paragraph 10.03.A.
B. No extension of the Contract Time will be allowed for additional Work or for claimed delay unless the additional Work contemplated or claimed delay is shown to be on the critical path of the Project's schedule of construction or Design/Builder can show by Critical Path Method analysis how the additional Work or claimed delay adversely affects the critical path.

12.03 
Delays Beyond Design/Builder’s Control

A.
Where Design/Builder is prevented from completing any part of the Work within the Contract Times (or Milestones) due to delay beyond the control of Design/Builder, the Contract Times (or Milestones) will be extended in an amount equal to the time lost due to such delay if a Claim is made therefor as provided in paragraph 12.02.A.  Delays beyond the control of Design/Builder shall include, but not be limited to, acts or neglect by OWNER, acts or neglect of utility owners or other Design/Builders perform​ing other work as contemplat​ed by Article 7, fires, floods, epidemics, abnormal weather conditions, or acts of God.  

12.04 
Delays Within Design/Builder’s Control

A.
The Contract Times (or Milestones) will not be extended due to delays within the control of Design/Builder.  Delays attributable to and within the control of a Subcontractor or Supplier shall be deemed to be delays within the control of Design/Builder.

12.05

Delays Beyond OWNER’s and Design/Builder’s Control

A.
Where Design/Builder is prevented from complet​ing any part of the Work within the Contract Times (or Milestones) due to delay beyond the control of both OWNER and Design/Builder, an extension of the Contract Times (or Milestones) in an amount equal to the time lost due to such delay shall be Design/Builder’s sole and exclusive remedy for such delay.

12.06 
Delay Damages

A.
In no event shall OWNER or Owner’s Engineer or Resident Project Representative be liable to Design/Builder, any Subcontractor, any Suppli​er, or any other person or organization, or to any surety for or employee or agent of any of them, for damages arising out of or resulting from:

1.
delays caused by or within the control of Design/Builder; or 

2.
delays beyond the control of both OWNER and Design/Builder including but not limited to fires, floods, epidemics, abnormal weather conditions, acts of God, or acts or neglect by utility owners or other Design/Builders per​forming other work as contemplated by Article 7.

B.
Nothing in this paragraph 12.06 bars a change in Contract Price pursuant to this Article 12 to compensate Design/Builder due to delay, interference, or disruption directly attributable to actions or inactions of OWNER or anyone for whom  OWNER is responsible.

ARTICLE 13 – TESTS AND INSPECTIONS; CORRECTION, REMOVAL OR ACCEPTANCE OF DEFECTIVE CONSTRUCTIONtc "ARTICLE 12 – TESTS AND INSPECTIONS; CORRECTION, REMOVAL OR ACCEPTANCE OF DEFECTIVE CONSTRUCTION"
13.01
Notice of Defects tc "12.01  Notice of Defects " \l 2
A.
Owner shall give Design/Builder prompt written notice of all defective Construction of which Owner has actual knowledge.  All defective Construction may be rejected, corrected or accepted as provided in this Article 13.

13.02
Access to Construction tc "12.02  Access to Construction " \l 2
A.
Owner, Owner's Consultants, other representatives and personnel of Owner, independent testing laboratories and governmental agencies with jurisdictional interests will have access to the Site and the Construction at reasonable times for their observation, inspecting, and testing.  Design/Builder shall provide them proper and safe conditions for such access and advise them of Design/Builder's Site safety procedures and programs so that they may comply therewith as applicable.

13.03
Tests and Inspections 

A.
If the Contract Documents or Laws or Regulations of any public body having jurisdiction require any part of the Construction specifically to be inspected, tested or approved, Design/Builder shall assume full responsibility for arranging and obtaining such inspections, tests or approvals, pay all costs in connection therewith, and furnish Owner the required certificates of inspection or approval.  Design/Builder shall also be responsible for arranging and obtaining and shall pay all costs in connection with any inspections, tests, or approvals required for Owner's acceptance of materials or equipment to be incorporated in the Work or of materials, mix designs, or equipment submitted for approval prior to Design/Builder's purchase thereof for incorporation in the Work.

B.
Design/Builder shall give Owner reasonable notice of the planned schedule for all required inspections, tests, or approvals.

C.
If any Construction (or the construction work of others) that is required to be inspected, tested, or approved is covered by Design/Builder without written concurrence of Owner, then Design/Builder shall, if requested by Owner, uncover such Construction for observation.

D. Uncovering Construction shall be at Design/Builder's expense unless Design/Builder has given Owner 72-hour written notice of Design/Builder's intention to cover the same and Owner has not acted with reasonable promptness in response to such notice.

E. Owner’s testing and inspection activities shall not relieve Design/Builder from performing project required testing and inspection.  Owner and Resident Project Representative and their consultants do not warrant the accuracy of test results performed by Owner’s consultants. Design/Builder and Design/Builder’s subcontractors use and rely on Owner provided test results at their own risk.

F. Owner testing and inspection activities are as stated in the Supplementary Conditions or Project Manual.  

13.04
Owner May Stop Construction tc "12.05  Owner May Stop Construction " \l 2
A.
If Construction is defective, or Design/Builder fails to supply sufficient skilled workers or suitable materials or equipment, or fails to furnish or perform Construction in such a way that the completed Construction will conform to the Contract Documents, Owner may order Design/Builder to stop Construction or any portion thereof, until the cause for such order has been eliminated; however, this right of Owner to stop Construction will not give rise to any duty on the part of Owner to exercise this right for the benefit of Design/Builder or any other party.

13.05
Correction or Removal of Defective Construction tc "12.06  Correction or Removal of Defective Construction " \l 2
A.
Owner will have authority to disapprove or reject defective Construction and will have authority to require special inspection or testing of the Construction whether or not the Construction is fabricated, installed or completed.  If required by Owner, Design/Builder shall promptly, as directed, either correct all defective Construction, whether or not fabricated, installed or completed, or, if the Construction has been rejected by Owner, remove it from the Site and replace it with non-defective Construction.  Design/Builder shall bear all direct, indirect, and consequential costs of such correction or removal (including but not limited to fees and charges of engineers, architects, attorneys and other professionals and all court, arbitration, or other dispute resolution costs) arising out of or relating to such correction or removal.  

13.06
Correction Period tc "12.07  Correction Period " \l 2
A.
If within two years after the date of Final Completion of the entire Work or such longer period of time as may be prescribed by Laws or Regulations or by the terms of any applicable special guarantee required by the Contract Documents or by any specific provision of the Contract Documents, any Construction is found to be defective, Design/Builder shall promptly, without cost to Owner and in accordance with Owner's written instructions, (i) correct such defective Construction, or, if it has been rejected by Owner, remove it from the Site and replace it with Construction that is not defective, and (ii) satisfactorily correct or remove and replace any damage to other Construction or the work of others resulting therefrom.  If Design/Builder does not promptly comply with the terms of such instructions, or in an emergency where delay would cause serious risk of loss or damage, Owner may have the defective Construction corrected or the rejected Construction removed and replaced, and all costs, losses, and damages caused by or resulting from such removal and replacement (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals, all court or arbitration or other dispute resolution costs, and all costs of repair or replacement of work of others) will be paid by Design/Builder. 

B.
Where defective Construction (and damage to other Construction resulting therefrom) has been corrected, removed or replaced under this Paragraph 13.06, the correction period hereunder with respect to such Construction will be two years after such correction or removal and replacement has been satisfactorily completed.

13.07
Acceptance of Defective Construction tc "12.08  Acceptance of Defective Construction " \l 2
A.
If, instead of requiring correction or removal and replacement of defective Construction, Owner prefers to accept it, Owner may do so.  Design/Builder shall pay all costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court or arbitration or other dispute resolution costs) attributable to Owner's evaluation of and determination to accept such defective Construction.  If any such acceptance occurs prior to final payment, a Change Order will be issued incorporating the necessary revisions in the Contract Documents, and Owner shall be entitled to an appropriate decrease in the Contract Price reflecting the diminished value of the Construction so accepted.  If the parties are unable to agree as to the amount thereof, Owner may make a Claim therefor as provided in Article 9.  If the acceptance occurs after final payment, an appropriate amount will be paid by Design/Builder to Owner.

13.08
Owner May Correct Defective Construction tc "12.09  Owner May Correct Defective Construction " \l 2
A.
If Design/Builder fails within a reasonable time after written notice from Owner to correct defective Construction or to remove and replace rejected Construction as required by Owner in accordance with Paragraphs 13.05.A or 13.06.A, or if Design/Builder fails to perform the Construction in accordance with the Contract Documents, or if Design/Builder fails to comply with any other provision of the Contract Documents, Owner may, after seven days' written notice to Design/Builder, correct and remedy any such deficiency.

B.
In exercising the rights and remedies under this Paragraph 13.08 Owner shall proceed expeditiously.  In connection with such corrective and remedial action, Owner may exclude Design/Builder from all or part of the Site, take possession of all or part of the Construction, and suspend Design/Builder's services related thereto, take possession of Design/Builder's tools, appliances, construction equipment and machinery at the Site, and incorporate in the Construction all materials and equipment stored at the Site or for which Owner has paid Design/Builder but which are stored elsewhere.  Design/Builder shall allow Owner, Owner's Consultant, Owner's representatives, agents, employees, and other Design/Builders access to the Site to enable Owner to exercise the rights and remedies under this paragraph.

C.
All costs, losses, and damages (included but not limited to fees and charges of engineers, architects, attorneys and other professionals, all court or arbitration or other dispute resolution costs and all costs of repair or replacement of work of others) incurred or sustained by Owner in exercising such rights and remedies under this Paragraph 13.08 will be charged against Design/Builder and a Change Order will be issued incorporating the  necessary revisions in the Contract Documents, and Owner shall be entitled to an appropriate decrease in the Contract Price.  If the parties are unable to agree as to the amount thereof, Owner may make a Claim therefor as provided in Article 10.   

D.
Design/Builder shall not be allowed an extension of the Contract Times (or Milestones) because of any delay in the performance of the Work attributable to the exercise by Owner of Owner's rights and remedies under this Paragraph 13.08.

ARTICLE 14 – PAYMENTS TO DESIGN/BUILDER AND COMPLETIONtc "ARTICLE 13 – PAYMENTS TO DESIGN/BUILDER AND COMPLETION"
14.01

Schedules

A.
Prior to submitting the first application for a progress payment, Design/Builder shall have obtained approval of the progress schedule, the schedule of shop drawing submission and the schedule of values of the Work.  These schedules shall be satisfactory in form and substance to Resident Project Representative.  The unit prices and lump sum component of the bid submittal will subdivide the Work into component parts in sufficient detail to serve as the basis for progress payments during construc​tion.  Upon acceptance of the schedule of values by Resident Project Representative, it shall be incorporated into a form of application for partial payment acceptable to Resident Project Representative.

14.02

Tax Identification Number

A.
Prior to submitting the first application for progress payment, Design/Builder shall complete and submit IRS W-9 Form. 

14.03

Application For Progress Payments

A.
Application - At least seven (7) days before each progress payment falls due (but not more than once a month), Design/Builder shall submit to Resident Project Representative for review a Progress Payment Application signed by Design/Builder covering the Work completed as of the date of the applica​tion and accompanied by such supporting documentation as is required by the contract documents and also as Resident Project Representative may reasonably require.  Each subsequent Application shall include an affidavit of Design/Builder stating that all previous progress payments received on account of the Work have been applied to discharge in full all of Design/Builder's obligations and is free of and clear of liens, claims, security interests, or encumbrances of any kind.  

1.
To receive partial payment for materials and equipment delivered to the Site, but not incorporated in the Work, it shall be necessary for the Design/Builder to submit to the Resident Project Representative a list of such materials, at least seven (7) days prior to submitting the monthly estimate of amount earned for work completed. At the Resident Project Representative's sole discretion, the Resident Project Representative will approve items for which partial payment is to be made subject to the following:

a. Only equipment or materials that have received favorable review of shop drawings will qualify.

b. Eligible equipment or materials must be delivered and properly stored, protected, and maintained in a manner favorably reviewed by the Resident Project Representative, at the job site or at a bonded warehouse.

c. The Design/Builder's actual net cost for the materials must be supported by invoices of suppliers, or other documentation requested by the Resident Project Representative.

d.
Materials or equipment delivered to the Site less than thirty (30) days prior to their scheduled incorporation in the Work shall not qualify.

e.
Final payment shall be made only for materials actually incorporated in the Work. Upon acceptance of the Work, all materials remaining for which advance payments had been made shall revert to the Design/Builder, unless otherwise agreed, and partial payments made for these items shall be deducted from the final payment for the Work.

f.
Partial payments for materials and equipment on hand shall not be deemed to be final payment for the material nor relieve the Design/Builder of its obligations under the Contract.

g.
Partial payments for materials and equipment on hand shall be subject to retention in accordance with the Contract Documents

B.
Retention - The OWNER shall retain ten percent (5%) of the value of the approved progress payment as a partial security for fulfillment of the contract by the Design/Builder.  When work is fifty percent (50%) complete and if the Resident Project Representative finds that satisfactory progress is being made, the OWNER may elect to refund that portion of retainage held by the OWNER that is in excess of five percent (2.5%) of the total work complet​ed to date and thereafter continue to retain five percent (2.5%) of the value of all approved progress payment requests subsequently submitted.  The OWNER may reinstate the ten percent (5%) retainage if it is determined that the Design/Builder is not making satisfactory progress or where there is other specific cause.

1.
Pursuant to Public Contract Code Section 22300, for moneys earned by the Design/Builder and withheld by the OWNER to ensure the performance of the Contract, the Design/Builder, may, at their option, choose to substitute securities meeting the requirements of said Section 22300. In the event the Design/Builder wishes to choose this option, the Design/Builder shall enter into an escrow agreement with the OWNER and the escrow agent, a qualified bank to be acceptable to the OWNER, in the form of the agreement included in the project specifications. The costs of such escrow shall be paid by the Design/Builder. The securities to be deposited in said escrow account shall be equivalent, in fair market value, to the amount to be withheld as performance retention. The securities shall be held in accordance with the provisions of Public Contract Code Section 22300, and the implementing agreement.

2.
DESIGN/BUILDER shall have the obligation of ensuring that such securities deposited are sufficient so as to maintain, in total fair market value, an amount equal to the cash amount of the sums to be withheld under the Contract. If, upon written notice from the OWNER, or from the appropriate escrow agent, indicating that the fair market value of the securities has dropped below the dollar amount of moneys to be withheld by the Resident Project Representative to ensure performance, Design/Builder shall, within five days of the date of such notice, post additional securities as necessary to ensure that the total fair market value of all such securities held by the OWNER, or in escrow, is equivalent to the amount of money to be withheld by the OWNER under the Contract.

3.
Any Design/Builder wishing to exercise this option shall give notice in writing to OWNER, and shall thereafter execute an escrow agreement in the form of the form included with these Contract Documents

14.04

DESIGN/BUILDER's Warranty Of Title

A.
DESIGN/BUILDER warrants and guarantees that title to all Work, materials and equipment covered by any application for payment, whether incorporated in the Project or not, will pass to OWNER at the time of payment free and clear of all claims, security interests and encumbran​ces (hereafter in these General Conditions referred to as "claims") except for those items listed in the specifications which shall become property of the Design/Builder.

14.05

Review Of Applications For Progress Payment

A.
Resident Project Representative will, within ten (10) days after receipt of each application for partial payment either indicate in writing a recommendati​on of payment and present the application to OWNER, or return the application to Design/Builder indicating in writing Resident Project Representative's reasons for refusing to recommend payment.  In latter case, Design/Builder may make the necessary corrections and resubmit the application.  The  OWNER shall pay Design/Builder within 30 days of  OWNER's approval of the application for partial payment in accordance with the OWNER’s accounts payable procedures.

B.
Resident Project Representative's recommendation of any payment requested in an applica​tion for partial payment will constitute a representation by Resident Project Representative to OWNER, based on Resident Project Representative's on‑site observations of the Work in progress as an experienced and qualified profes​sional and on Resident Project Representative's review of the application for partial payment and the accompanying data and schedules that the Work has progressed to the point indicated; that, to the best of Resident Project Representative's knowledge, information, and belief, the quality of the Work is in accordance with the contract documents (subject to an evaluation of the Work as a func​tioning Project upon substantial completion, to the results of any subsequent tests called for in the contract documents and any qualifications stated in the recommendation).  However, by recommending any such payment Resident Project Representative will not thereby be deemed to have represented that exhaustive or continu​ous on‑site inspections have been made to check the quality or the quantity of the Work, or that the means, methods, techniques, sequences, and procedures of construc​tion have been reviewed or that any examination has been made to ascertain how or for what purpose Design/Builder has used the monies paid or to be paid to Design/Builder on account of the Agreement price, or that title to any Work, materials or equipment has passed OWNER free and clear of any claims.

C.
Resident Project Representative may refuse to recommend and the OWNER may refuse to pay the whole or any part of any payment if, in their opinion, it would be incorrect to make such payment.  They may also refuse to recommend to make any such payment, or because of subsequently discovered evidence or the results of subsequent inspections or tests, nullify any such payment previously recommended, to such extent as may be necessary in Resident Project Representative's or OWNER's opinion to protect OWNER from loss because:

1.
The Work is defective, or completed Work has been damaged requiring correction or replacement.

2.
Written claims have been made against OWNER or claims have been filed in connection with the Work.

3.
The Agreement price has been reduced because of modifica​tions.

4.
OWNER has been required to correct defective work or complete the work in accordance with paragraph 13.08.A.

5.
Of Design/Builder's unsatisfacto​ry prosecution of the Work in accordance with the contract documents.

6.
Of Design/Builder's failure to make payment to Subcontractors for labor, materials or equipment.

14.06

Substantial Completion

A.
When Design/Builder considers the entire Work ready for its intended use Design/Builder shall, in writing to OWNER and Resident Project Representative, certify that the entire Work is substantially complete and request that Resident Project Representative issue a Certificate of Substantial Completion.  Within a reasonable time thereafter, OWNER, Design/Builder, and Resident Project Representative shall make an inspection of the Work to determine the status of comple​tion.  If Resident Project Representative does not consider the Work substanti​ally complete, Resident Project Representative will notify Design/Builder in writing giving his reasons therefor.  If Resident Project Representative considers the Work substantially complete, Resident Project Representative will prepare and deliver to OWNER a tentative Certifi​cate of Substantial Completion.  There shall be attached to the certificate a punch list of items to be completed or corrected before project completion and final payment.


B. Owner shall have the right to exclude Contractor from the Site after the date of Substan​tial Completion subject to allowing Contractor reasonable access to complete or correct items on the tentative list.

14.07

Partial Utilization

A.
Use by OWNER of completed portions of the Work may be accomplished prior to substantial completion of all the Work subject to the following:

1.
OWNER at any time may request Design/Builder in writing to permit OWNER to use any part of the Work which OWNER believes ready and necessary for operation.   Resident Project Representative shall issue a Certifi​cate of Partial Utilization prior to operation of said portion of Work.

2.
No occupancy of part of the Work or taking over of operations of a facility will be accomplished prior to compliance with the requirements of paragraph 5.07.A in respect to property insurance.

14.08

Final Inspection

A.
Upon written notice from Design/Builder that the Work is complete and that all items on the punch list have been completed, Resident Project Representative will make a final inspection with OWNER and Design/Builder and will notify Design/Builder in writing of all particulars in which this inspection reveals that the Work is incomplete or defective. Design/Builder shall immedia​tely take such measures as are necessary to remedy such deficiencies.

14.09

Final Payment
A. Application for Final Payment

1. After Design/Builder has, in the opinion of Resident Project Representative, satisfactorily completed all corrections identified during the final inspection and has delivered, in accordance with the Contract Docu​ments, all main​tenance and operating instructions, schedules, guaran​tees, bonds, certificates or other evidence of insur​ance certificates of inspec​tion, marked‑up record docu​ments (as provid​ed in Paragraph 6.12), and other documents, Design/Builder may make application for final payment follow​ing the procedure for progress pay​ments.

2. The final Application for Payment shall be accom​panied (except as previously delivered) by: 

a. all documenta​tion called for in the Contract Docu​ments, including but not limited to the evidence of insurance required by Paragraph 5.05.B.7;

b. con​sent of the surety, if any, to final payment; 

c. a list of all Claims against Owner that Design/Builder believes are unsettled; and 

d. complete and legally effective releases or waivers (satisfactory to Owner) of all Lien rights arising out of or Liens filed in connection with the Work.

3. In lieu of the releases or waivers of Liens specified in Paragraph 14.07.A.2 and as approved by Owner, Design/Builder may furnish receipts or releases in full and an affidavit of Design/Builder that: (i) the releases and receipts include all labor, services, material, and equipment for which a Lien could be filed; and (ii) all payrolls, material and equipment bills, and other indebtedness connected with the Work for which Owner or Owner's property might in any way be responsible have been paid or otherwise satis​fied. If any Subcontractor or Supplier fails to furnish such a release or receipt in full, Design/Builder may furnish a bond or other collateral satisfactory to Owner to indemnify Owner against any Lien.

B. Resident Project Representative’s Review of Application and Acceptance

1. If, on the basis of Resident Project Representative’s obser​va​tion of the Work during construction and final inspec​tion, and Resident Project Representative’s review of the final Applica​tion for Payment and accompanying docu​men​tation as re​quired by the Contract Documents, Resident Project Representative is satisfied that the Work has been complet​ed and Design/Builder’s other obligations under the Con​tract Documents have been fulfilled, Resident Project Representative will, within ten days after receipt of the final Appli​ca​tion for Payment, indicate in writing Resident Project Representative’s recommen​dation of payment and present the Applica​tion for Payment to Owner for pay​ment. At the same time Resident Project Representative will also give written notice to Owner and Design/Builder that the Work is acceptable subject to the provi​sions of Paragraph 14.09. Other​wise, Resident Project Representative will return the Application for Payment to Design/Builder, indicat​ing in writing the reasons for refusing to recommend final payment, in which case Design/Builder shall make the necessary corrections and resubmit the Application for Payment. 

C. Payment Becomes Due

1. Forty-five days after the presentation to Owner of the Application for Payment and accompanying docu​mentation, the amount recommended by Resident Project Representative, less any sum Owner is entitled to set off against Resident Project Representative’s recommendation, including but not limited to liquidated damages, will become due and , will be paid by Owner to Design/Builder.

14.10

DESIGN/BUILDER's Continuing Obligation

A.
DESIGN/BUILDER's obligation to perform and complete the Work in accordance with the contract documents shall be absolute.  Neither recommendation of any progress or final payment by Resident Project Representative, nor the issuance of a Certificate of Substantial Completion, nor any payment by OWNER to Design/Builder under the contract documents, nor any use or occupancy of the Work or any part thereof by OWNER, nor any act of acceptance by OWNER nor any failure to do so, nor the issuance of a notice of acceptability by Resident Project Representative pursuant to paragraph 14.09.A, nor any correction of defective Work by OWNER shall constitute an acceptance of Work not in accordance with the contract documents or a release of Design/Builder's obligation to perform the Work in accordance with the contract documents.

B. The OWNER will conduct a post-construction inspection of the project before expiration of the Maintenance and Guarantee Bond.  The Design/Builder will be notified in writing of deficiencies and shall reply in writing within two (2) weeks of receipt of such notification with a schedule to promptly correct these deficiencies or, if failing to do so, the OWNER may notify the bonding company of forfeiture of the bond.

14.11

Waiver Of Claims

A.
The making and acceptance of final payment shall constitute:

1.
A waiver of all claims by OWNER against Design/Builder, except claims arising from unsettled claims, from defective Work appearing after final inspection pursuant to paragraph 13.08.A or from failure to comply with the contract documents or the terms of any special guarantee specified therein; however, it shall not constitute a waiver by OWNER of any rights in respect of Design/Builder's continuing obliga​tions under the contract documents.

2.
A waiver of all claims by Design/Builder against OWNER other than those previously made in writing and still unsettled.

ARTICLE 15 – SUSPENSION OF WORK AND TERMINATIONtc "ARTICLE 14 – SUSPENSION OF WORK AND TERMINATION"
15.01
Owner May Suspend Work 
tc "14.01  Owner May Suspend Work " \l 2
A.
At any time and without cause, OWNER may suspend the Work or any portion thereof for a period of not more than 90 consecutive days by notice in writing to Design/Builder and Resident Project Representative which will fix the date on which Work will be resumed. Design/Builder shall resume the Work on the date so fixed. Design/Builder shall be allowed an adjust​ment in the Contract Price or an extension of the Contract Times, or both, directly attributable to any such suspension if Design/Builder makes a Claim therefore as provided in Article 10.

15.02

OWNER May Terminate for Cause

A.
The occurrence of any one or more of the following events will justify termination for cause:

1.
Design/Builder’s persis​tent failure to per​form the Work in accordance with the Con​tract Documents (including, but not limited to, failure to supply suffi​cient skilled workers or suitable materi​als or equip​ment or failure to adhere to the prog​ress schedule established under paragraph 2.07 as adjusted from time to time pursuant to paragraph 6.05);

2.
Design/Builder’s disregard of Laws or Regula​tions of any public body having jurisdic​tion;

3. 
Design/Builder’s disregard of the author​i​ty of Resident Project Representative; or

4. 
Design/Builder’s violation in any substantial way of any provisions of the Contract Docu​ments.

B.
If one or more of the events identified in Paragraph 15.02A. occur, OWNER will provide written notice to Design/Builder and Surety to arrange a conference with Design/Builder and Surety to address Design/Builder's failure to perform the Work. Conference shall be held not later than 15 days, after receipt of notice.

1. 
If the OWNER, the Design/Builder, and the Surety do not agree to allow the Design/Builder to proceed to perform the Construction Contract, the OWNER may, to the extent permitted by Laws and Regulations, declare a Design/Builder Default and formally terminate the Design/Builder's right to complete the Contract. Design/Builder Default shall not be declared earlier than 20 days after the Design/Builder and Surety have received notice of conference to address DESIGN/BUILDER's failure to perform the Work.

2. 
If Design/Builder's services are terminated, Surety shall be obligated to take over and perform the Work. If Surety does not commence performance thereof within 15 consecutive calendar days after date of an additional written notice demanding Surety's performance of its obligations, then  OWNER, without process or action at law, may take over any portion of the Work and complete it as described below.

a. 
If OWNER completes the Work, OWNER may exclude Design/Builder and Surety from the site and take possession of the Work and of all tools, appliances, construction equipment and machinery at the site and use the same to the full extent they could be used by Design/Builder and Surety (without liability to Design/Builder and Surety for trespass or conversion), incorporate in the Work all materials and equipment stored at the site or for which OWNER has paid Design/Builder or Surety but which are stored elsewhere, and finish the Work as OWNER may deem expedient.

3. 
Whether OWNER or Surety completes the Work, Design/Builder shall not be entitled to receive any further payment until the Work is finished. If the unpaid balance of the Contract Price exceeds all claims, costs, losses and damages sustained by OWNER arising out of or resulting from completing the Work, such excess will be paid to Design/Builder. If such claims, costs, losses and damages exceed such unpaid balance, Design/Builder shall pay the difference to OWNER. Such claims, costs, losses and damages incurred by OWNER will be reviewed by Resident Project Representative as to their reasonableness and when so approved by Resident Project Representative incorporated in a Change Order, provided that when exercising any rights or remedies under this Paragraph, OWNER shall not be required to obtain the lowest price for the Work performed.

4. 
Neither OWNER, Resident Project Representative, Owner’s Engineer, nor any of their respective consultants, agents, officers, directors or employees shall be in any way liable or accountable to Design/Builder or Surety for the method by which the completion of the said Work, or any portion thereof, may be accomplished or for the price paid therefore.

5. 
OWNER, notwithstanding the method used in completing the Contract, shall not forfeit the right to recover damages from Design/Builder or Surety for Design/Builder's failure to timely complete the entire Contract. Design/Builder shall not be entitled to any claim for damages on account of the method used by OWNER in completing the Contract.

6.
Maintenance of the Work shall continue to be Design/Builder's and Surety's responsibilities as provided for in the bond requirements of the Contract Documents or any special guarantees provided for under the Contract Documents or any other obligations otherwise prescribed by law. If OWNER proceeds as provided in Paragraph 15.02.B, Design/Builder shall not be entitled to receive any further payment until the Work is completed. If the unpaid balance of the Contract Price exceeds all claims, costs, losses, and damages (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs) sustained by OWNER arising out of or relating to completing the Work, such excess will be paid to Design/Builder. If such claims, costs, losses, and damages exceed such unpaid balance, Design/Builder shall pay the difference to OWNER. Such claims, costs, losses, and damages incurred by OWNER will be reviewed by Resident Project Representatives to their reasonableness and, when so approved by Resident Project Representative, incorporated in a Change Order.

7.
When exercising any rights or remedies under this Paragraph OWNER shall not be required to obtain the lowest price for the Work performed.  Any retention or payment of moneys due Design/Builder by OWNER will not release Design/Builder from liability.
15.03

OWNER May Terminate For Convenience

A.
Upon seven days written notice to Design/Builder and Resident Project Representative, OWNER may, without cause and without prejudice to any other right or remedy of OWNER, elect to terminate the Contract.  In such case, Design/Builder shall be paid (without duplica​tion of any items):

1.
for completed and acceptable Work execut​ed in accordance with the Contract Docu​ments prior to the effective date of termination, including fair and reasonable sums for overhead and profit on such Work;

2.
for expenses sustained prior to the effective date of  termination in performing services and fur​nish​ing labor, materials, or equip​ment as re​quired by the Contract Documents in connection with uncom​pleted Work, plus fair and reasonable sums for overhead and profit on such expenses;

3.
for all claims, costs, losses, and damag​es (including but not limited to all fees and charges of engineers, architects, attorneys, and other professionals and all court or arbitration or other dispute resolution costs)  in​curred in settlement of terminated contracts with Subcontractors, Suppliers, and others; and

4.
for reasonable expenses directly attributable to termination.

B.
DESIGN/BUILDER shall not be paid on account of loss of anticipated profits or revenue or other eco​nomic loss arising out of or resulting from such termina​tion.

15.04

DESIGN/BUILDER May Stop Work or Terminate

A.
If, through no act or fault of Design/Builder, the Work is suspended for more than 90 consecutive days by OWNER or under an order of court or other public authority, or Resident Project Representative fails to act on any Application for Payment within 30 days after it is submitted, or OWNER fails for 30 days to pay Design/Builder any sum finally deter​mined to be due, then Design/Builder may, upon seven days written notice to OWNER and Resident Project Representative, and provided OWNER or Resident Project Representative do not remedy such suspen​sion or failure within that time, terminate the Contract and recover from OWNER payment on the same terms as provided in paragraph 15.03.  In lieu of terminat​ing the Contract and without prejudice to any other right or remedy, if Resident Project Representative has failed to act on an Application for Payment within 30 days after it is submitted, or OWNER has failed for 30 days to pay Design/Builder any sum finally determined to be due, Design/Builder may, seven days after written notice to OWNER and Resident Project Representative, stop the Work until payment is made of all such amounts due Design/Builder, including interest thereon.  The provi​sions of this paragraph 15.04 are not intended to preclude Design/Builder from making a Claim under paragraph 10.05 for an adjustment in Contract Price or Contract Times or other​wise for expenses or damage directly attributable to Design/Builder’s stopping the Work as permitted by this paragraph.

ARTICLE 16 – DISPUTE RESOLUTIONtc "ARTICLE 15 – DISPUTE RESOLUTION"
16.01
Methods and Procedures tc "16.01  Giving Notice " \l 2
A.
If the Design/Builder disputes the written response, as provided in paragraph 10.05.A., the Design/Builder shall so notify the  OWNER in writing within fifteen (15) days of receipt of the OWNER's response or within fifteen (15) days of the  OWNER's failure to respond within the time prescribed in Article 10.  The Design/Builder's notification shall include a request for an informal conference to meet and settle the issues in dispute.

B.
Should the informal conference fail to resolve the disputed claims, the claims shall be resolved by the procedure as described in Section 20104 of Article 1.5 (amended) - "Resolution of Construction Claims," or Sections 10240 – 10240.13, inclusive, of Article 7.1, Chapter 1, Division 2, of the Public Contract Code and applicable regulations.

ARTICLE 17 – MISCELLANEOUStc "ARTICLE 16 – MISCELLANEOUS"
17.01

Giving Notice

A.
Whenever any provision of the Con​tract Documents requires the giving of written notice, it will be deemed to have been validly given if deliv​ered in person to the individual or to a member of the firm or to an officer of the corporation for whom it is intend​ed, or if delivered at or sent by registered or certified mail, postage prepaid, to the last business address known to the giver of the notice.

17.02

Computation of Times

A.
When any period of time is referred to in the Contract Documents by days, it will be comput​ed to exclude the first and include the last day of such period.  If the last day of any such period falls on a Saturday or Sunday or on a day made a legal holiday by the law of the applicable jurisdiction, such day will be omitted from the computation.

17.03

Cumulative Remedies

A.
The duties and obligations imposed by these General Conditions and the rights and remedies avail​able hereunder to the parties hereto are in addition to, and are not to be construed in any way as a limita​tion of, any rights and remedies avail​able to any or all of them which are otherwise im​posed or available by Laws or Regula​tions, by special warranty or guarantee, or by other provisions of the Contract Documents, and the provisions of this paragraph will be as effective as if repeated specifical​ly in the Contract Documents in connection with each particular duty, obligation, right, and remedy to which they ap​ply.

B.
No action or failure to act by the OWNER or Owner’s Engineer or the Resident Project Representative shall constitute a waiver of any right or duty afforded any of them under the Contract, nor shall any such action or failure to act constitute an approval of or acquiescence in any breach thereunder, except as may be specifically agreed in writing.

17.04
Survival of Obligations

A.
All representations, indemnifications, war​ran​ties, and guarantees made in, required by, or given in accor​dance with the Contract Documents, as well as all continu​ing obligations indicated in the Contract Docu​ments, will survive final payment, completion, and acceptance of the Work or termina​tion or comple​tion of the Agreement.

17.05

Controlling Law

A.
This Contract is to be governed by the law of the State of California.

17.06
Penalty for Collusion

A.
If, at any time, it is found that the person, firm, or corporation to whom the Contract has been awarded has, in presenting any bid or bids, colluded with any other party or parties, then the Contract shall be null and void, and the Design/Builder and its sureties shall be liable for loss or damage which the OWNER may suffer thereby, and the OWNER may advertise for new bids for said Work.

17.07
Waste Disposal

A.
Unless otherwise shown on the plans or specified herein, all existing improvements and surplus materials not to be salvaged, stockpiled, or disposed of as provided in the Specifications shall become the property of the Design/Builder and disposed of away from the work site at his expense.

B.
Full compensation for all costs involved in disposing of materials, including all hauling costs, shall be considered as included in the prices paid for the various Contract items of work and no additional compensation will be allowed.

ARTICLE 18 – LIQUIDATED DAMAGES
A.
It is understood and agreed by the parties that damages for Design/Builder delay are expensive to litigate and difficult to ascertain.  Therefore, it is agreed that as and for a separately bargained for liquidated damage, and not as a penalty, the OWNER shall deduct or recover the amount set forth in the Construction Agreement unless extensions of time granted by OWNER specifically provide for the waiving of liquidated damages.

ARTICLE 19 - ALIEN LABOR

A.
The Design/Builder shall forfeit, as penalty to the OWNER, one-hundred dollars ($100.00) for each alien knowingly employed in the execution of the contract, by him or by a Subcontractor under him, upon any of the work for each calendar day, or portion thereof during which such alien is permitted or required to labor in violation of the provisions of the Labor Code, particularly Section 1850 to 1854, thereof.

- END OF SECTION -
February 27, 2013




General Conditions



             City of Manteca







      00700-1                                                   Atherton Tank and PS Project

