## NonResidential
Name of Project | Project # | Description | Location | Applicant | Notes | Status | PC Date | CC Date | Complete Ltr. | Planning PM | Eng. PM | PRIORITY
Yosemite Square | P25- 0019 | TPM Extension Request | [7 empty] | Sol
Tractor Supply/Dutch Bros | P25-0018 | LLA | [7 empty] | Zuzi
Aretakis | GPA-21-129, REZ-21-130, IS-21-131 | Commercial Center |  | NorthStar Engineering | 1/22/25- Project was withdrawn. |  |  |  |  | SJ |  | HIGH
Sunrise Trucking | SPC-24-64, TPM-24-65 | Intermodal terminal | 2519 N airport Way | MCR Engineering | 1/16/25- Told by applicant to follow-up March 1st |  |  |  |  | SJ |  | MID
Airport Business Center NS | SPC-24-71 | Industrial Warehouse | 2803, 3045, 3157, and 3123 N Airport Way | Grenlaw Partners | 1/15/25- Applicant is discussing options internally for project to move forward. |  |  |  |  | SJ
Airport Annexation | ANX-23-65, PRZ-23-66 | Annexation Only |  |  | 1/9/25- Possible withdrawal per App, will follow up when applciant is back from vacation 2/24/25. |  |  |  |  | SJ
The Village at Villa Ticino | SPC-24-04, UPN-24-05, TPM-24-06 | Commercial Businesses | 995 N Airport Way | MCR Engineering | Revised comment Ltr. To applicant sent 12/23/24. 15183 document required. CEQA scoping meeting 3/3/35. | Pending Response/Action from Applicant |  |  |  | TB
Diede Self Storage | ANX-23-41, PRZ-23-42, SPC-23-43, CUP-23-46 | Self Storage | 15733 S Airport Way | Diede Construction, Inc. | 3/3/25 - Likely to withdraw application. Awaiting confirmation from Diede. | Unknown |  |  |  | TB
Kaiser Emergency Room Expansion | PST-24-43, IS-24-83, LLA-24-82, SPC-24-81 | ER Expansion | 1777 W Yosemite Ave | Kaiser | Awaiting CEQA document |  |  |  |  | TB | David Bahr
Pillsbury Road Commercial | SPC-23-61, UPN-23-62, MSP-23-63 | Mixed Commercial | 1840 Pillsbury Road | RMK Design, Inc. | Comment Ltr. To applicant sent 2/3/25 | Pending Response/Action from Applicant |  |  |  | TB
400 Industrial | MPM 24-59 | Site Improvements | 400 Industrial |  | Comment Ltr. To applicant due 1/30/25 | Pending Response/Action from Applicant |  |  |  | TB | Lauren
Crossroads Plaza | TPM-24-87 | Commercial | 2064 N Union Road | Manteca 18, LLC | (comments sent 11/27) |  |  |  |  | AD
Sonic Drive Thru | SPC-24-24, UPN-24-25 | Drive Thru Restsurant | 2153 Daniels Street | Sandy Singh | [5 empty] | AD |  | HIGH
ARCI Office Building | SPC-23-100 | Medical Office Building | 1093 Eucalyptus Street | Elevation Design & Consulting | [5 empty] | AD |  | MID
Prologis Expansion | SPC-24-72 | Expansion | Pheonix Drive | HPA Architecture | CEQA Checklist received 1/23/25 | Resubmittal Review - In Progress | N/A | N/A |  | JO
1155 E Yosemite Ave | SPC-24-12 | Laundry and Retail | 1155 E Yosemite Avenue | David Rasuli | [5 empty] | JO
407 Spreckels (Prologis #2) | SPC-24-29, CUP-24-30 | NewWarehouse & Industrial | 407 Spreckels | Prologis | EIR being prepared by Consultant; draft due 3/1/25 | Initial Review In-Progress |  |  |  | JO
GESCO Fire Pump | SPC 24-81 & LLA 24-82 | Industrial |  |  | Distribution #2 sent. Letter due 3/14/25 | Pending Response/Action from Applicant |  |  |  | TB
Crossroads Community Church | PSC 24-51 | New Church Admin Building | 1505 Moffat Blvd. | Ishita Bansal | Not complete. Waiting on applicant to submit. 2/25/25 | Pending Response/Action from Applicant |  |  |  | NZM
Machado Ranch - Lot 91 Var. | MZM 25-13 | Minor zone mod. | 2401 Diablo View | Red Gabriel | Not complete. Waiting on applicant to submit. 2/19/26 | Pending Response/Action from Applicant |  |  |  | NZM
Machado Ranch -Phase 2 | MPM 25-08 | Architectual update | 2550 S Airport Way | Red Gabriel | Waiting on corrections to be sumitted by applicant 2/25/25 | Pending Response/Action from Applicant |  |  |  | NZM
Tractor Supply/Dutch Bros | SPC 25-18 & LLA 25-18 | Parcel split | 2160 Union Rd | Joe Verceles |  | Initial Review In-Progress | June?? |  |  | NZM
Yosemite Plaza |  | New Retail Building | 1492 W Yosemite Ave | [6 empty] | ?
Chamberlain Annexation |  | Sign Board Project | NE City | City | Preparing for an outreach meeting with res. In April 25 (02/24/25) | No Formal Submittal | May | June |  | JO
Climate Action Plan |  |  | City-wide | City | Admin. Draft #1 comments due 02/10/25 | Out for internal review | ??May? | ?? June?? |  | TB
Zoning Code Update | MCA 25-00xx | Zoning Code updated per GPU & HE | City-wide | City | In progress review and edits by Deputy | In-progress | ??May? | ?? June?? |  | JO
Nexus Fee Study |  |  |  |  | Call with consultant to discuss timelines, draft due to City in april/may (02/24/25) | Kick-off in February |  |  |  | JO

## Residential
Name of Project | Project # | Description | # of Units | Location | Applicant | Notes | Status | PC Date | CC Date | Complete Lts. | Planning PM | Eng. PM | PRIORITY
PACIFIC WEST AFFORDABLE APARTMENTS | SPA-23-112 | APTS | 270 | 1688 S Airport Way | Pacific West Communities, Inc | 2/19/25- Told by ENG that conditions can be expected next week. Tentative April meeting. |  |  |  |  | SJ | Toshi | HIGH
Harmony Woods | P24-49, ANX, PRZ, SDJ | SFR | 147 | S Aiport Dr. n/o Kiper | MCR Engineering | 2/19/25- Told by ENG that I can expect commetns back on second round next week. Will then issue next comment letter for corrections. |  |  |  |  | SJ | Toshi | MID
Sedan Subdivision | ANX-24-37 PRZ-24-38 SDJ-24-39 DEV-24-40 EIR-24-41 | SUB-DIVISION | 310 | 9715 E Sedan | Meritage | 2/19/25- Told by ENG that I can expect comments back next week. |  |  |  |  | SJ
4-C RANCH | SDJ-21-024 | SUB-DIVISION | 81 | 9683 E LOUISE RD | Toni Raymus | letter sent 2/18/25 | Resubmittal in review by Staff | 2025-03-20 |  |  | TB | Toshi
YOSEMITE FAMILY APARTMENTS | SPA-23-113 | APTS | 260 | 1758 W Yosemite Avenue | Pacific West Communities, Inc | SR Docs pending Deputy for review | Scheduling for Approval/Hearing Action | 2025-03-20 |  |  | TB
Edwards Grove | ANX-24-33 SDJ-24-34 PRZ-24-35 LlA-24-36 | SUB-DIVISION | 79 |  |  | CEQA scope approved 2/10/25. | Resubmittal in review by Staff |  |  |  | TB
Wawona Apartments | SPA-24-79 | APTS | 44 | 2027 Wawona Street |  | CEQA draft IS/MND distributed. Due 3/18/25 | Resubmittal Review - In Progress |  |  |  | TB | David Bahr
SARENE PLACE APARTMENTS | SPC-23-85 | APTS | 6 | 429 Sutter Street | Jeremy Metz | [5 empty] | AD |  | HIGH
Union Ranch North (Annexation) | DA-20-139 | SUB-DIVISION | 450 | S UNION RD | Albert Boyce | Pending revision to TSM 2/12/25 | Scheduling for Approval/Hearing Action |  |  |  | JO |  | MID
PSS Mixed-Use Project | SPR 25-09 & CUP 25-09 | Mix-Use | 164 MFR/ 14,714 s.f. retail | 2218, 2210 & 2226 W. Yosemite Avenue |  | Awaiting missing MSP document |  |  |  |  | TB
Vans Subdivision |  | SUB-DIVISION | 202 | [7 empty] | SJ
Orchard Park |  | SUB-DIVISION | 245 |  |  | 2/18/25- Project deemed complete and reffered for comments due 3/19/25. |  |  |  |  | SJ
Lupton Triplex | SPA 25-11 | MFR | 5 | [7 empty] | AD
Villeda @ Oleander TPM | TPM 25-0012 | TPM | 3 Parcels |  |  | 2/20/25- Waiting for response from ENG regarding sharing a well, then I will update incomplete letter and get it emailed out. |  |  |  |  | SJ

## Status
| Type | Description
Staff | 1 | Initial Review In-Progress
App | 2 | Initial Review Complete - Pending Response from Applicant
- | 3 | Initial Review Complete
App | 4 | Resubmittal by Applicant
Staff | 5 | Resubmittal Review - In Progress
App | 6 | Pending Response/Action from Applicant
- | 7 | No Update
Staff | 8 | Scheduling for Approval/Hearing Action
Staff | 9 | Preliminary Review Only

## Outdated
Development Services Projects
Project Manager | Project Name | Start Date | Project Info | Status
Wungluck | User Fee Update | 2021-08-01 | User Fee Update for all Building and Planning Permits, Applications, and Services | Project kicked off in August, Data provided to Consultant and has been returned to City for review and comment. Draft due January 2022. Draft completed, awaiting Finance to move the item forward.
| New Development CFD | 2021-08-30 | Creating of a new Citywide CFD to help cover costs of required upkeep and maintenance | Contract Prepared and Signed in August 2021, in data collection, initial draft released internally in December. Scheduled for City Council 7/19/22.
| Permit Software Replacement | 2021-09-15 | Replacement of Current Permit Software for efficiency and customer service | RFP has been prepared and released. Three vendors responded. 2 demonstrations were held in December. Site visits to occur in March through June.
| Infill Fee Reduction Program | 2021-08-01 | Fee Reduction Program for Infill projects located in CBD-1 and CBD-2 | Initial Research Completed, Conference Call with Consultant Scheduled for first week of September to discuss ideas, concepts, and cost of further study. Infill Fee Reduction Program completed May 2022. May need to adjust for 305 W Yosemite
| 305 W Yosemite | 2022-06-15 | Redevelopment of a city owned vacant parcel at 305 W Yosemite. | RFP prepared and SLA in process.
| Roth Road Corridor Study | 2021-11-01 | With SJCOG as lead agency, partner with the City of Lathrop and SJ County to study and plan for needed improvements to the Roth Road Corridor | PDT meetings and stakeholder meetings taking place; Engineering coordinating efforts with consultants to establish ultimate buildout of City.
Simvoulakis | Hat Ranch | 2019-09-06 | 739 units | EIR circulated; community meeting on 1/12/23; potential PC hearing date in February, CC in March
| Lumina @ Machado Ranch | 2020-05-26 | 827 units | Approved by LAFCO; waiting on tax-sharing agreement to be finalized.
| North Manteca Annexation 1 | 2021-04-12 | 657 SFR, 450 MFR | North Manteca Annexation 1 Draft EIR ciculation complete, consultant is workign on response to comments; North Manteca Annexation 2 EIR not circulating until response to comments from NM A 1 incorporated into document.
| North Manteca Annexation 2 | 2021-04-12 | 560 SFR, 3 industrial lots
| Indelicato Annexation | 2021-08-19 | 173 units | Indelicato MND circulation paused due to issue with Engineering and access to Airport; new traffic section submitted to Engineering in December; once Engineering has reivewed, will circulate MND for 30 days (expected in Feb 2023).
| Municipal Services Review | April, 2021 | Municipal Services Review for LAFCo | Interim MSR approved by LAFCO on 7/14/2022.
| LEAP Grant -- Reinvigorate distressed commercial with new residential | October, 2021 | Conducting vested party informal interviews to present to Planning Commission and City Council and grant status report in November | Consultant is working on CMU developmetn standards to integrate into MC update; Workign on environmetnal clearnce for Poag shopping center.
| Climate Action Plan Update | October, 2021 | Update of 2013 CAP for consistency of GP Update | Need inventory of power consumption by Public Works Department
| Development Code Update | January, 2022 | Update of Development Code to be consistent with GPU | On-going and formal commencement upon General Plan Update adoption
Erias | Downtown Specific Plan | n/a | Long Range plan for downtown | Draft Complete - routed for editting 11/09. On hold.
| Department Succession Plan | 2021-08-23 | Provides for department succcession | Implemented Planning Dept re-org, building to follow once new position is filled. Positions approved by City Council. Funding now required.
| Standard Conditions of Approval | 2021-07-01 | Create standard COA's for new growth | Draft Complete - routed to Engineering 11/09
| General Plan Update | April, 2017 | Comprehensive General Plan Update | Second EIR circulation to be complete on 1/6/2023; consultant to prepare response to comments.
| Affordable Housing Fee | June , 2021 | Inclusionary housing/affordable housing fee ordinance | Draft Report completed, sent to BIA 7/5/2022 for review and comment; item paused.