## Sheet1
Planning Division
Current and Anticpated Project List
Active Projects
Project | Project #/ Type | Description | Status | STATUS | Planner
General Plan & Zoning Ordinance Map consistency | CITY INITIATED | Map consistency | Henson | To create a schedule of project milestones. | Henson/ Durrer
Records Retention | CITY INITIATED | Find, Organize, Scan, Inventory, Files |  | 4 Shelves complete | All Hands
Zoning Ordinance Design Guidelines | CITY INITIATED | Small Lot Residential Design Guidelines | Henson | Time w/submittal of Trails PD Design Guidelines for the small lots. | Durrer
The Trails |  | Williamson Act Cancellation |  |  | Durrer
Austin Road | DA-12-98-01, and SDM-12-77-01 | Phase 1 entitlements including a Tentative Parcel Map and Development Agreement | Durrer |  | Henson
T&A Painting Office | SPC-12-59-01 | Site Plan to Convert House on Airport Way to Painting Contractors Office |  |  | Henson
Woodbridge Apartment Complex | SPA-12-78-01 | Site Plan Review and Minor Specific Plan Amendment | Henson |  | Henson
Housing Element Progress Report | Annual Obligation | Provide the State Housing & Community Development Department with annual progress report |  |  | Meissner
Machado Estates | SDJ, ANX, PRZ, DA | 500 lot subdivsion, with DA, Annexation and Prezone. | EIR certified, terms of DA still be negotiated |  | Henson
Island Annexation | 12-99-01 ANX & PRZ CITY INITIATED | Woodward Road Island annexation and Prezone. (9 parcels) |  |  | Henson
Bicycle Master Plan Update | SVP Grant - CITY INITIATED | Update of the Bicycle Master Plan (Smart Valley Places) |  |  | Meissner
LGO GHG inventory | CITY INITIATED | Local Government Organization Greenhouse Gas Inventory (Grant: Great Valley Center Modesto) |  |  | Durrer & Meissner
Air Quality Element Update | SVP Grant- CITY INITIATED | Update of the General Plan Air Quality Element To include CAP (Smart Valley Places) |  |  | Durrer & Meissner
State Flood Legislation | SVP Grant - CITY INITIATED | General Plan Updates as necessary to accommodate State Flood Legislation, GP Element update (Smart Valley Places) |  |  | Henson
Approved Auto Center | MPM 12-57-05 | Establish Car Sales Building on existing used car sales lot. |  | Application Date 10/12/12 | Durrer
Revise Master Sign Program | MSP 12-49-01 | Revise Master Sign Program for Valley Light Industrial Project 2353 W. Yosemite Ave |  | Application Date 10/12/12 | Henson
Growth Allocation Processing for October | GMO 12-48-01, 02, 03 | GMO allocation applications for Wesport Plaza, Terra Ranch, and Evans Estates |  | Application Date 09/18/12, & 10/09/12 | Meissner
French Camp Outlet Wetland Mitigation and Permitting | CITY INITIATED | The wetland area of the City's storm drainage canal just west of Costco will be removed as part of the piping of the canal. Requires State and Federal Permitting and Environmental. |  | Will mature with Family Entertainment Zone and establishment of plans for alignment of roadways and underground utilities. | Meissner
Planned Development Binder | CITY INITIATED | Planned Developments will be mapped on the zoning map with a unique color and referenced to a separate map with more detail on the PD's allowances. |  | Partially completed by Intern | Durrer
Habitat Technical Advisory Committee | Monthly Obligation | SJCOC HTAC |  |  | Henson
Regional Smart Growth Transit Oriented Development Plan |  | Review and comment on the Regional Smart Growth Transit Oriented Development Plan being developed by SJCOG |  |  | Durrer & Meissner
Vacant Lot Inventory | Monthly as time permits |  |  |  | Meissner
Residential and Commercial Activity Logs | Monthly as time permits |  |  |  | Rick/ Mandy
Uhaul at GMC Pontiac | 12-78-03 | Use permit and Site Plan Review Entitlement Processing |  |  | Durrer
Promenade Shops Billboard | 12-73-02 | Use permit, DA Amendment, PD Amendment, for LED billboard shopping center sign |  |  | Durrer
Pacific Industrial Park | 12-78-02 | Site Plan to construct 1 million sq. ft. building |  |  | Meissner
Approved Auto Center | MPM 12-57-05 | Establish Car Sales Building on existing used car sales lot. |  | Application Date 10/12/12 | Durrer
Revise Master Sign Program | MSP 12-49-01 | Revise Master Sign Program for Valley Light Industrial Project 2353 W. Yosemite Ave |  | Application Date 10/12/12 | Henson
Growth Allocation Processing for October | GMO 12-48-01, 02, 03 | GMO allocation applications for Wesport Plaza, Terra Ranch, and Evans Estates |  | Application Date 09/18/12, & 10/09/12 | Meissner
Completed
Project | Project #/ Type | Description | STATUS | STATUS | Planner
Calvary Community Church PV/Carport | MPM 12-57-04 | Contruct Photo Voltaic/Carports in existing parking lot of Calvary Community Church |  | Completed | Meissner
Ad Hoc Sign Committee | 12-90-01 CITY INITIATED | Code Update to provide for off-site signage. |  | Completed | Meissner
McDonald's Spreckels | SPC/UPJ 11-78-02 | Site Plan Review & CUP to construct a new McDonald's | Comment letter sent on Oct. 24, 2011 | Completed | Henson
Rainforest Nursery | SPC 12-59-02 | Site Plan Review for an Open air Nursery at 1982 W. Yosemite Av. |  | Completed | Meissner
McDonald's 1236 W. Yosemite | MPM-12-57-02 | Minor Plan Modification for revisions to landscaping and drive thru |  | Completed | Henson
Manteca Marketplace GPA & REZ | GPA & REZ 12-96-01 | General Plan Amendment and Rezone the Manteca Marketplace shopping center from Neighborhood Commercial Zoning to Commercial Mixed Use. |  | Completed | Durrer
McDonalds Daniels Airport | MPM-12-57-03 | Minor Plan Modification for revisions to landscaping and drive thru |  | Completed | Meissner
Recycling Collection Facility | MPM-12-57-01 | Establish a Recycling Collection Facility at 1001 E. Yosemite Av. (Code enforcement) |  | Completed | Meissner
Union Ranch Specific Plan Amendment | 12-91-01 SPPA | Specific Plan Amendment for changes to fencing requirements |  | Completed | Meissner
Wetmore Cell Tower | 12-73-01 | Use Permit to construct a cell tower at City facility on Wetmore |  | Completed | Durrer
Ken Hill Estates Tentative Parcel Map | SDM 12-77-02 | Tentative Parcel Map |  | Completed | Durrer
Yosemite Square |  | Master Plan, GPA, Rezone & TM for a 144.3 acre project including residntial and commerical/office development | Draft Master Plan complete, Mitigated Neg Dec to be released the week of Nov. 1st. | Completed | Durrer & Henson
Indy Carwash/Bakery | CUP & MPM | Phased development & remodel |  | Completed | Durrer
Save On Gas & Liquor | UPN 11-58-08 | Use Permit to allow U-Haul rentals | Application routed Oct. 27, 2011 | Completed | Henson
CenterPoint | DAA-11-97-01 | Entitlement processing |  | Completed | Henson
Anticipated
Project | Project #/ Type | Description | STATUS | STATUS | Planner
Wireless Tower at Yosemite Commercial |  | New Wireless Communications Tower |  |  | Henson
Trails |  | Design Guidelines & Phasing Plan |  |  | Durrer
F&M Bank |  | Site Plan Review Entitlement Processing |  |  | Durrer?
Hat House | Master Plan/Specific Plan | Entitlement processing & Enviromental |  |  | ?
Yosemite Square |  | Phase 1 entitlements |  |  | ?
Family Entertainment Zone | Master Plan/Specific Plan | Entitlement processing & Enviromental |  |  | ?
Great Wolf |  | Entitlement processing & Enviromental |  |  | Meissner?
Wetland Bank Annexation |  | Entitlement processing & Enviromental |  |  | Meissner?
Oakwood Shores Annexation |  | Entitlement processing & Enviromental |  |  | Henson?
CenterPoint |  | Phase 1 entitlements |  |  | Henson
New World |  | Implementation for CDD |  |  | Meissner?
7th Day Adventist Church Expansion |  | Entitlement Processing |  |  | Henson?
Ed Cardoza Annexation SW Corner Lathrop/Airport |  | Entitlement processing & Enviromental |  |  | Henson?
Large Annexation Per Ron Cheek |  | Entitlement processing & Enviromental |  |  | ?
Bike/Ped Safe Routes to School Plan |  | Work with SJCOG to plan for routes within Manteca |  |  | Meissner
State Department of Finance | Annual | Provide State Department of Finance with annual housing counts |  |  | Meissner
Growth Management | CITY INITIATED | Update Growth Management Ordinance for compliance with updated Housing Element |  |  | Meissner
GENERALLY WE FACILITATE ALL PUBLIC INQUIRIES REGARDING DEVELOPMENT AT ANY LEVEL