## Current
Planning Division
Current Project List,
UPDATED: 09/24/2013
Active Projects
Project | Appl. Date: | Project #/ Type | Description | STATUS | Priority | Planner
Raley's #311 Fresh Vision Remodel |  | MPM | Minor Plan Modification | Project file to be created and assigned. |  | ?
The Commons at Union Ranch Parking Enhancement | 2013-09-13 | MPM 13-57-07 | Minor Plan Modification to increase the number of parking stalls for the Commons at Union Ranch. | Project assigned. |  | Durrer
Alma Apartments | 2013-09-13 | SPA & SDN 13-78-01 | Site Plan for a 184-unit apartment and/or condominium complex and tentative parcel map to create 4 parcels for the new project area. | Meeting with project engineer and owner 05/23/13 indicates the project will move forward. Initial contact and meeting with ED & MM. Project assigned. |  | Durrer
General Plan & Zoning Ordinance Map consistency | N/A | CITY INITIATED | Map consistency | Zoning Map Update Workshop for Non-Residential properties held at PC meeting March 26. Workshop for Residential properties held June 11th. Work to begin on Environmental Document. Schedeled for PC hearing August 27. Planning Commission approved 08/27. Public Hearing w/CC scheduled for 09/17. |  | Henson/ Durrer
Air Quality Element Update | N/A | SVP Grant- CITY INITIATED | Update of the General Plan Air Quality Element To include CAP (Smart Valley Places) | Admin Draft Complete, Distribution of Draft to PC on 3/12. Workshop held with PC on 4/9. Draft Initial Study under review. Public Hearing with Planning Commission scheduled for 09/24. |  | Durrer
LED Sign | 2012-07-25 | PDA, DAA, UPJ 12-73-02 | Establish LED billboard at Promenade Shops | Workshop held March 12th. Awaiting photometric plan from applicant prior to scheduling follow up workshop and/or PC hearing. Direction from Admin to send 30-day letter to act or quit 07/17. Resubmitted 07/31. ED to review resubmitted materials as time permits. |  | Durrer
U-Haul of Manteca | 2012-11-27 | SPC-12-78-03 | Establish Personal Storage Use at 1190 S. Main St. | 2nd Comment Letter sent. Awaiting response to comments. No response. Resubmitted 07/11 re-routed and comments due back 08/08. |  | Durrer
Woodward Park 1 | 2013-04-03 | 13-99-01 DA, PRZ, ANX, SDJ & EIR | Tentative Map, General Plan Amendment, Prezoning, Annexation, Development Agreement & Enviromental | ED has prepared RFP for the EIRs for the three projects of the SOWA. Proposals due July 1st. Incomplete letter sent to applicant including comments, corrections, and additional materials necessary to complete application. Raney selected as env. consultant. Pro Serv Agreement to City Council 08/20. Kicked off Environmental 08/21. |  | Durrer
Woodward Park 2 | 2013-04-03 | 13-99-02 DA, PRZ, ANX, SDJ & EIR | Tentative Map, General Plan Amendment, Prezoning, Annexation, Development Agreement & Enviromental | Same as Woodward Park 1 |  | Durrer
Hat Ranch | 2013-05-08 | 13-99-03 ANX, GPA, PD, PRZ, SDV, DA, EIR | Tentative Map, Planned Development, General Plan Amendment, Prezoning, Annexation, Development Agreement, and Enviromental | ED has prepared a draft RFP for the EIRs for the three projects of the SOWA. Proposals due July 1st. Incomplete letter sent. Raney selected as env. consultant. Pro Serv Agreement to City Council 08/20/2013. MH to provide answer on Kennedy Jenks or Fernando for WSA. ED & MM to discuss dual project description EIR with Raney. Raney to prepare PSA amendment for dual project description. |  | Durrer
Zoning Ordinance Design Guidelines | N/A | CITY INITIATED | Small Lot Residential Design Guidelines | Time w/submittal of Trails PD Design Guidelines for the small lots. Trails on-hold. |  | Durrer
The Trails |  |  | Williamson Act Cancellation | Waiting on Cancellation Payment to County. Waiting on application fees for revised appraisal. |  | Durrer
State Flood Legislation | N/A | SVP Grant - CITY INITIATED | General Plan Updates as necessary to accommodate State Flood Legislation, GP Element update (Smart Valley Places) | RH & MM met with Jim Stone 02/27, RH to formalize SOW. Mark Houghton assigned Koosun as new PW contact. New information regarding timing discussed with State representative 08/13. |  | Henson
Revise Master Sign Program | 2012-10-12 | MSP 12-49-01 | Revise Master Sign Program for Valley Light Industrial Project 2353 W. Yosemite Ave | Project awaiting response from applicant to initial review comments. Henson to write letter. RH to send 30-day letter to act or quit. |  | Henson
Austin Road | 2013-02-07 | 13-91-01 MPA, GPA, REZ. | Master Plan, General Plan Amendments and Rezoning | Application routed for initial review. 9/11/13 Staff working with Fehr & Peers on traffic impacts. Staf is writing EIR addendum |  | Henson
Doctors Hospital | 2013-02-27 | MPM 13-57-02 | MPM for Fuel Tank and Generator in parking lot to serve main hospital building. | Application routed for initial review. RH to send 30-day or quit letter due to inactivity. |  | Henson
Copper Cove (Yosemite Square) | 2013-05-20 | 13-75-01 SDJ & IS | Tentative Subdivision Map and Initial Study for 342 low density residential lots on 64.2-acres. | Project assigned to RH. Application routed for initial review. Incomplete letter sent. MM met with RLC regarding completeness letter 06/18/2013. RH to comment on map consistency w/Master Plan. Project scheduled for public hearing 09/24. |  | Henson
Monte Bello Estates (Ott) | 2013-05-29 | 13-75-02 SDJ, GPA, REZ, IS | Tentative Subdivision Map, General Plan Amendment, Rezone, and Initial Study for 121 low density residential lots on 30-acres. APN 202-220-07 | Application materials under review prior to initial routing and review. Application routed for initial review 06/21/2013 with comments due 07/11/2013. RH to prepare letter regarding comments received on original map, and to meet with FC & MH on revised map. MM to request memo from MH RE: Caltrans request for TIS. Revised application to include GPA for CMU at Airport and Louise. 9/11/13 Staff waiting for resubmittal |  | Henson
Machado Estates | 2005-01-19 | SDJ, ANX, PRZ, DA | 500 lot subdivsion, with DA, Annexation and Prezone. | Met with Owner, Buyer, Engineer, and Planner 05/15/2013 to explain current status and process to move forward to completion. Revised map submitted for review 08/05/2013. RH to contact applicant for SDM application fees. |  | Henson
Cottage Food Operations -AB1616 | N/A | CITY INITIATED | Research changes necessary to existing ordinance and/or processes to accommodate the new legislation. | RH continuing to research. RH suggested preparation of a handout 07/30. |  | Henson
Family Entertainment Zone (FEZ) | Pending | GPA, REZ, PD, Master Plan | Entitlement processing & Enviromental | Waiting for Project Description from Don Smail in order to prepare RFP for EIR. FC/DS prepare project description. RH preparing draft RFP for distribution. Distribution of RFP depending on legal determination 08/06/2013. MM met with Art Nunez RE: FEZ application (08/14). Final project description for RFP provided 08/16. MM Received draft application materials for review 08/28. RH working with DS to finalize RFP, waiting for revised project description 09/11/2013 |  | Henson/Meissner
Great Wolf Lodge | Pending | GPA, REZ, PD, SPC | Entitlement processing & Enviromental | Same as above. No project application materials. |  | Henson/Meissner
107 West North Street, Façade and Parking Remodel. | 2013-06-26 | MPM 13-57-03 | Minor Plan Modification to update the façade of the old CAPS building on the northwest corner of North and Main Streets and update the parking and landscaping. | Application materials out for initial routing and review with comments due back 08/07/2013. Routed revised site plan to Lumen & Jim 09/05. |  | Kang
Meritage Homes, Pillsbury Estates Sales Trailer | 2013-08-29 | TUP 13-58-02 | Temporary Use Permit application to establish a model home complex, temporary sales trailer, and parking lot for the Pillsbury Estates subdivision. | Project under review for application completeness. Initial comment to applicant that the temporary sales trailer must be on-site. Expecting revised application materials. |  | Kang
Meritage Homes, Pillsbury Estates Sales Trailer |  | TUP | Temporary Use Permit application to establish a model home complex, temporary sales trailer, and parking lot for Oleander Estates Unit 1. |  |  | Kang
Book Fair |  | TUP 13-58-?? |  |  |  | Kang
Used Car Event |  | TUP 13-58-?? |  |  |  | Kang
Woodward Estates | 2013-06-12 | 13-75-03 SDJ | Tentative Subdivision Map and Initial Study for 7177 low density residential lots on 16.79-acres. | Application materials under review prior to initial routing and review. Application routed for initial review 06/21/2013 with comments due 07/11/2013. Incomplete letter delivered 07/11/2013. Revised Map submitted and Re-routed 08/05/2013. MM to request memo from MH RE: Caltrans request for TIS. MM to prepare IS/MND. |  | Meissner
Consumer's Choice Pest Control, 1726 N. Main St. | 2013-07-03 | MPM 13-57-04 | Minor Plan Modification to update the project site plan, parking and landscaping due to the N. Main St. widening project which requires removal of the existing curb, gutter, sidewalk, and street frontage lanscaping. | Application materials routed 07/19/2013 for initial routing and review with comments due back 08/02/2013. Incomplete letter mailed 08/02/2013. MM spoke with applicant RE: incomplete letter 08/19. No response to comment letter 09/10. |  | Meissner
Great Valley Academy and Place of Refuge | 2013-07-31 | MPM 13-57-06 | Minor Plan Modification | Awaiting corrected project description prior to routing 08/05/2013. Project Routed 08/07 w/comments due 08/21. Correction letter mailed 08/28. Pubilc Notice mailed 09/16. |  | Meissner
Municipal Services Review & Sphere Of Influence Update | N/A | CITY INITIATED | Forthcoming annexations to the City will require an update of the MSR. Needs to be budgeted for and to find a consultant to complete. MSR updates are scheduled for each 5-years. The SOI update provides an opportunity for the City to amend its 10-year sphere to include areas not previously contemplated (e.g. Hat Ranch and Lathrop/99 interchange) | Received rough proposal and estimated cost from DeNovo Planning for review prior to formalizing proposal. MM requested funding from FC and City Manager. Preliminary budget indicates that the money will be available. MM shared MSR proposal w/MH. MH indicated that support for data collection/creation dependant on future staffing. MM to prepare Pro Serv Agreement 08/06/2013. MSR routed for review and approval 08/15. Currently in Finance 09/10. To City Manager for approval 09/12/2013. Approved by CM 09/23. Schedule Kickoff. |  | Meissner
Bicycle Master Plan Update | N/A | SVP Grant - CITY INITIATED | Update of the Bicycle Master Plan (Smart Valley Places) | Mark Houghton requested participation by PW and emphasis of class 2 bike lanes on main roadways rather than class 3 on neighborhood streets. MM to route existing BMP to PW for comments. MM preparing binders of neighboring City and County BMP's and Manteca Circulation Element, and general plan goals/policies/implementation measures that promote bicycle and ped. Survey created and posted 09/09. |  | Meissner
Zoning Ordinance Updates | N/A | CITY INITIATED | Update Zoning Ordinance to fix aspects of the code that are not working well. | Folder full of potential amendments. MM met with Commissioner Morowit regarding this item being moved forward 06/10/2013. |  | Meissner
Corporation Yard Consolidation | N/A | MCA | General Plan Amendment, Rezone, and Initial Study to establish Public Quasi Public zoning for the corporation yard consolidation projects recently constructed on Wetmore (i.e. Animal Shelter and Vehicle Maintenance Building). | NEW APPROACH: Research previous code amendment that allowed Public Buildings in any zone. |  | Meissner
Active Previously Entitled Projects
Austin Road/Hwy. 99 Interchange Environmental |  | IS/MND | Review and management of the Initial Study and Mitigated Negative Declaration for the interim improvements being made to the Austin Road and Hwy. 99 Interchange to support the Austin Road Business Park and Residential Communities Master Plan project area. | MND sent to State Clearing House 7/13 |  | Henson
Austin Road Environmental | N/A |  | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | Met with Ripon and County regarding Sub Regional Fee 05/29/2013. Meetings on June 10 with Traffic Consultant and Developer regarding MMRP. Proposal to prepare sub regional fee submitted 06/11/2013. Pro Serv Agreement with F&P RE: Sub Regional Fee routed for review and approval by KM/CM 08/01/2013. Funding? PSA approved Fehr & Peers completing work, due 10/4/13. |  | Henson
Centerpoint Environmental | N/A | Master Plan | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | Per Mark Houghton the Grading Permit is conditioned to require Air District permitting prior to work. RH, Centerpoint has not bonded for its Habitat Mitigation. Centerpoint paid cash for 57.4-acres of Habitat Mitigation 06/13. Water, Sewer, and Grading Permits ready to issue upon pulling Encroachment Permit 07/09/2013. |  | DeJong/ Henson
Crothall CIC South - Centerpoint Project Development | N/A | Plan Check | Plan Check and MMRP for Crothall Laundry Facility | RH continuing discussion with Jeremy RE: conditions of approval for Crothall. Construction application submittal 08/06/2013. RH to confirm architecture and grading mitigations are complete. Grading Permit issued 9/10/13. Plan check comments for Building Permit provided 9/5/13. |  | DeJong/ Henson
Yosemite Square Environmental | N/A | Master Plan | Plan check and review of the Yosemite Square Master Plan Improvement plans and compliance with the MMRP. | Plans submitted |  | DeJong/ Henson
Popeye's | N/A | Plan Check |  | Plans submitted, comments due 10/8/13 |  | Henson
AT&T Cellular/Clock Tower | N/A | Plan Check | Plan Check for the building permit to construct the AT&T Cellular/Clock Tower. | Plan Check comments provded 9/3/13 |  | Henson
Evans Estates | N/A | SDJ | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | Met with KB Homes and Raymus on 06/05/13 with due-dilegence questions. ED/FC/MH provide answers to due-dilegence questions, 06/19/2013. MM met w/Chris Mullen & MH RE: availablity (i.e. well, tank). |  | DeJong/ Durrer
Silva Estates | N/A | SDJ | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | Applicant has met requirements of the MMRP to allow final map and grading. Need to bond for improvements and obtain final approval of subdivision improvement agreement. |  | DeJong/ Meissner
Oleander Estates | N/A | SDJ | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | JD, Lumen, RC, & MM met with Jed Bennett of DR Horton on 04/10/13 to discuss steps moving forward with 118-units at NW project corner. Jed to submit master plans for review as additions to PD and Building Plan Check. MM to prepare approval letter for additional master plans. MM working with Toni Raymus on compliance with MMRP 06/04/2013. JD, improvement plans back to MCR for corrections. MM determined that Oleander has complied with MMRP requirements allowing grading 07/30/2013. |  | DeJong/ Meissner
Pillsbury Estates | N/A | SDJ | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | Received letter from SJVAPCD to allow grading. Grading permit issued. Minor Use Permit application to establish the model home complex 08/29/2013. |  | DeJong/ Durrer
The Trails | N/A | SDJ | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. (see above and Anticipated page) | Met with Jay Utal regarding various outstanding mapping conditions and requirements. Determined problem with Storm Drainage requirement. Storm Drain Condition revisions approved by City Council 05/21/2013. FC met with State regarding drainage 06/14/2013. Due-dilegence mtg. with potential buyer 07/18/2013. |  | Durrer/Clark
Terra Ranch | N/A | SDJ | Project follow-up: Review of Improvement Plans, MMRP Tracking, Developer Meetings. | MM & FC spoke/met with project engineer regarding substantial compliance questions due to minor mapping adjustments. Provided answers to due-dilegence questions of potential buyer on utilities and GMO, 07/31/2013. |  | Meissner/Clark

## Anticipated
Planning Division
Anticipated Project List
Anticipated Projects
Project | Project #/ Type | Description | STATUS | Planner
550 Commerce Court | LLA & MPM | Minor Plan Modification and Lot Line Adjustment to add land to the parcel to accommodate a new row of parking for the project site. | MK, spoke with the architect from Siegfried about the proposal and submittal requirements 09/10/2013 | MK
Oakwood Trails at Tara Park | SDJ, GPA, REZ | Tentative Subdivision Map, General Plan Amendment and Rezone for the area South of Bronzan, West of McKinley, North or Woodward. | Meeting with Project Engineer 05/30/2013 indicates that the project will move forward. Follow-up meeting on 07/16 with project engineer to discuss design challenges identified at May meeting. | ?
Silva Estates 2 | SDJ | Requires revisions to approved tentative map to accommodate lots fronting to Woodward Avenue. Requires review and recommendation of Planning Commission for review and approval by City Council. | MK, ED and JD met with the Milners in regards to bringing the subdivision back on line. MM, ED, JD met with project engineer RE preliminary design 08/05/13. | ?
Arco at Stadium Square | LLA, SPC | Lot Line Adjustment and Site Plan Review application to establish a new Arco Gas Station and Mini Mart east of the McDonald's site on what was originally approved for a Walgreen's. | MM received email from Kitchell Development in regard to a Lot Line Adjustment to reconfigure an existing parcel to accommodate the Arco. | ?
Tesla Charging Station | MPM | Minor Plan Modification to modify the parking area near the northwest end of the Promenade Shops at Orchard Valley Shopping Center to add a Tesla (Electric Vehicle) charging station. | MM emailed application requirements and time estimates to Poag and McEwen representatives, 07/09/2013. Status update from Poag and McEwen that Tesla moving forward to application 07/25/2013 | ?
MUSD Union Ranch East School Site | SPPA, SDJ, DAA IS/MND | Specific Plan Amendment to redesignate the existing school site within the Union Ranch East subdivision for development as additional single family homes. Possibly requires a DA amendment. | MM met with project engineer regarding the entitlement process and timing 08/02/2013. | ?
MUSD Tesoro School Site | GPA, REZ, PD Amend, SDJ, IS/MND | General Plan Amendment, Rezone, PD Amendment to redesignate the existing MUSD school site within the Tesoro subdivision for development as additional single family homes. Possibly requires a DA amendment. | MM met with project engineer regarding the entitlement process and timing 08/02/2013. | ?
Trails | SDJ | Tentative Map for small lot areas |  | Durrer
Trails | PD Amend, MCA | Design Guidelines & Phasing Plan |  | Durrer
Sundance | SDJ, ENV | Requires revisions to approved tentative map to accommodate lots fronting to Woodward Avenue. Requires review and recommendation of Planning Commission for review and approval by City Council. | MM & FC met with Frontiers Homes regarding required tentative map revisions. ED and JD met with the Maria Dutra in regards to bringing the subdivision back on line. | ?
Oakwood Shores Annexation | ANX, PREZ, ENV | Entitlement processing & Enviromental | Rochelle to contact Jim Glaser (LAFCO) RE: City to enter into DA with Oakwood Shores. | ?
Shadowbrook | SDJ, ENV | Approved Tentative Map to brought back on line, may require re-map, DA Amendments. | Discussions with project engineers indicate the project will move forward. | ?
Arditi Property | GPA, REZ, SDJ | Tentative Parcel Map to split the property on both sides of Atherton Drive. General Plan Amendment and Rezone to accommodate a small lot residential subdivision. | Staff met with Florshiem Homes 05/14/13 regarding the proposed development. Project applicant to submit within the next 45-days. | Henson
CBS LED Signage at GWL/FEZ | UPJ, DA | Establish LED Billboard on City property west of Costco on Daniels, future development site of Great Wolf Lodge. | MM, ED, met with City Manager, Don Smail, and City Attorney regarding technical details and legalities of locating the proposed LED sign in the GWL/FEZ project area 07/17/2013. | ?
Delta College Annexation | ANX, GPA, PREZ, SDJ, EIR | Annexation of the Delta College properties. The properties are currently PQP, but would be redesignated under master/specific plan to include Single & Multi Family, and Mixed Use Commercial Development. | MM, FC, KM met with Delta College reps and their planner to discuss annexation and future development potential 07/17/13. MM spoke with their Planner RE: land use and projections 08/07/13. | ?
French Camp Outlet Wetland Mitigation and Permitting | CITY INITIATED | The wetland area of the City's storm drainage canal just west of Costco will be removed as part of the piping of the canal. Requires State and Federal Permitting and Environmental. | Will mature with Family Entertainment Zone and establishment of plans for alignment of roadways and underground utilities. | ?
Staples Parcel Map | SDN | Tentative Parcel Map for ? | Kjeldsen Sinnock Neudeck informed me that they are wrapping up a tentative parcel map application for the Staples Property in Spreckles Business Park. | ?
Northeast Airport Way Annexation | ANX, PREZ, SDJ, ENV | Cardoza Estates Specific Plan Redo? | MM, FC met with interested party RE 40-acre parcel at Airport adjacent to Woodbridge on the south to discuss annexation for subdivision 07/30/13. | ?
PG&E Corp Yard | MPM | Include a corp yard with a CNG fueling station at the Ergonis property |  | ?
F&M Bank | SPC | Site Plan Review Entitlement Processing |  | ?
Wetland Bank Annexation |  | Entitlement processing & Enviromental |  | ?
New World |  | Implementation for CDD | ? | Meissner

## Tasks
Planning Division
On-Going Tasks
On-Going Tasks
Project | Project #/ Type | Description | STATUS | Planner
SJCOG RHNA | N/A | Participate on Regional Housing Needs Allocation (RHNA) Advisory Committee | April 25th Meeting to kick-off the process and establish process moving forward. | Meissner
Records Retention | CITY INITIATED | Find, Organize, Scan, Inventory, Files | 4 Shelves complete | All Hands
Housing Element Progress Report | Annual Obligation | Provide the State Housing & Community Development Department with annual progress report |  | Meissner
State Department of Finance | Annual | Provide State Department of Finance with annual housing counts |  | Meissner
SJCOG RTP/SCS | n/a |  | Contiuous | Durrer & Meissner
Smart Valley Places Time Keeping | n/a | Track hours for staff keep records updated for backup to finance | Continuous | Durrer
Smart Valley Places Monthly & Quarterly Reports | n/a | Compile hours, give overview and description of all activities completed both monthly and quarterly | Continuous | Durrer
Planned Development Binder | CITY INITIATED | Planned Developments will be mapped on the zoning map with a unique color and referenced to a separate map with more detail on the PD's allowances. | Partially completed by Intern | Durrer
Update Building Handouts |  | Review existing building handouts for consistency with the updated development standards. | In the process of making the changes (status update 02-27-13) | Mandy
SJCOG HTAC | Monthly Obligation | As a signator to the San Joaquin Multi Species Habitat and Conservation Plan, the City of Manteca is obligated to participate as a member of the plan's Habitat Advisory Committee (HTAC). | Meetings typicaly are scheduled for the 2nd Wednesday of each month. | Henson
SJCOG SJMSCP Fees Update | Annual Obligation |  | MM to prepare Council Agenda Report for updated fees to be adopted at the Council meeting of October 1, 2013. | Meissner
Successor Agency Oversight Board |  | EH is a member of the City's Successor Agency Oversight Board. |  | Durrer
Growth Management Allocation Process (March & October) | Bi-Annual | The City's Growth Management Ordinance establishes application periods for Growth Allocations for the 2 Friday of March and October. | Applications for March submitted for Silva Estates, Pillsbury Estates, and Yosemite Square. | Meissner
Bike/Ped Safe Routes to School Plan |  | Work with SJCOG to plan for routes within Manteca |  | Meissner

## Completed
Planning Division
Completed Project List
Completed
Project | Project #/ Type | Description | STATUS | Planner
AT&T Cell Tower Extension | MPM 13-57-01 | Extension of existing cell tower on Vanderbuilt Circle | Approved by FC | Durrer
AT&T Cell Tower Expansion | MPM 12-57-11 | Additional tower at Cabral | Approved by FC 03/05/13 | Durrer
U-Haul Truck Rental | UPN & MPM 12-73-03 | Establish U-Haul Truck rental at 1190 S. Main St | Approved by FC | Durrer
Growth Allocation Processing for October | GMO 12-481-01, 02, 03 | GMO allocation applications for Wesport Plaza, Terra Ranch, and Evans Estates | Approved | Meissner
LGO GHG inventory | CITY INITIATED | Local Government Organization Greenhouse Gas Inventory (Grant: Great Valley Center Modesto) | Completed | Durrer
Woodbridge Apartment Complex | SPA-12-78-01 | Site Plan Review and Minor Specific Plan Amendment | Approved by PC 12/11/2012 | Henson
Pacific Industrial Park | MPM 12-57-09 | Site Plan to construct 1 million sq. ft. building | Approved by FC 12/11/2012 | Meissner
Approved Auto Center | MPM 12-57-05 | Establish Car Sales Building on existing used car sales lot. | Application Date 10/12/12 | Durrer
Calvary Community Church PV/Carport | MPM 12-57-04 | Contruct Photo Voltaic/Carports in existing parking lot of Calvary Community Church | Completed | Meissner
Ad Hoc Sign Committee | 12-90-01 CITY INITIATED | Code Update to provide for off-site signage. | Completed | Meissner
McDonald's Spreckels | SPC/UPJ 11-78-02 | Site Plan Review & CUP to construct a new McDonald's | Completed | Henson
Rainforest Nursery | SPC 12-59-02 | Site Plan Review for an Open air Nursery at 1982 W. Yosemite Av. | Completed | Meissner
McDonald's 1236 W. Yosemite | MPM-12-57-02 | Minor Plan Modification for revisions to landscaping and drive thru | Completed | Henson
Manteca Marketplace GPA & REZ | GPA & REZ 12-96-01 | General Plan Amendment and Rezone the Manteca Marketplace shopping center from Neighborhood Commercial Zoning to Commercial Mixed Use. | Completed | Durrer
McDonalds Daniels Airport | MPM-12-57-03 | Minor Plan Modification for revisions to landscaping and drive thru | Completed | Meissner
Recycling Collection Facility | MPM-12-57-01 | Establish a Recycling Collection Facility at 1001 E. Yosemite Av. (Code enforcement) | Completed | Meissner
Union Ranch Specific Plan Amendment | 12-91-01 SPPA | Specific Plan Amendment for changes to fencing requirements | Completed | Meissner
Wetmore Cell Tower | 12-73-01 | Use Permit to construct a cell tower at City facility on Wetmore | Completed | Durrer
Ken Hill Estates Tentative Parcel Map | SDM 12-77-02 | Tentative Parcel Map | Completed | Durrer
Manteca Seventh Day Adventist Church | PST-12-39-02 | Preliminary Staff Review for Church expansion | Completed | Durrer
U-Haul of Manteca | PST-12-39-01 | Mini-Storage and Truck Rental 1190 S. Main St | Completed | Durrer
Yosemite Square |  | Master Plan, GPA, Rezone & TM for a 144.3 acre project including residntial and commerical/office development | Completed | Durrer & Henson
Indy Carwash/Bakery | CUP & MPM | Phased development & remodel | Completed | Durrer
Save On Gas & Liquor | UPN 11-58-08 | Use Permit to allow U-Haul rentals | Completed | Henson
Ernie's Lot Line Adjustment | LLA-12-5710 | Lot Line Adjustment for restaurant bldg | Completed | Durrer
Yosemite Auto Center | MPM-12-57-05 | Used Car Sales | Completed | Durrer
Austin Industrial Truck Dock | SPRA-12-57-07 | Add Truck dock to existing Industrial Park | Completed | Durrer
Regional Smart Growth Transit Oriented Development Plan |  | Review and comment on the Regional Smart Growth Transit Oriented Development Plan being developed by SJCOG |  | Durrer & Meissner
CenterPoint | DAA-11-97-01 | Entitlement processing | Completed | Henson
Growth Allocation Processing for March | GMO 13-481-01, 02, 03 | GMO allocation applications for Pillsbury Estates, Yosemite Square, and Silva Estates | Completed 04/01/2013 | Meissner
Atherton Drive Extension | MND | Mitigated Negative Declaration and Initial Study for the extension of Atherton Drive between Airport Way and Union Road | Adopted 04/02/2013 | Frederic/Meissner
Cinco De Mayo Music Festival | TUP 13-48-01 | Temporary Use Permit for large cultural fesitval at Best Buy parking lot and building | Approved 04/24/2013 | Henson
Cell Tower/Clock Tower | MPM 13-73-01 | Use Permit to establish a new cell tower on Yosemite Commercial site. | Approved by PC 04/09/2013 | Henson
Centerpoint - South | 12-78-04 | Laundry Facility | Approved by PC 04/09/2013 | Henson
Plan-It Cabinets | UPN 13-73-02 | Minor Use Permit to allow cabinet shop at Valley Light Industrial complex. | Approved by FC 04/09/2013 | Henson.
Ernie's Food | MPM-12-57-10 | Addition of outdoor patio | Approved by FC 05/30/2013 | Durrer
Oleander Lot Line Adjustment | 13-47-01 LLA | Lot Line Adjustment to | Approved by FC 06/05/2013 | Meissner
Louise Avenue Widening | NOE | Notice of Exemption for the Louise Avenue Project | Completed | Meissner
T&A Painting Office | SPC-12-59-01 | Site Plan to Convert House on Airport Way to Painting Contractors Office | withdrew application. | Henson
Island Annexation | 12-99-01 ANX & PRZ CITY INITIATED | Woodward Road Island annexation and Prezone. (9 parcels) | withdrew application. | Henson
400 Industrial Park (AKA Indy Building) | 13-39-01 PST | Preliminary Staff Review to determine City requirements for the conversion of the existing building at 400 Industrial Park Drive into self storage units, office, and onsite managers unit. | Staff meeting held 07/22/2013. Significant Code Enforcement issues to resolve. | Durrer
Sunnyvalley Smoked Meats, 2475 W. Yosemite Av. | MPM 13-57-05 | Minor Plan Modification to add a cold storage freezer to the existing processesing plant. | Approved 09/09/2013. | Kang
Fencing and Accessory Structures Standards, Cargo Containers. | N/A | Workshop with Planning Commission to discuss fencing, and accessory structures including cargo containers. | PC conscensus to report to CC to begin enforcement | Meissner
Popeye's | 13-58-01 SPC & UPN | Minor Site Plan and Minor Use Permit for a drive through restaurant at 1401 W. Yosemite Avenue. | FC approved 07/25/2013. | Henson
Austin Road | DA-12-98-01, and SDM-12-77-01 | Phase 1 entitlements including a Large Lot Tentative Parcel Map and Development Agreement | Tentative Parcel Map approved by Planning Commission 07/09/2013. | Henson