CITY OF MANTECA
2012 PUBLIC FACILITIES 
IMPLEMENTATION PLAN UPDATE
[image: image1.jpg]


[image: image3.png]



INITIAL ADMINISTRATIVE DRAFT

December 7, 2012
[image: image2.jpg]BEYOND ENGINEERING




CITY OF MANTECA

2012 PUBLIC FACILITIES 
IMPLEMENTATION PLAN UPDATE
SEALS

INITIAL ADMINISTRATIVE DRAFT

December 7, 2012
Prepared by:
City of Manteca

1001 West Center Street

Manteca, CA 95337

and
Nolte Associates, Inc.
(a subsidiary of NV5, Inc.)
1215 West Center Street, Suite 201

Manteca, CA  95337

(209) 239-9080   •   (209) 239-4166 (fax)
TABLE OF CONTENTS
11.
Introduction and  Executive Summary


1A.
Purpose of the PFIP


1B.
Summary of Fees


42.
Program Methodology


4A.
Impact Fee Model


4B.
Program Goals


4C.
Program Financing


4D.
Facility Implementation


5E.
Program Administration


51.
Payment of Fees


52.
Expenditures and Reimbursements


63.
Fee Adjustments


64.
Program Updates


7F.
Nexus Requirements


7G.
Other Policies


71.
Construction Timing


72.
Out-of-Sequence Construction


73.
Upsizing


84.
Existing Deficiencies


93.
Development Assumptions


9A.
Population


9B.
Land Use Categories and Density Assumptions


11C.
Vacant land Inventory


134.
PFIP Fee Methodology


13A.
Dwelling Unit Equivalent (DUE) Factors


13B.
Cost Estimates


13C.
Mark-up Assumptions


14D.
Land Acquisition Assumptions


14E.
Fee Methodology


14F.
Existing Liabilities


165.
Water


16A.
Background


17B.
Facilities and Costs


171.
Groundwater Supply Facilities


172.
Water Treatment Facilities


173.
Costs


17C.
Dwelling Unit Equivalents


18D.
Fee Methodology


181.
Non-PFIP Fees


182.
PFIP Fees


19E.
Fee Schedule


20F.
Construction Responsibilities


201.
City Responsibilities


202.
Developer Responsibilities


213.
Construction Sequencing


226.
Storm Drainage


22A.
Background


22B.
Facilities and Costs


23C.
Dwelling Unit Equivalents


23D.
Fee Methodology


23E.
Fee Schedule


24F.
Construction Responsibilities


241.
City Responsibilities


252.
Developer Responsibilities


263.
Construction Sequencing


277.
Sewer Collection


27A.
Background


27B.
Facilities and Costs


27C.
Dwelling Unit Equivalents


271.
Residential


282.
Commercial


283.
Industrial


284.
Equivalent Dwelling Units


29D.
Fee Methodology


291.
Non-PFIP and PFIP Fees


302.
Facility Costs


30E.
Fee Schedule


31F.
Construction Responsibilities


311.
City Responsibilities


312.
Developer Responsibilities


313.
Construction Sequencing


328.
Implementation and Administration


32A.
Implementation


32B.
Fee Adjustments


32C.
Fee Program Administrative Requirements


339.
References




APPENDICES
Appendix A
Vacant Land Inventory

Appendix B
Water Data
Appendix C
Storm Drainage Data
Appendix D
Sewer Collection Data
LIST OF TABLES
2Table E-1     Summary of PFIP Water Fees, $/Meter Size


2Table E-2     Summary of PFIP Storm Drainage Fees, $/EDU


3Table E-3     Summary of PFIP Sewer Collection System Fees, $/EDU


12Table 3-1     Summary of Undeveloped Acreage


14Table 4-1     Land Acquisition by Dedication or Purchase


18Table 5-1     Water Meter Hydraulic Capacity/EDU Factors


19Table 5-2     Summary of PFIP Water Fees by Meter Size


19Table 5-3     Summary of Non-PFIP Water Fees by Meter Size


23Table 6-1     Storm Drainage C Factors and EDU Factors


23Table 6-1     Projected Storm Drainage Project Costs by Zone


24Table 6-2     Summary of PFIP Storm Drainage Fees, $/EDU


28Table 7-2     Summary of Wastewater EDU Factors


30Table 7-3     Projected Sewer Project Costs by Zone


31Table 7-4     Summary of PFIP Sewer Collection System Fees, $/EDU




LIST OF PLATES
Plate A-1
Vacant land
Plate B-1
Water Financing Zone

Plate C-1
Storm Drainage Financing Zones

Plate D-1
Wastewater Collection Financing Zones

1. Introduction and 
Executive Summary

The City of Manteca (City) developed the Public Facilities Implementation Plan (PFIP) as the implementing program for specific public infrastructure policies identified in the City of Manteca General Plan 2023 Policy Document (General Plan) [1].  Originally adopted in 1993, the purpose of the PFIP is to ensure that certain public infrastructure needed for growth – namely water, wastewater, storm drainage, and transportation facilities – were adequate as the City grew and developed in accordance with its General Plan.  Another purpose of the PFIP was to ensure that infrastructure was constructed in a timely manner and financed in a way that equitably divided financial responsibility in proportion to the demands placed on the new facilities. 

The PFIP was originally developed as a reimbursement model program that utilized developers’ resources to fund and construct improvements.  Developers were reimbursed either in fee credits or with funds as they were accumulated from the imposed fees.  This method was successful in some aspects, but often required that developers fund substantial improvements with limited assurance of timely repayment.  This situation ultimately presented significant barriers to growth.  

The City desires to update the PFIP such that these barriers are reduced.  To do so, the PFIP will be revised to utilize a development impact fee model wherein the City assumes some responsibility for funding and constructing major facilities, while the developers – in most cases – simply pay their proportionate share to reimburse the City for the cost to finance and construct the infrastructure. 

Only water, storm drainage, and sewer collection facilities and their respective fees are updated in this 2012 Public Facilities Implementation Plan Update (2012 PFIP).  Additional time is needed to prepare the transportation program element due to the complexity of the transportation facilities.  The program and fees for transportation adopted previously remain in effect until updated in the future.

A. Purpose of the PFIP

The City’s purpose of the PFIP is to:

1) Develop impact fees that are cost-competitive within the region.

2) Promote orderly growth in accordance with the General Plan.

3) Develop and maintain an impact fee program that is flexible and responsive to changing market conditions.

B. Summary of Fees

PFIP Water Fees were originally charged on a per unit basis for residential users and on a net acreage basis for other commercial and industrial users.  For the 2012 PFIP, Water Fees are all based on the size of meter installed, regardless of development type, and are consistent throughout the entire City.  PFIP Water Fees are comprised of a Groundwater Supply Fee, a Peaking Facility Fee, and a Distribution System Fee.  Table E-1 summarizes all three fees together.  Chapter 5 provides details on each individual fee.

Table E-1    
Summary of PFIP Water Fees, $/Meter Size
	Meter Size, in
	PFIP Water Fee, $

	5/8
	3,064

	1
	5,117

	1½
	10,204

	2
	16,333

	3
	30,643

	4
	51,082

	6
	102,134

	8
	163,420


PFIP fees for storm drainage are based on the land use type and the zone in which the parcel is located.  This is the same methodology utilized in the original PFIP.  However, for the 2012 PFIP, some of the original zones which are largely built out have been consolidated to simplify accounting and administration.
Table E-2    
Summary of PFIP Residential Storm Drainage Fees 

	
	Fee Per Dwelling Unit, $

	Land Use
	Zone 30
	Zone 32
	Zone 34
	Zone 36
	Zone 39

	VLDR
	108
	1,514
	974
	2,991
	989

	LDR
	43
	606
	390
	1,197
	395

	MDR
	40
	561
	361
	1,108
	366

	HDR
	27
	386
	248
	762
	252


Table E-3    
Summary of PFIP Non-Residential Storm Drainage Fees 

	
	Fee Per Acre, $

	Land Use
	Zone 30
	Zone 32
	Zone 34
	Zone 36
	Zone 39

	AG
	43
	606
	390
	1,197
	395

	BP
	646
	9,085
	5,844
	17,948
	5,931

	CMU
	646
	9,085
	5,844
	17,948
	5,931

	GC
	646
	9,085
	5,844
	17,948
	5,931

	NC
	646
	9,085
	5,844
	17,948
	5,931

	HI
	502
	7,066
	4,546
	13,959
	4,613

	LI
	502
	7,066
	4,546
	13,959
	4,613

	BIP
	502
	7,066
	4,546
	13,959
	4,613


PFIP Sewer Fees recover the cost of providing the collection system to convey sewer generated in the City to the City’s treatment plant.  The original PFIP broke the City into five financing zones, and charged per unit for residential users and per 1,000 square feet (sf) for non-residential users.  In addition, some infrastructure that was amended into the PFIP was charged as a separate overlaying zone.  In the 2012 PFIP, some of these financing zones have been consolidated.  In addition, the basis for sewer fees has been changed.  The 2012 PFIP will charge per unit for residential users but non-residential users will be charged upon usage , which will be estimated based on each development’s characteristics.  This is expected to more accurately relate the cost of infrastructure to the actual demand.

Table E-4    
Summary of PFIP Residential Sewer Collection System Fees
	Land Use
	Fee Per Dwelling Unit, $

	
	Zone 21
	Zone 22
	Zone 24
	Zone 25
	Zone 26

	VLDR
	752
	2,232
	1,809
	785
	1,568

	LDR
	752
	2,232
	1,809
	785
	1,568

	MDR
	550
	1,632
	1,323
	574
	1,146

	HDR
	550
	1,632
	1,323
	574
	1,146


Table E-5    
Summary of PFIP Non-Residential Sewer Collection System Fees

	Land Use
	$ per Gallon per Day

	
	Zone 21
	Zone 22
	Zone 24
	Zone 25
	Zone 26

	All Non-Residential
	4.70
	13.95
	11.31
	4.91
	9.80


2. Program Methodology
C. Impact Fee Model

The PFIP has been revised to use a development impact fee model approach wherein the City assumes some responsibility of funding and constructing major facilities, while the developers – in most cases – simply pay their proportionate share to reimburse the City for the cost to finance and construct the infrastructure.
D. Program Goals

The City’s primary goals for the PFIP programs are to:

1) Develop impact fees that are cost-competitive within the region.
2) Promote orderly growth in accordance with the General Plan.
3) Develop and maintain an impact fee program that is flexible and responsive to changing market conditions.
Deleted text regarding flexibility
E. Program Financing 

Development impact fees are one source of financing that is within the control of the City to provide facilities to serve new development.  The City also intends to participate aggressively in Regional, State, and Federal programs that may become available to finance public improvements.  However, the City is not prepared to depend on these sources to pay for public improvement projects that are essential to growth and development.  Thus to fund the required infrastructure, the City may utilize other sources.
F. Facility Implementation

The sequence of implementing projects for increased capacity and expanded public water, sewer, and storm improvements in the City is as follows:

· General Plan and accompanying growth management policies and ordinances are adopted.

· Facilities master plans are prepared or updated and conceptual engineering is developed to identify the new facilities/capacity that will be needed to serve the expected growth.

· These new facilities are then programmed into the City’s Capital Improvement Program (CIP), which is updated annually and approved by the City Council at time of fiscal year budget adoption.

G. Program Administration

1. Payment of Fees

Payment of PFIP fees is due at the time of issuance of building permit.  Payment of PFIP fees at occupancy of a residential or commercial facility is allowed only with City Council approval.
Fees are collected by the Community Development Department.  An individual acting under the supervision of the Chief Building Inspector accomplishes all of the following:

· Classifies the building permit application in terms of the development impact fee zone or zones that are applicable.

· Selects the development impact fee rates that are applicable.

· Calculates the total development impact fee that is due with the building permit application.

· Collects the land use description and other data for this particular application to monitor land use data within the City.

· Transmits the fee information to the Finance Department for appropriate accounting.

Receipts and disbursements of the proceeds of development impact fees are managed in accordance with the normal system of accounting and financial controls.  In addition, the Community Development Director or his/her designee has a responsibility to verify that the appropriate development impact fee account has been identified when funds for each construction project in the PFIP are encumbered.  This review responsibility is particularly important in those instances where fees at different levels are collected in different geographic financing zones.  Accounts are maintained contemporaneously on a transaction-by-transaction basis to assure that a proper accounting can be made and that there is a visible, understandable audit trail for the use of all development impact fees.  

2. Expenditures and Reimbursements

Funds will be used to pay PFIP costs in the following priority:

1. City administration costs

2. New capital projects

3. Repayment of existing liabilities

To insure that the program has sufficient funds to be maintained appropriately, each fund will maintain a minimum balance of $200,000.  No expenditures will be made or programed when the fund balance is below that amount.  Costs of City administration for the program will be deducted from the funds annually.  Project-specific costs will be charged to the individual projects, which are programed and budgeted in the CIP.

When funds exceed the reserve amount, priority will be given to capital projects needed to provide facilities included in the master plans and CIP.

If no projects are currently planned, any funding in excess of the designated reserves shall be used to repay existing liabilities.  Reimbursement shall be prioritized based upon: 1) date of acceptance, 2) inter-fund debt and 3) other developer liabilities.

Reimbursement for improvements will be limited to the amount programed within the PFIP at the time the project is constructed.
3. Fee Adjustments

The City will review the PFIP and each development impact fee resolution annually.  Any material change in development impact fees as a result of the monitoring and review of the program would be implemented as soon as feasible.  The PFIP is subject to revision due to several factors.  These factors include the difficulty of forecasting the rate and location of development in the City, variations in the cost of construction of public improvements, and variation in the standards that may be applicable in the future to the design of public improvements.  

Annual fee and reimbursement rate adjustments will be calculated in November of each year and will take effect in January of the following year for every year.  The automatic inflation adjustment to the fees will be based upon the preceding July 20-Cities Engineering News Record Construction Cost Index (ENRCCI).  Should the ENRCCI be revised or discontinued, the Director of Finance will use the revised index or a comparable index, as approved by the City Council, for determining fluctuations in the cost of development.  The statute requires 60 days after adoption before fees become effective.  Therefore, staff will need to process fee increases as early as possible to ensure new fees will be effective the following year. 

4. Program Updates 

The City intends to assure that the General Plan and the various master plans remain responsive to City policy and changing development conditions.  The City intends to review both the General Plan and the facility master plans on a ten-year cycle.  Policies in an amended General Plan will be incorporated into all of the City facilities master plans and into each impact fee Ordinance and Resolution.  At the same time, a forecast of growth and development for an additional five years will be added to the planning period for each master plan document.

Information about changes in the availability of Regional/State/Federal grants (principal forgiveness) and loans or other sources of revenue will be incorporated into the fee programs during the annual review.
H. Nexus Requirements

The PFIP incorporates Capital Improvement Programs (CIPs) and/or utilities master plans for water, sewer, and storm drainage as defined in Government Code §66002.  The basis for determination of costs and fees that are provided in this document are based, in part, upon findings and conclusions provided in the utilities master plans.  This PFIP document and the various utility master plans jointly identify the use to which the fee will be put and determine the reasonable relationship between a benefit, the fee’s use, and the type of development project on which the fee is imposed.  

I. Other Policies

5. Construction Timing
Facilities will be constructed as demand occurs and are not rigidly tied to the calendar.  Thus, growth forecasts are not needed nor used in the PFIP.  Accordingly, the timing of facility construction in this program is self-correcting in that:

· A slowdown in development produces a slower rate at which additional capacity will be demanded, as well as a slower rate at which development impact fees will be collected.  Consequently, the construction of facilities would slow down.

· As development increases, then development impact fees will be available sooner to construct improvements for which demand has occurred sooner than expected.  An excessive rate of development that is beyond that which could be accommodated because of lead time required to construct projects is unlikely because at some point, the limitations in the City Growth Management Ordinance would become effective.

6. Out-of-Sequence Construction

In some cases, development projects maybe proposed that are not proximate to existing infrastructure.  In such cases, developers may advance the construction of needed PFIP infrastructure at their cost.  Infrastructure included in the PFIP that is installed by developers will be eligible for reimbursement as outlined in Section 2 above.  
7. Upsizing 

Sewer facilities are sized to provide adequate capacity for each of the zones. The facilities will efficiently serve development beyond 2023.  Financing for oversizing will not be paid from the current development impact fees.  At such time as development uses the excess capacity, the costs of that capacity will be brought into the impact fee.  As funds are collected for those facilities, the initial source of funds may be reimbursed. 

8. Existing Deficiencies

If a facility improvement will remedy an existing deficiency and provide new capacity, then the cost of that facility will be allocated between new development and other financing sources as follows:

· The least-costly improvement to remedy the existing deficiency, in the absence of further growth, is identified.  This cost is assumed to be the responsibility of existing funding sources and is not financed from development impact fees.  The least costly improvement must be feasible and realistic. 

· The cost to provide capacity for additional growth (i.e., the difference between the full cost of the improvement and the cost of the least costly improvement to remedy existing deficiencies) is financed from development impact fees.
3. Development Assumptions

J. Population

Since incorporating in 1918, Manteca has been a rapidly growing city. The City experienced its highest average annual growth rate (AAGR) between 1950 and 1960 when the population grew at an AAGR of 8.04 percent. The population continued to grow at an average rate between 5 and 6 percent over the following decades (1960 to 1990) [2].  The population growth slowed slightly between 1990 and 2000, and then increased through 

.  With the recent economic downturn, population growth again slowed; but unlike other communities in the area, development in the City continued at a greater rate than surrounding cities.  As of 

 the City has a population of 

. 

The total land use proposed in the City General Plan will accommodate a population of 94,000 to 144,000[2].  This projection is derived through assumptions relating to residential density, the average density, the efficiency of the land use, vacancy factors, and a market reserve for each residential land use type.  
Through the Growth Management Ordinance (Chapter 18.04 of the City Municipal Code) the City regulates the number of housing units approved each year according to a growth management system that reflects the availability of infrastructure, the City’s ability to provide public services, housing needs, and employment growth.  The Growth Management Ordinance limits population growth to 3.9 percent and development allocations are determined on a point rating system.

K. Land Use Categories and Density Assumptions

The land use categories are tailored to meet the specific needs of the City. Economic development opportunities, housing needs, and environmental characteristics are among the factors that determine the appropriate land use categories. The land use categories are implemented through the Manteca Municipal Code, Zoning Ordinance.
The following are abbreviated descriptions of the various land use categories and include a description of the density assumption for each category along with the floor area ratio (FAR) as outlined in the General Plan.  In case of conflict, the descriptions contained in the adopted General Plan shall prevail.
Very Low Density Residential (VLDR) – less than 2 dwelling units per gross acre. The VLDR land use category provides for residences on larger lots and small, quasi-agricultural activities, including raising and boarding livestock. 
Low Density Residential (LDR) – 2.1 to 8.0 dwelling units per gross acre.  The LDR land use will establish a mix of dwelling unit types and character determined by the individual site and market conditions. The density range allows substantial flexibility in selecting dwelling unit types and parcel configurations to suit particular site conditions and housing needs. 
Medium Density Residential (MDR) – 8.1 to 15 dwelling units per gross acre.  The MDR use includes single family homes, smaller scale multi-family developments, including garden apartments, townhouses, and cluster housing. 
High Density Residential (HDR) – 15.1 to 25 dwelling units per acre.  The HDR use includes multi-family apartment style housing. 

Commercial Mixed Use (CMU) – 15.1 to 25 dwelling units per acre; FAR 1.0; maximum site coverage 50%.  The CMU designation accommodates a variety of purposes including high density residential, employment centers, retail commercial, and professional offices.  The mixed use concept would integrate a mix of compatible uses on a single site.
Business Industrial Park (BIP) – FAR 1.0; maximum site coverage 50%.  The BIP designation is intended to provide sites for large uses in an office park environment that would include multi-tenant buildings. 
Business Professional (BP) – FAR 1.5; maximum site coverage 50%.  The BP land use is intended primarily for office and related uses in a landscaped site. The use category is specifically intended for the frontage along State Route (SR) 120 and along other major roads and in the Central Business District (CBD).  This designation provides for professional and administrative offices, medical and dental clinics, laboratories, financial institutions, public and quasi-public uses, and similar and compatible uses.
Neighborhood Commercial (NC) – FAR 2.0 in the CBD and 0.6 outside the CBD. 
This designation provides for locally oriented retail and service uses; offices, restaurants, and service stations; public and quasi-public uses; and similar and compatible uses.
General Commercial (GC) – FAR 0.6; maximum site coverage 40%.  The GC category provides for wholesale, warehousing, and heavy commercial uses; highway oriented commercial retail; public and quasi-public uses; and similar and compatible uses. The designation is also intended to accommodate visitor commercial, lodging, commercial recreation and public gathering facilities, such as amphitheaters, or public gardens.
Light Industrial (LI) – FAR 0.7; maximum site coverage 60%.  The LI designation provides for industrial parks, warehouses, distribution centers, light manufacturing, public and quasi-public uses and similar and compatible uses.
Heavy Industrial (HI) – FAR 0.5; maximum site coverage 40%.  The HI designation provides for manufacturing, processing, assembling, research, wholesale, and storage uses; trucking terminals, railroad and freight stations; and similar activities that require separation from residential uses due to noise, vibration, or other characteristics incompatible with residential use.
Agriculture (AG) – The AG designation provides for agricultural uses (such as vineyards, orchards, and row crops), single family homes directly related to the agricultural use of the property, limited industrial uses directly related to agriculture, and similar and compatible uses.
Open Space (OS) – The OS category encompasses habitat, open space, natural areas, lands of special status species, wetlands, and riparian areas. These areas are set aside as permanent open space preserves to protect environmentally sensitive areas.
Park (P) – This designation provides for neighborhood, community, and regional parks; golf courses; and other outdoor recreational facilities within urban development. 
Public/Quasi-Public (P/QP) – This designation provides for government-owned facilities, public and private schools, institutions, civic uses and public utilities, and quasi-public uses such as hospitals and churches.
Urban Reserve (UR) – UR is applied to many properties around the perimeter of the City. In most instances the UR category overlies another land use category. In these instances the underlying land use is the intended use when the land is ultimately annexed to the City. UR with no underlying land use indicates that the City intends to expand in the time horizon beyond the current General Plan and that it is premature to indicate a specific future land use in this area. 
Floor Area Ratio (FAR):  ratio of building square footage to the site area.

L. Vacant land Inventory

The City calculated the amount of vacant land remaining within the General Plan boundary and the results are summarized in Table 3-1.  Plate A-1 in Appendix A provides a graphic depiction. 
Table 3-1    
Summary of Undeveloped Acreage
within the City of Manteca

	Land Use Type
	Undeveloped
Acreage

	AG
	3,688.21

	BIP
	179.98

	BP
	1.00

	CMU
	318.69

	GC
	464.12

	HDR
	147.57

	HI
	738.92

	LDR
	3,674.98

	LI
	750.38

	MDR
	237.56

	NC
	56.10

	OS
	444.35

	P
	161.23

	PQP
	242.22

	UR
	1,709.09

	UR-AG
	1,611.85

	UR-BIP
	408.70

	UR-CMU
	435.63

	UR-GC
	40.43

	UR-LDR
	1,381.35

	UR-LI
	114.45

	UR-MDR
	19.74

	UR-P
	67.52

	UR-PQP
	11.65

	UR-VLDR
	627.30

	VLDR
	659.53

	Total
	18,192.57


4. PFIP Fee Methodology

M. Dwelling Unit Equivalent (DUE) Factors

DUEs are units of measure that standardize land use categories (residential, commercial, industrial, etc.).  A low-density, single-family residential unit has a DUE factor of 1.0.  The DUE factor for other land use types is developed based on the anticipated demand for each land use category relative to the demand for a low-density, single-family residential unit.
DUEs are commonly utilized to calculate the probable demand that a user places on facilities by assignment of an equivalency factor.  DUEs are measured differently for each component in the PFIP.  The term DUE may be used interchangeably with EDU, equivalent dwelling unit.
N. Cost Estimates

The facility master plans identify the public facilities to serve the forecasted development.  Results of the master plan studies specify the sizes of facilities to serve the demand and represent a preliminary design level of accuracy.  Opinions of probable construction cost are conceptual and are based upon information available at the time of preparation.  

Appurtenant facilities have been accounted for within the unit prices.  Opinions of probable cost are based upon current cost data for similar construction in the region, contractors, and suppliers.  Opinions of cost are referenced to one ENRCCI (need index number) as of 

, 2012.  Costs will be adjusted for inflation based on changes in the ENRCCI.
Estimates of environmental review cost have been included in the cost of administering the PFIP.
O. Mark-up Assumptions

Contingency factors have been applied to the opinions of probable construction cost.  They represent a combination of factors allowing for additional costs associated with unknown site conditions, extra quantities of materials, etc.  Ancillary project costs are:

Design engineering
10%

Construction management, surveying, and inspection
7%

Plan check
2%

Design services would typically include preliminary studies; plans, specifications, and estimates; and construction consultation.  Based on industry accepted standards of practice and cost estimating guides, these percentages are reasonable for the type and magnitude of projects in the PFIP and are consistent with engineering practice.

P. Land Acquisition Assumptions

For the purposes of preparing the financial plan, land will be assumed to be either dedicated or purchased in accordance with Table 4-1.  Generally, the land for any facility that serves an area‑wide purpose will be purchased.  

Table 4-1    
Land Acquisition by Dedication or Purchase

	Infrastructure Category
	Facilities for Which 
Lands are to be Dedicated
	Facilities for Which 
Lands are to be Purchased

	Water
	· Pipelines 
· Well sites

· Storage tank sites
	· Treatment plant

	Storm Drainage
	· Detention basins serving individual and combined projects

· Easements serving individual projects

· Pipelines

· Canals serving individual projects
	

	Sewer
	· Pipelines

· Trunks
· Lift stations
	· Treatment plant and disposal areas



Q. Fee Methodology

Development impact fees are the primary source of financing that is within the control of the City to provide facilities to serve new development.  When needed, the City may pursue other funding options including private and public funding programs.  However, to fund the required infrastructure, the City plans to utilize the following sources: 

· Development Impact Fees paid pursuant to the PFIP will be used to finance the expansion of facilities that are necessary to accommodate the demand for new capacity.  

· Inter-Account Borrowing, such as borrowing between PFIP accounts when practical or employing other comparable devices, may be used if development impact fees, considered alone, are insufficient to build public improvements when required. 

· Outside Financing, such as bonds or other public financing instruments may be utilized to fund larger facilities in advance of the fees that will retire any such accumulated debt. Any such funding will require participation by the specific beneficiaries in the form of land or other source of security to insure repayment. 

R. Existing Liabilities

As a result of development activity over the years, the various PFIP funds have accumulated cash balances, inter-fund borrowing obligations, and other liabilities. The PFIP fund balances as of July 1, 2012, will be used as the starting point for each zone’s initial fund balance and initial obligations. The cash balances carried over into the PFIP will be used for PFIP projects, and the obligations (liabilities) carried over into the PFIP will be retired from future fee collections under the program.
5. Water

This chapter provides PFIP information as it pertains to the City water system.  A summary of the information is as follows: 1) background; 2) facilities and costs; 3) dwelling unit equivalents; 4) fee methodology; 5) fee schedule; and 6) construction responsibilities.
S. Background

The City of Manteca 2005 Water Master Plan (2005 WMP) presents the results of an evaluation of the water supply and distribution system.  The planning document provides a tool for addressing changing regulations, aging infrastructure, and anticipated growth in planning future improvements to its water system through the year 2035.  The purpose of the 2005 WMP is to provide a comprehensive planning document to guide improvement and expansion of the City water system to meet current and future needs for a safe, reliable water supply and distribution system.  

Key objectives of the 2005 WMP affecting future development projects include the following:

· Provide a strategic approach to comply with the new maximum contaminant level (MCL) for arsenic, which took effect in January 2006, through the addition of a combination of treatment and storage facilities.

· Evaluate alternatives and plan water system improvements to facilitate delivery of the South San Joaquin Irrigation District (SSJID) surface water supply.  Alternatives addressed a groundwater supply and storage plan to meet a conjunctive groundwater/ surface water use approach by the City without exceeding the aquifer’s safe yield.

· Update the City’s existing water distribution system hydraulic model and conduct hydraulic modeling to determine distribution system expansion requirements.

· Prepare a CIP for the water system that identifies projects for completion by the City.  This CIP included improvements needed for the existing system (funded by ratepayers) and growth driven improvements funded by this program.

The 2005 WMP reviews water demand required to provide for the 2023 General Plan lands within the Primary Urban Service Area (PUSA) through build out.  Historically, the City has utilized separate planning documents for Zone 11 (2002 Water Master Plan) and Zone 12 (1993 PFIP) to define the required capital improvements.  The earlier area contained in Zone 11 included the existing developed portions of Manteca with growth generally limited to infill development and redevelopment.  The earlier area contained in Zone 12 included the lightly developed lands that could be characterized as agricultural areas with significant urban development potential.  However, because the City water system operates as a single system, the City uses one planning document for all areas, which have been merged into a single zone designated as Zone 12. See Plate B-1 in Appendix B for a depiction of Zone 12. 

T. Facilities and Costs
New water supply comes from groundwater and surface water.  Groundwater supply is limited to safe yield limits and surface water supply is limited to capacity available at the South San Joaquin Irrigation District (SSJID) water plant.  Service is provided by a network of water wells, storage tanks, and distribution pipelines.  The water system for current and future users will be operated as a single pressure zone.

9. Groundwater Supply Facilities
New wells will be located as needed to supplement existing groundwater and surface water supplies, optimize distribution, and maintain minimum pressures during peak conditions throughout the system.

10. Water Treatment Facilities
With the increase in regulations, treatment of groundwater has become a standard expense, even on newer wells.  The City anticipates having to provide treatment for a significant portion of new wells.  Currently the City provides treatment on 76 percent of the City wells for arsenic, volatile organic compounds, or other constituents.  The hope or expectation that new wells would require less treatment is offset by the potential for additional regulation that could increase water treatment requirements.  Hence, for planning purposes, the PFIP anticipates funding treatment at the same ratio.

11. Costs

Costs for major water infrastructure (wells and tanks) are based upon the capacity provided by each water facility, the users’ anticipated demand determined by the size of meter, and current engineer’s opinion of probable costs.  The need for water mains is based upon the pipe system outlined in the 2005 WMP and updated as needed to serve the areas included in the City General Plan.  

U. Dwelling Unit Equivalents

All PFIP water fees will be charged based upon the meter size installed.  A 5/8-inch water meter is the standard meter for a single family residence or single equivalent dwelling unit (EDU) and is considered an EDU factor of 1.0.  Larger meters and their respective hydraulic capacity/EDU factor are shown in Table 5-1.
Table 5-1    
Water Meter Hydraulic Capacity/EDU Factors

	Meter Size, in
	Hydraulic Capacity/ EDU Factor

	5/8
	1.00

	1
	1.67

	1½ 
	3.33

	2
	5.33

	3
	10.00

	4
	16.67

	6
	33.33

	8
	53.33


V. Fee Methodology

The City has established a fee structure that allocates costs to construct water infrastructure related to new development.  There are two types of fees assessed, non-PFIP fees which have been adopted by separate City resolutions, and PFIP fees which are adopted by this document.  Brief descriptions of what are included in the fees are provided.  Descriptions of the non-PFIP fees are provided for informational purposes only.  Because these fees are adopted by separate City resolution, policies related to these fees including fee adjustments are identified in other City documents.

12. Non-PFIP Fees

Meter Installation Fee:  The Meter Installation Fee recovers the City’s cost to install new water meters.  The fee includes the cost of the meter, meter box, pipe fittings, labor, and equipment charges.

Surface Water Debt Fee:  The Surface Water Debt Fee is development’s proportionate share of the capitalized costs of the surface water treatment system and transmission system.  

Surface Water Capital Fee:  The Surface Water Capital Fee is development’s proportionate share of ongoing capital improvement projects to improve, upgrade, and rehabilitate the surface water treatment system and transmission system.

13. PFIP Fees

Groundwater Supply Fee:  The Groundwater Supply Fee recovers the cost of new well construction required to supply water to new development.  The costs include: environmental fees; test wells; well drilling, casing and development; consulting services; electrical service charges; and water treatment systems.

Peaking Facility Fee:  The Peaking Facility Fee recovers the cost to construct water storage and booster pumping facilities to provide peaking demand and fire flows for new development.  The costs include: environmental fees; site acquisition; consulting services; electrical service charges; and construction of tanks and booster pumping facilities. 

Distribution System Fee:  The Distribution System Fee will reimburse developers for the cost of oversizing public water mains installed in the public right of way.
W. Fee Schedule 
The PFIP fees described above combine to establish the PFIP Water Fee. Table 5-2 summarizes the fees by meter size.  The tables in Appendix B identify the costs and calculations associated with the PFIP fees. 
Table 5-2    
Summary of PFIP Water Fees by Meter Size
	Meter Size, in
	Groundwater Supply Fee, $
	Peaking Facility Fee, $
	Distribution System Fee, $
	PFIP Water Fee, $

	5/8
	1,021
	1,571
	473
	3,064

	1
	1,705
	2,623
	789
	5,117

	1½
	3,400
	5,230
	1,574
	10,204

	2
	5,442
	8,372
	2,519
	16,333

	3
	10,210
	15,707
	4,726
	30,643

	4
	17,021
	26,183
	7,879
	51,082

	6
	34,031
	52,350
	15,753
	102,134

	8
	54,452
	83,763
	25,206
	163,420


For informational purposes only, Table 5-3 provides a summary of the current non-PFIP fees by meter size.

Table 5-3    
Summary of Non-PFIP Water Fees by Meter Size
	Meter Size, in
	Non-PFIP Fees, $

	5/8
	3,563

	1
	5,885

	1½
	11,647

	2
	18,381

	3
	36,482

	4
	59,312

	6
	121,919

	8
	191,550


X. Construction Responsibilities
The City and developer have responsibilities for construction of water facilities as follows:

14. City Responsibilities 
The City will construct all wells and storage tanks.  The City may also install some water transmission and/or distribution mains needed for looping or redundancy.
15. Developer Responsibilities 
The developer will be responsible for construction of the distribution system and dedication of well and tank sites as described below.
a) Distribution System

Water mains will be installed by developers as outlined in the 2005 WMP on a typical one-half mile grid spacing.  All development projects that construct streets on this grid will be responsible for installing a minimum 12-inch water main with associated appurtenances (valves, hydrants, etc.).  

Developers that install water mains on the main grid and/or oversize water mains on the interior grid may be entitled to reimbursement at the rate provided in Appendix B.
Reimbursements are contingent on the availability of funds for such purpose, based on order of project acceptance by the City in the following order of priority: 

· All water mains on the one-mile grid or “Main Grid” will be subject to reimbursement for oversizing for the amount per foot shown in Table B-7 in Appendix B. 

· Larger water mains (16-inch to 18-inch diameter) shall be installed at locations on the Main Grid as needed to provide efficient movement and distribution of water through the City system and will be subject to reimbursement for the amount per foot shown in Table B-7 in Appendix B.  Actual location of large mains shall be as directed by the City. 

· All in-tract water mains on the “Interior Grid,” which are spaced roughly on the half mile grid, shall be 12-inch diameter and will be reimbursed based upon the “oversizing” of water mains from an 8-inch to 12-inch. 

b) Well and Tank Sites
To provide sufficient opportunity for placement of productive groundwater facilities or wells, the City will require the dedication of a suitable well site within every quarter section.  All projects that include the development of more than 80 acres within any given quarter section shall offer for dedication a suitable well site for exclusive use of the installation of a water well and any needed treatment facilities.

Prior to the dedication of the well site, the developer shall provide access and permission to the City to complete an exploratory well or test well.  If the test well is successful, the offer of dedication will be accepted.  If the test well is not successful, the developer shall provide an alternate site at an agreed upon location for a second test well.

A suitable well site shall be at least 5,000 sf and shall be fenced appropriately.  

Developers that dedicate a well site may be entitled to a reduction in the Groundwater Supply Fee.  Should the cost of the dedicated site exceed the Groundwater Supply Fee obligation, the City will enter into an agreement with the developer to reimburse the developer for the cost of the dedicated site, including an amount attributable to interest.  The fee reduction and/or reimbursement amount for the well site is provided in Appendix B.  Reimbursements are contingent on the availability of funds for such purpose.  Funding for well site reimbursement will come solely from the Groundwater Supply Fee Fund.

Tank sites will be dedicated as needed to support development.    Developers that dedicate tank sites may be entitled to a reduction in the amount of the Peaking Facility Fee.  Should the cost of the dedicated site exceed the Peaking Facility Fee obligation, the City will enter into an agreement with the developer to reimburse the developer for the cost of the dedicated site, including an amount attributable to interest.  The fee reduction and/or reimbursement amount for the tank site is provided in Appendix B.  Reimbursements are contingent on the availability of funds for such purpose.
Reimbursement for dedicated tank sites will only be made after the tanks are installed and functional.  Other tank sites may be acquired by the City or may be a consideration of project approval.   Funding for tank site reimbursement will come solely from the Peaking Facility Fee Fund.

All well and tank sites shall be as approved by the Director of Public Works and may be combined with other public facility sites such as parks or landscape strips where feasible.

16. Construction Sequencing 

While pressurized systems can be installed virtually anywhere, the City generally plans to install new supply and peaking facilities in a concentric manner starting at the perimeter of the existing water system.  This is to provide for redundancy and to ensure that fire flow demands are met for additions to the water system.
6. Storm Drainage
This chapter provides PFIP information as it pertains to the City storm drainage system.  A summary of the information is as follows: 1) background; 2) facilities and costs; 3) dwelling unit equivalents; 4) fee methodology; 5) fee schedule; and 6) construction responsibilities.

Y. Background

The Storm Drain Master Plan 2012 (2012 SDMP) provides a comprehensive planning document to guide improvement and expansion of the City’s storm drainage system to meet current and future needs in a safe and reliable manner while maintaining compliance will all applicable regulations.

Key objectives of the 2012 SDMP affecting future development include the following:

· Compliance with the provisions of the SSJID/City Master Drainage Agreement.

· Compliance with stormwater quality provisions in the State Water Resources Control Board’s stormwater NPDES permit for Phase II cities. 

· Adherence to the drainage methodology.

The 2012 SDMP evaluates drainage from the 2023 General Plan lands within the PUSA through build out.  Five planning zones have been identified to define the capital improvements needed to serve future growth:  Zones 30, 32, 34, 36 and 39.  With the exception of drainage Zone 39, all drainage zones are located in the SSJID service area.  See Plate C-1 in Appendix C for a depiction of the drainage zones.  

Z. Facilities and Costs

Stormwater control is essential to protect the City from flooding during storm events.  This protection is provided through a series of storm drains, detention basins, and pumping facilities.   For zones within the SSJID service area, the City has an agreement with SSJID to allow discharge into the SSJID facilities.  SSJID facilities then convey the runoff to the San Joaquin River.  While areas of the City currently are allowed to have direct discharge to SSJID facilities, new development cannot discharge direct to the SSJID facilities and attenuation facilities must be installed to control the runoff.  For development in Zone 39, which is outside the SSJID service area, separate facilities will be constructed to convey the runoff to one regional pump station that will discharge into Walthall Slough.
Development is required to install attenuation facilities for control of storm runoff within their area of influence.  Through the collection of PFIP fees, the City will construct the necessary pipelines and pump stations to convey stormwater to the appropriate discharge points.
The total storm drainage CIP construction cost is approximately $17,530,000 of which $2,612,500 is the responsibility of SSJID and not included in the PFIP fee calculation.
AA. Dwelling Unit Equivalents

Allocation of costs is based on run-off coefficients (“C” factor).  Table 6-1 provides a summary of the C factor and EDU factor by land use type.
Table 6-1    
Storm Drainage C Factors and EDU Factors

	Land Use
	C Factor per EDU
	EDU Factor 

	VLDR
	0.1500
	2.50

	LDR
	0.0600
	1.00

	MDR
	0.0556
	0.93

	HDR
	0.0382
	0.64

	AG
	0.0600
	1.00

	BP
	0.9000
	15.00

	CMU
	0.9000
	15.00

	GC
	0.9000
	15.00

	NC
	0.9000
	15.00

	HI
	0.7000
	11.67

	LI
	0.7000
	11.67

	BIP
	0.7000
	11.67


AB. Fee Methodology

Allocation of costs is based on run-off coefficients utilized per land use.
AC. Fee Schedule

The costs of facilities and the division of construction costs among the fee zones are summarized in Table 6-1.  Table C-X in Appendix C provides a breakdown of the projects and an allocation of projects costs to the individual zones. 
Table 6-2    
Projected Storm Drainage Project Costs by Zone
	Parameter
	Cost, $

	Zone 30
	288,984

	Zone 32
	2,159,860

	Zone 34
	1,465,928

	Zone 36
	9,462,538

	Zone 39
	1,540,000

	SSJID Costsa
	2,612,500

	Total Project Costs
	17,529,810


a Portion of project costs to be paid by SSJID based on the SSJID/City drainage agreement.
The PFIP Storm Drainage Fees are provided in Table 6‑2 for residential land uses and Table 6‑3 for non-residential land uses.
Table 6-3    
Summary of PFIP Residential Storm Drainage Fees 

	
	Fee Per Dwelling Unit, $

	Land Use
	Zone 30
	Zone 32
	Zone 34
	Zone 36
	Zone 39

	VLDR
	108
	1,514
	974
	2,991
	989

	LDR
	43
	606
	390
	1,197
	395

	MDR
	40
	561
	361
	1,108
	366

	HDR
	27
	386
	248
	762
	252


Table 6-4    
Summary of PFIP Non-Residential Storm Drainage Fees 

	
	Fee Per Acre, $

	Land Use
	Zone 30
	Zone 32
	Zone 34
	Zone 36
	Zone 39

	AG
	43
	606
	390
	1,197
	395

	BP
	646
	9,085
	5,844
	17,948
	5,931

	CMU
	646
	9,085
	5,844
	17,948
	5,931

	GC
	646
	9,085
	5,844
	17,948
	5,931

	NC
	646
	9,085
	5,844
	17,948
	5,931

	HI
	502
	7,066
	4,546
	13,959
	4,613

	LI
	502
	7,066
	4,546
	13,959
	4,613

	BIP
	502
	7,066
	4,546
	13,959
	4,613


AD. Construction Responsibilities
The City and developer have responsibilities for construction of storm drainage facilities as follows:

17. City Responsibilities 
SSJID Drain Improvements:  Per the 2012 SDMP, the City will construct a new pipeline to increase the capacity of Drain 5 to accommodate future flows.  The Drain 5 improvement costs are included in the Zone 34 PFIP fee structure.

Zone 32 Conveyance Improvements:  The City will construct a new pipeline to connect Lateral Rga to Drain 3 per the 2012 SDMP.  The cost of this connector pipe is included in the Zone 32 PFIP fee structure.
Zone 36 Improvements:  The City will construct a drainage pipeline in Woodward Avenue – known as the South Drain – to serve as the main stormwater conveyance facility for Zone 36.  The City will also construct a pump station and force main – called the South Drain Pump Station and Force Main – to convey storm water from the South Drain Pipeline to the French Camp Outlet Canal (FCOC).  In addition, the City will construct several junction structures to divert water from the dual use laterals to the South Drain.  The cost of the South Drain, South Drain Pump Station and Force Main, and the junction structures are included in the Zone 36 PFIP fee structure.  

Water Level Monitoring Stations:  The City will construct water level monitoring facilities in the various PFIP zones and in the FCOC to monitor water elevations in real-time to prevent flooding caused by additional drainage flows.  Each zone’s proportionate share of the water level monitoring stations is included the various PFIP zone fees. 

FCOC Culvert Crossing Improvements:  As identified in the 2012 SDMP, several existing culvert crossings in the FCOC need improvement to accommodate additional drainage flows.  The existing SSJID/City drainage agreement contains cost-sharing provisions regarding these culvert crossing improvements wherein both parties share equally in the costs.  The City or SSJID will construct the culvert crossing improvements, and the City’s 50 percent cost share for all FCOC improvements needed for growth is included in the PFIP fee structure.  The FCOC culvert crossing improvement costs are spread proportionately among the PFIP zones based upon the contribution of each zone.   

18. Developer Responsibilities 
Local Drainage Management Facilities:  Developers will install, at their expense, local drainage collection, attenuation, pumping, and conveyance facilities necessary to serve their development.  This includes facilities needed to convey stormwater from development projects to the nearest SSJID dual-use lateral.  It is also the responsibility of the developer to collect and convey drainage from arterial streets adjacent to their projects to the local attenuation facility.

While the City encourages regionalization of attenuation facilities, this effort is left to the developers to make arrangements amongst themselves.  Should developers reach an arrangement for a regional attenuation facility, the City will support this effort by establishing and administering an area of benefit (AOB) for the regional facility.  Costs for local collection facilities and local/regional attenuation facilities are not included in the PFIP program.  

SSJID Lateral Improvements:  SSJID laterals will be used to convey stormwater from the local/regional attenuation facilities to SSJID drains or the South Drain.  While laterals are important conveyance facilities, all costs to replace and/or upsize the existing laterals are not included in the PFIP for the reasons described below.

SSJID laterals are found throughout the existing and undeveloped areas of the City; and virtually all existing laterals in the PFIP planning area are 42-inch diameter in size, which is the size needed to convey build-out storm flows at the 96-hour drainage rate.  Also, SSJID requires new development projects that disturb their laterals to remove, realign, and replace the laterals, at the developer’s expense, with at least the same diameter pipe as the existing lateral.  Moreover, SSJID requires an increase in pipe diameter to the next standard pipe size (or more) to account for additional headloss created by any pipeline realignments.  Because these are SSJID requirements, there are no replacement and/or upsizing costs in the PFIP.    
The City does acknowledge the possibility that an existing SSJID lateral in the PFIP planning area may be less than 42-inch diameter.  In the event that a lateral is found to be less than 42‑inch diameter and should SSJID not require the replacement pipe to be at least a 42-inch pipe, the City will require the developer to upsize the pipe to 42-inch diameter.  Should this situation occur, the developer will be reimbursed the incremental cost increase of a 42-inch pipe per the reimbursement policies in Chapter 2

Zone 39 Improvements:  Zone 39 is outside of the SSJID service area, and therefore SSJID facilities cannot be used to convey runoff from this area.  As a result, the 2012 SDMP identifies a conveyance and disposal system separate from SSJID facilities for this zone.  The storm infrastructure needed for Zone 39 will be funded and constructed by the developer to first develop in this zone.  Because this infrastructure will be sized to serve all of Zone 39, the developer will be reimbursed the cost of these facilities, less their proportionate share, in accordance with the reimbursement policies in Chapter 2.
19. Construction Sequencing  
The gravity-based sewer systems will be constructed concentrically outward beginning with the infrastructure with the lowest invert elevations and advancing in sequence to the infrastructure with the highest invert elevations.  This approach will be used to ensure that newly installed facilities can be put into service immediately.  For storm drainage facilities, the lowest elevation is the Storm Drain Pump Station in Zone 36.  
7. Sewer Collection 

This chapter provides PFIP information as it pertains to the City sewer collection system.  A summary of the information is as follows: 1) background; 2) facilities and costs; 3) dwelling unit equivalents; 4) fee methodology; 5) fee schedule; and 6) construction responsibilities.
AE. Background

The 2012 Wastewater Collection System Master Plan Update (2012 WWCSMP) has been developed to ensure that the City’s trunk sewer system can cost-effectively meet the demands of development goals adopted in the General Plan with appropriate consideration of construction costs and operation and maintenance issues. 

As part of the 2012 WWCSMP, residential wastewater generation factors (WGFs) for future development were reduced to reflect upcoming water conservation legislation for residential development based on a generation factors study.  The study also focused on reductions of industrial and general commercial WGFs to reflect historical water use data from local businesses.

The 2012 WWCSMP evaluates wastewater conveyance requirements through buildout based on the 2023 General Plan for lands within the PUSA.  Five planning zones have been delineated to define the capital improvements need to serve future growth:  Zones 21, 22, 24, 25, and 26.  See Plate D-1 in Appendix D for a depiction of the sewer zones.
AF. Facilities and Costs

The overall collection sewer strategy consists of a combination trunk sewer gravity collection system with pump or lift stations located along the alignment to convey wastewater to an influent pump station located at the City Wastewater Quality Control Facility (WQCF).  The North Manteca Collection Strategy (NMCS) and South Manteca Collection Strategy (SMCS) will collect flow from areas where future growth is expected. The Central Manteca Collection Strategy (CMCS) will connect the existing collection system to the NMCS.

Construction of the NMCS, SMCS, and CMCS were grouped into potential projects for implementation in the future as part of the City CIP.  The total wastewater collection system CIP construction cost is approximately $54,936,000 of which $5,940,000 is related to existing development and not included in the PFIP fee calculations. 
AG. Dwelling Unit Equivalents

Wastewater generation factors (WGF) are utilized to calculate the anticipated wastewater flows generated by residential, commercial, and industrial development.  The 2012 WWCSMP utilizes updated wastewater generation factors for future residential, commercial, and industrial land uses based on water conservation legislation for residential development and historical water use data from local businesses [3]. 
20. Residential

California approved the 2010 California Green Building Standards Code (CALGreen 2010) which requires new buildings in California to become more efficient by mandating new construction to meet minimum standards.  CALGreen 2010 requires a 20 percent reduction in indoor water use from the 2008 Title 24 baseline. Other legislation and water conservation programs include the 20x2020 Water Conservation Plan, LEED, Senate Bill (SB) 407, and EPA WaterSense® Program, each of which have similar goals in water use reduction and efficiency to CALGreen. 

With the new CALGreen legislation and other water conservation programs, indoor water use (and wastewater flows) is expected to decrease significantly for new residential development. 

21. Commercial

WGFs for general commercial land uses in the City were updated in the 2012 WWCSMP after reviewing historical water usage data from existing commercial developments at Spreckels Park and Big League Dreams.

22. Industrial

WGFs for heavy and light industrial land uses in the City were updated in the 2012 WWCSMP after reviewing historical water usage data from existing industrial developments. 

23. Equivalent Dwelling Units

Based on the WGFs by land use type, Table 7-2 provides the per unit EDU factor for each land use.
Table 7-2    
Summary of Wastewater EDU Factors

	Land Use
	EDU Factor

	VLDR
	1.00

	LDR
	1.00

	MDR
	0.73

	HDR
	0.73

	BIP
	7.50

	CMU
	15.46

	GC
	4.69

	HI
	6.25

	LI
	6.25

	NC
	7.00

	P
	2.50

	PQP
	2.66


AH. Fee Methodology

This section describes the non-PFIP and PFIP fees and also briefly summarizes how project costs are developed.

24. Non-PFIP and PFIP Fees

The City has established a fee structure that allocates costs to construct sewer infrastructure related to new development.  There are two types of fees assessed, non-PFIP fees which have been adopted by separate City resolutions and PFIP fees which are adopted by this document.   Brief descriptions of what are included in the fees are also provided.  Descriptions of the Non-PFIP fees are provided for informational purposes only.  Because these fees are adopted by separate City resolution, policies related to these fees including fee adjustments are identified in other City documents.

c) Non-PFIP Fees

Wastewater Connection Fee:  The WQCF Phase III Expansion Project corrected a number of existing deficiencies at the plant and thus benefited current rate payers.  Based on an analysis of project costs and proposed improvements, the expansion costs were allocated between rate payers and new development.

The Wastewater Connection Fee was imposed in 2003 on new development during the Phase III Expansion in lieu of development impact fees.  The Wastewater Connection Fee varies based on the timing of the development in relation to the Expansion Schedule(s) under construction.  For reference, these fees are outlined in Appendix D, Table D-X.
WQCF Phase 3 Completion Fee:  As part of a sewer rate study in 2007-2008, the connection fee schedule was re-evaluated to account for actual project costs.  The study found that the Wastewater Connection Fee for the Phase III Expansion Project needed to be increased to repay the interfund loan obligations and the additional debt needed to complete the project.  To comply with bonding requirements, a separate fee, called the WQCF Phase 3 Completion Fee, was implemented.  For reference, these fees are outlined in Appendix D, Table D-X.
d) PFIP Fees

The Sewer Collection System Fee will fund the installation of pipelines and pump stations needed to serve future growth.  The fee will also finance administration of the fund and advance planning for system and processing expansion.
25. Facility Costs
Facilities are sized to accommodate the projected flows along the route.  The following method was used to estimate wastewater flow:

· Establish sewer shed boundaries to assign areas which will contribute flow to the trunk sewer.
· Obtain land use information for each shed from the General Plan land use diagram.

· Multiply land use areas within each shed by the corresponding WGF to obtain the projected average dry weather flow (ADWF) for each shed.

· Estimate peak wet weather flow (PWWF) by multiplying the projected ADWF with the peaking factor (PF).  PWWF is the flow used to size trunk sewers, pump/lift stations, and force mains.

Unit costs were developed in the 2012 WWCSMP for sewers, manholes, isolation gates, and other elements identified as recommended improvements.  Construction costs for the NMCS, SMCS, and CMCS were divided by fee zone for each link or element, where applicable.  Costs for the zones contributing to each link were calculated based on ADWF.  
AI. Fee Schedule

The costs of all the facilities included in the NMCS, SMCS, CMCS and the division of construction costs among the fee zones is summarized in Table 7-3.  Table D-X in Appendix D provides a breakdown of the projects and an allocation of projects costs to the individual zones. 
Table 7-3    
Projected Sewer Project Costs by Zone
	Parameter
	Cost, $

	Zone 21
	2,085,337

	Zone 22
	17,048,343

	Zone 24
	25,602,950

	Zone 25
	2,643,490

	Zone 26
	1,606,560

	City Costsa
	5,949,320

	Total Project Costs
	54,936,000


a Portion of project costs to be paid by the City to alleviate existing deficiencies.
The PFIP Sewer Collection System Fees for residential land uses are provided in Table 7‑4.  The fees for non-residential land uses are provided in Table 7-5
Table 7-4    
Summary of PFIP Residential Sewer Collection System Fees

	Land Use
	Fee Per Dwelling Unit, $

	
	Zone 21
	Zone 22
	Zone 24
	Zone 25
	Zone 26

	VLDR
	752
	2,232
	1,809
	785
	1,568

	LDR
	752
	2,232
	1,809
	785
	1,568

	MDR
	550
	1,632
	1,323
	574
	1,146

	HDR
	550
	1,632
	1,323
	574
	1,146


Table 7-5    
Summary of PFIP Non-Residential Sewer Collection System Fees

	Land Use
	$ per Gallon per Day

	
	Zone 21
	Zone 22
	Zone 24
	Zone 25
	Zone 26

	All Non-Residential
	4.70
	13.95
	11.31
	4.91
	9.80


AJ. Construction Responsibilities
The City and developer have responsibilities for construction of sewer facilities as follows:

26. City Responsibilities 
As funds are available, the City will construct the major sewer facilities as shown in the 2012 WWCSMP. If insufficient funds are available, developers may advance construction by providing funding following City approval.  In such an event, developers shall be entitled to reimbursement for costs up to the amount provided in the PFIP when construction is complete.  Reimbursement shall be in accordance with the PFIP reimbursement policy.
27. Developer Responsibilities 
Developers will install, at their expense, local collection and conveyance facilities necessary to serve their development.

28. Construction Sequencing  
The gravity-based sewer systems will be constructed concentrically outward beginning with the infrastructure with the lowest invert elevations and advancing in sequence to the infrastructure with the highest invert elevations.  This approach will be used to ensure that newly installed facilities can be put into service immediately.  For sewer facilities, the lowest elevation is the influent pump station wet well at the WQCF.    
8. Implementation and Administration

AK. Implementation

The sequence of planning for increased capacity and expanded public improvements in the City is as follows:

· General Plan and accompanying growth management policies and ordinances are adopted.

· Facilities master plans are prepared or updated and conceptual engineering is developed to identify the new facilities/capacity that will be needed to serve the forecasted growth.

· These new facilities are then programmed into the City’s CIP, which is updated annually and approved by the City Council at time of fiscal year budget adoption.
AL. Fee Adjustments

The City will review the PFIP and each development impact fee resolution annually.  Any material change in development impact fees as a result of the monitoring and review of the program would be implemented as soon as feasible.  The PFIP is subject to revision due to several factors.  These factors include the difficulty of forecasting the rate and location of development in the City, variations in the cost of construction of public improvements, and variation in the standards that may be applicable in the future to the design of public improvements.  

Annual fee and reimbursement rate adjustments will be calculated in November of each year and will take effect in January of the following year for every year.  The automatic inflation adjustment to the fees and reimbursement rates will be based upon the preceding July 20-Cities ENRCCI.  Should the ENRCCI be revised or discontinued, the Director of Finance will use the revised index or a comparable index, as approved by the City Council, for determining fluctuations in the cost of development.  Statute requires 60 days after adoption before fees become effective.  Therefore, staff will need to process fee increases as early as possible to ensure new fees will be effective the following year.

AM. Fee Program Administrative Requirements

The City intends to assure that the General Plan and the various master plans remain responsive to City policy and changing development conditions.  The City intends to review both the General Plan and the facility master plans on a ten-year cycle.  Policies in an amended General Plan will be incorporated into all of the City facilities master plans and into each development impact fee Ordinance and Resolution.  

9. References
[1]
City of Manteca General Plan 2023 Policy Document, Adopted October 6, 2003; Housing Element Amended June 15, 2010; Circulation Element Amended April 5, 2011

[2]
Manteca General Plan Housing Element, Mintier Harnish Planning Consultants, Adopted June 15, 2010
[3]
Wastewater Generation Factors, Technical Memorandum – Draft, Nolte Associates, Inc., November 2010.

Appendix A
Vacant Land Inventory
Appendix B
Water Data
Appendix C
Storm Drainage Data
Appendix D
Sewer Collection Data


